## TODO (hidden)
TO-DO List
日付 | 関連NMIR No | Item | 変更箇所 | 変更内容 | NMIR関連項目 | 担当 | Due date | 最終対応
2019-06-13 | 20 | 輸出規制事前確認 | クライテリア | 追加：「輸出規制事前確認の責任担当者が明確になっており、輸出までに完了する目途が立っていること」 | CVT前確
21
22
| 24 | CVT前確 | 事前の実施事項 | 変更：20.輸出規制事前確認済 → 20.輸出規制事前確認 | 20
13

## Event Planning Table
|  | Document name |  | Edition | Date of enactment | Written by | [6 empty] | Checked by | Checked by | Approved by
|  | NMIR (New Model Introduction Rule) |  | 19th. Edition | 2020. 3. 31st (19th Edition) | SHES TV Quality Assurance Dept. Quality Assurance Sec. Junichi HIRANO | [6 empty] | SHES TV Quality Assurance Dept. Quality Assurance Sec. Shin, FUJIMORI | SHES TV Quality Assurance Dept. Quality Assurance Sec. Shin, FUJIMORI | SHES TV Quality Assurance Dept. General Manager Satoru. KANNO
No. |  | Event Requirement | Comment |  | Main Event |  | Events by model | [5 empty] | Responsibility for Event/Subject | Responsibility for Approval/Judgment | Outline
|  | Mandatory/Optional |  |  | Relevant Event/Subject |  | Seg1 | Seg2 | Seg3 | Seg4 | Seg5 | Seg6
|  | Mandatory |  |  | Software/Device/Panel Event
PPP : Product Planning / 商品企画 | P1-1 | Mandatory/Optional |  |  | Fix Product Strategy | 商品戦略策定 | [6 empty] | Product Planning | Business responsible person | To decide product strategy/planning.
| P1-2 | Mandatory |  |  | Commercialization PJ Review | 商品化プロジェクトレビュー | [6 empty] | PMO | ー | Review process improvement points for kickoff next fiscal year
| P1-3 |  |  |  | New Key device Selection | 新キーデバイス選択 | [6 empty] | Device Group | Responsible person of Device or/and Responsible person of Product Design | To select new devices at the beginning of model introduction.
| P1-4 | Mandatory/Optional |  |  | Software project kickoff | ソフトウェアプロジェクトKick Off | [6 empty] | Software Design | SW Project manager | To announce PJ kick off to inside/outside SW design and to confirm availability of all necessary information for project start up.
| P1-5 | Mandatory |  |  | Adverse Health Effects: Risk Classification Judgment | 人体影響 リスク判定 | [6 empty] | Product Design | Responsible person of Product Design and responsible person of QA | To assess the risks of health damage caused by adverse health effects and to determine whether or not the risks should be reduced and obtaining approval.
| P1-6 | Mandatory/Optional |  |  | Kick Off Meeting | Kick Off Meeting | [6 empty] | Product Design | ー | To confirm availability of all necessary information for project start up.
| P1-7 | Mandatory |  |  | Basic Concept Meeting | 基本構想会議 | [6 empty] | Product Planning | Business Manager | Towards PPJ, we will form consensus on the winning line of each series based on the change point from the middle term, the Feasibility study result of the mid-term development item
| P1-80 | Mandatory |  |  | Product Planning Judgement (PPJ) / Issue Series Concept Sheet | 商品企画判定 (PPJ) / シリーズコンセプトシート発行 | [6 empty] | Product Planning | Business Manager | To fix product line-up/features/specifications/design.
DQCP : Design and Quality Concept / 設計・品質構想 | P2-1 | Mandatory |  |  | Event planninga/e21 project model registration | 実施イベント計画/e21登録 | [6 empty] | Product Design | Responsible person PD and QA(DR) | To determine what events in NMIR are to be done.
| P2-2 |  |  |  | D4Q Kick Off Meeting | D4Q Kick Off Meeting | [6 empty] | Product Design | Responsible person of Product Design | Set quality targets and clarify indicators of design activities
| P2-3 |  |  |  | D4EX Kick Off | D4EX Kick Off | [6 empty] | Product Design | Responsible person of Product Design | Approval of manufacturable KPI
| P2-4 |  |  |  | SCT（System Confirmation Test) | SCT（System Confirmation Test) | [6 empty] | Product Design | Not specified | System and chassis structure confirmation with a few actual sets / Simulation.
| P2-5 |  |  |  | Patent confirmation | 特許確認 | [6 empty] | Product Design | Business responsible person | To confirm the related patents of the key new features.
| P2-6 | Mandatory/Optional |  |  | Software Design Concept Judgment | Software設計構想判定 | [6 empty] | Software Design | Software General Manager and Software Quality Supporter | To confirm requirements to SW specification and to judge its feasibility.
| P2-7 | Mandatory/Optional |  |  | Software Quality Concept Judgment | Software品質構想判定 | [6 empty] | Software Design | Software Quality Supporter | To define the target of software quality.
| P2-8 | Mandatory/Optional |  |  | Confirm of luminance specifications | 輝度スペック確認 | [6 empty] | Product Design | Responsible person of Product Design
| P2-79 | Mandatory |  |  | Quality Concept Judgment (QCJ) | 品質構想判定 (QCJ) | [6 empty] | Product Design | Responsible person of Product Design and responsible person of QA | To confirm important subjects and their C/M about design quality.
| P2-80 | Mandatory |  |  | Design Concept Judgent (DCJ) | 設計構想判定 (DCJ) | [6 empty] | Product Design | Responsible person of Product Design and responsible person of QA | Target and approve business targets and design plans for the next fiscal year, taking into account the progress and details of the model from the series concept
| P2-81 | Mandatory/Optional |  |  | Panel Design & Quality Concept Judgment | パネル 設計・品質構想判定 | [6 empty] | Panel Mech Design | Senior Manager or above of panel design responsible department | To judge panel specification to meet requirements from product design.
DVP : Design and Verification / 設計・検証 | P3-1 |  |  |  | Pre-confirmation of export regulation | 輸出規制事前確認 | [6 empty] | Product Design | Import/Export Control | To judge Export Trade Control Order and foreign exchange order. *Apply for models manufactured in Japan.
| P3-2 | Mandatory/Optional |  |  | DCE Compliance confirmation meeting | DCE認証確認会議 | [6 empty] | Digital Country Expansion | Responsible person of Digital Country Expansion | To confirm requirement on Broadcast compliance application.
| P3-3 | Mandatory/Optional |  |  | Confirmation Meeting before DVT (Design Verification Trial) | DVT前確認会議 | [6 empty] | Product Design | Project Maneger | To judge design maturity to go to DVT.
| P3-4 |  |  |  | DVT(Design Verification Trial) | DVT(Design Verification Trial) | [6 empty] | Product Design | Not specified | Design Verification Trial
| P3-5 |  |  |  | SAPAPS at DVT stage | SAPAPS at DVT stage | [6 empty] | Product Design | Responsible person of Product Design | To perform SAPAPS on DVT stage.
| P3-6 |  |  |  | CIT(Customer Installation Test) at DVT stage | CIT(Customer Installation Test) at DVT stage | [6 empty] | Product Design | Responsible person of Product Design | To perform CIT on DVT stage.
| P3-7 |  |  |  | DR Meeting for DVT result | DVT DR会議 | [6 empty] | QA(DR) | Responsible person of QA(DR) | To make clear DVT problems and schedule of corrections/improvements.
| P3-8 |  |  |  | OoBE(Out of Box Experience) | OoBE(Out of Box Experience) | [6 empty] | QA | Not specified | To confirm usability from customer view point.
| P3-9 |  |  |  | RIPR check (1st) | RIPRチェック（1回目） | [6 empty] | Product Design | Responsible person of Product Design | To check RIPR items on DVT stage.
| P3-10 |  |  |  | Minimum Product Quality Rules and Requirements check (1st.) | 品質ﾎﾞﾄﾑﾁｪｯｸ(1回目) | [6 empty] | Product Design | Responsible person of Product Design | To check MPQR items on DVT stage.
| P3-11 |  |  |  | Product assessment check (1st.) | 製品ｱｾｽﾒﾝﾄ(1回目) | [6 empty] | Product Design | Responsible person of Product Design | To assess requirement from GEMS on DVT stage.
| P3-12 |  |  |  | Confirmation for Key Device ES | キーデバイス ES確認 | [6 empty] | Device Responsible | N/A | Confirmation of new key device evaluation result
| P3-13 |  |  |  | Judgment of basic PS (Picture/Sound) | 基本画音質判定 | [6 empty] | Product Design | PS Chairman or Vice chairman | To judge basic P/S to meet design policy.
| P3-14 | Mandatory/Optional |  |  | DR Meeting for Panel DVT | パネルDVT DR会議 | [6 empty] | Panel Mech Design | Senior Manager or above of panel design responsible department | To fix CS panel specification.
| P3-15 |  |  |  | Judgment for Key Device MP | キーデバイス量産判定 | [6 empty] | Device Responsible | Responsible person of Device or/and Responsible person of Product Design | Judgment for GO TO MP of key device
| P3-16 | Mandatory/Optional |  |  | α release | αリリース | [6 empty] | Software Design | SW Senior Manager | To verify software implementation progress and to judge whether System Test can be started or not. To confirm all feature's design/implementation/integration completion excluding the exception with PL approval and its quality that can be used for evaluation. If any delay from original schedule, the next action should be judged, for example, the function drop, function postpone, RJM schedule change etc.
| P3-17 | Mandatory |  |  | Confirmation Meeting for Product Safety and Compliance | 安規/コンプライアンス確認会議 | [6 empty] | Product Design | Responsible person of Product Design | To confirm the specifications of the set that may affect on product safety and compliance, to define Safety standards to be applied, and make clear the schedule.
| P3-18 |  |  |  | Compliance indication check (1st) (ICCS/S-PAS) (prior to "Confirmation Meeting before PVT") | コンプライアンス表示チェック(1回目)(ICCS/S-PAS) (PVT前確認会議前) | [6 empty] | Product Design | Responsible person of Product Design | Product design person in charge makes the compliance check sheet before Confirmation Meeting before PVT by using ICCS and confirms a necessary indication requirement.
| P3-19 | Mandatory/Optional |  |  | Recurrence prevention check sheet | 再発防止チェックシート | [6 empty] | Product Design | Responsible person of Product Design | Check sheet for preventing past HW problem
| P3-20 | Mandatory |  |  | Adverse Health Effects:Developing risk reduction measures | 人体影響 リスク低減策策定
| P3-21 | Mandatory/Optional |  |  | Confirmation Meeting before PVT (Production Verification Trial) | PVT前確認会議 | [6 empty] | Product Design | Responsible person of Product Design | Judgment for go to PVT phase （Can be combined with before BOM release confirmation meeting）
| P3-22 |  |  |  | Confirmation Meeting before BOM Release | BOMリリース前確認会議 | [6 empty] | Product Design | Responsible person of Product Design | To confirm BOM can be released.
| P3-23 | Mandatory |  |  | BOM Release | BOM Release | [6 empty] | Product Design | Responsible person of Product Design | Official BOM release.
| P3-24 | Mandatory |  |  | Official Model Release | Official Model Release | [6 empty] | Product Design | Responsible person of Product Design | Official Model Order to Production.
| P3-25 | Mandatory |  |  | Service classification meeting | サービス区分会議 | [6 empty] | Service Promotion | Responsible person of Service Promotion | To confirm preparation status of service related items.
| P3-26 |  |  |  | Field test | Field test | [6 empty] | Product Design | Not specified | To grasp unique problems at specific market and confirm correction/improvement schedule.
| P3-27 | Mandatory/Optional |  |  | PVT (Production Verification Trial) | PVT (Production Verification Trial) | [6 empty] | Product Design | Not specified | Model Verification Trial.
| P3-28 | Mandatory/Optional |  |  | Confirmation before DCE Application | DCE申請前確認 | [6 empty] | Digital Country Expansion | Responsible person of Digital Country Expansion | Check the Digital Broadcast application sample and document with the experts to comply regulations and technical standards of the applicable destination before the sample application.
| P3-29 |  |  |  | Confirmation Meeting before Product Safety Application | 安全規格申請前確認会議 | [6 empty] | Product Design | Responsible person of Safety | Check the safety sample and document with the experts to comply regulations and technical standards of the applicable destination before the sample application.
| P3-30 |  |  |  | SAPAPS at PVT stage | SAPAPS at PVT stage | [6 empty] | Product Design | Responsible person of QA(Safety) | To perform SAPAPS on PVT stage.
| P3-31 |  |  |  | CIT/OoBE at PVT stage | CIT/OoBE at PVT stage | [6 empty] | Product Design | Responsible person of Product Design | Closing CIT / OoBE issues at the PVT stage
| P3-32 | Mandatory/Optional |  |  | DR meeting for PVT result | PVT DR会議 | [6 empty] | QA(DR) | Responsible person of QA(DR) | To make clear PVT problems and schedule of corrections/improvement.
| P3-33 | Mandatory/Optional |  |  | O-Cell DFJ | O-Cell DFJ | [6 empty] | Panel Design | Responsible person of Panel Design | To judge panel design maturity.
| P3-34 | Mandatory |  |  | Judgment of champion panel performance | チャンピオン用パネル性能判定 | [6 empty] | Product Design | PS Chairman or Vice chairman | To confirm the picture performance of the panel and carry out the final confirmation that the performance of the panel can fulfill enough merchantability of the model.
| P3-35 |  |  |  | Judgment of design PS quality | 基本画音質判定 | [6 empty] | Product Design | Leading model : PS(Picture/Sound) Chairman or Vice chairman Derivative model : PS committee. | To judge the final P/S quality in design stage.
| P3-36 |  |  |  | Drop and vibration check | 落下振動チェック | [6 empty] | Product Design (Mechanical) | Responsible person of Product Design | To check PVT set to meet drop/vibration specification.
| P3-37 |  |  |  | Remote commander check | リモコンチェック | [6 empty] | Product Design | Responsible person of Product Design | To check function and performance of remote commander.
| P3-38 |  |  |  | Serviceability check | サービス性基準チェック | [6 empty] | Product Design | Responsible person of Service Promotion | To check serviceability.
| P3-39 |  |  |  | Parts application check | 部品使用基準チェック | [6 empty] | Product Design | Responsible person of Product Design | To check parts with parts application specification.
| P3-40 | Mandatory |  |  | Minimum Product Quality Rules and Requirements check (2nd) | 品質ボトムチェック (2回目) | [6 empty] | Product Design | Responsible person of QA | To check PVT set to meet MPQR items.
| P3-41 | Mandatory |  |  | EMC check | EMCチェック | [6 empty] | Product Design | Responsible person of QA(Safety) | To check PVT set to meet EMC requirement.
| P3-42 | Mandatory |  |  | RIPR check (2nd) | RIPRチェック（２回目） | [6 empty] | Product Design | Responsible person of Product Design | To get approval from Responsible person of Product Design before DFJ.
| P3-43 | Mandatory |  |  | DSS (Design Standard Safety) check | DSS (Design Standard Safety)確認 | [6 empty] | Product Design | Responsible person of Product Design | To check PVT set to meet DSS check sheet.
| P3-44 |  |  |  | TV spec. special exemption request | TVスペック特別許可願い発行 | [6 empty] | Product Design | GPS/RS: Responsible person of Product Design & Sony QA. DSP/DSR: Responsible person of Product Design. | To issue in case of GPS/Reliability standard is not conformed to.
| P3-45 |  |  |  | RIPR special exemption request | RIPR特別許可願い発行 | [6 empty] | Product Design | Responsible person of Product Design | To issue in case of RIPR is not confirmed to.
| P3-46 |  |  |  | Report of pending DR problems | DR残問題報告 | [6 empty] | QA(DR) | Responsible person of QA(DR) | To report design maturity level to plants before PP.
| P3-47 | Mandatory |  |  | Product standard for each model | モデル別製品規格の発行 | [6 empty] | Product Design | Responsible person of Product Design | To define model-unique spec, incl. inspection items at assy line
| P3-48 |  |  |  | Schedule Management of Applications for Energy Regulations | Energy Regulations申請 日程管理 | [6 empty] | Product Design | Responsible person of QA(Energy Saving) | To check power consumption including dispersion to be in spec.
| P3-49 |  |  |  | Product Compliance Assessment Sheet（UC） | Product Compliance Assessment Sheet（UC） | [6 empty] | Product Design | Responsible person of QA(Safety) | To check with Product Compliance Assessment Sheet. *Apply for USA/Canada/Mexico/Argentina models only.
| P3-50 | Mandatory |  |  | Compliance indication check (2nd) (ICCS/S-PAS) (Before DFJ) | コンプライアンス表示チェック(2回目)(ICCS/S-PAS) (DFJ前) | [6 empty] | Product Design | Responsible person of Product Design | Product design person in charge makes the compliance check sheet before Design validation by using ICCS and confirms that indication contents of PVT product are correct.
| P3-51 | Mandatory |  |  | Product assessment (2nd) | 製品ｱｾｽﾒﾝﾄ(2回目) | [6 empty] | Product Design | Responsible person of Product Design | To assess requirement from GEMS.
| P3-52 | Mandatory/Optional |  |  | Product Safety check | Product Safety check | [6 empty] | Product Design | Responsible person of Product Design | Top confirm that Products comply with requirements of the safety standard before DV.
| P3-53 | Mandatory |  |  | Software Release Judgment Meeting | ソフトウェア量産リリース判定会議 | [6 empty] | Software Design | SW Project manager, HW Project manager and Software Quality Supporter | To confirm quality risks identified by software quality activities involving related stakeholders to judge whether software can be released or not.
| P3-54 | Mandatory/Optional |  |  | Panel DFJ (Design Finalization Judgment) | パネルDFJ (Design Finalization Judgment) | [6 empty] | Panel Mech Design | Senior Manager or above of panel design responsible department | To judge panel design maturity.
| P3-55 |  |  |  | DFJ (Design Finalization Judgment) for Power Supply unit | 電源DFJ (Design Finalization Judgment) | [6 empty] | Power Supply System Design | Responsible person of Product Design | To judge the design maturity level of power supply
| P3-56 | Mandatory/Optional |  |  | Localization Process | ローカライゼーションプロセス | [6 empty] | Product Design | Responsible person of Product Design | Prevent any compliance issue caused by localization at Sales Co. or W/H
| P3-57 |  |  |  | Chinese company standard application / registration | 中国企業標準申請/登録 | [6 empty] | Product Design | Responsible person of Product Design | To comply with the common Chinese company action standard. *Apply for models manufactured and sold in China.
| P3-80 | Mandatory |  |  | Design Finalization Judgment (DFJ) | 設計完了判定 (DFJ) | [6 empty] | Product Design | Responsible person of Product Design and responsible parson of QA | To validate set design.
MPP | P4-80 | Mandatory |  |  | Mass Production Judgment (MPJ) for PP | PP量産判定 (MPJ) | [6 empty] | Plant Production Eng. | Responsible person of Plant Production or Plant Production Eng. | To judge PP is ready to start.
IMP : Initial Mass Production / 初期量産 | P5-1 |  |  |  | Judgment meeting for Picture/Sound performance at PP stage | PP画音質判定会議 | [6 empty] | Plant Production Eng. | Responsible person of Plant Production or Plant Production Eng. | To judge that P/S of PP product and that of the design champion are equal.
| P5-2 | Mandatory |  |  | Compliance indication check (Final) (ICCS/S-PAS) | コンプライアンス表示チェック (最終) (ICCS/S-PAS) | [6 empty] | Plant QA | Responsible person of Plant QA | Plant Products Safety person in charge uses the compliance check sheet of the charge model made in ICCS before "Confirmation Meeting before MP" and confirms that indication contents of PP product are correct.
| P5-3 | Mandatory/Optional |  |  | PP Evaluation | 量産先行(PP)評価 | [6 empty] | Plant QA | Responsible person of Plant QA | To execute prescribed evaluations / tests with PP products and judge quality of the mass production products.
| P5-50 | Mandatory |  |  | Mass Production Judgment (MPJ) for MP | MP量産判定 (MPJ) | [6 empty] | Plant Production Eng. | Responsible person of Plant Production or Plant Production Eng. | To judge MP is ready to start.
| P5-51 |  |  |  | Judgment meeting for Picture/Sound performance at MP stage | MP画音質判定会議 | [6 empty] | Plant QA | Responsible person of Plant QA | To judge that P/S of MP product and that of the design champion are equal.
| P5-80 | Mandatory |  |  | Initial Shipping Judgment (ISJ) | 初期出荷判定 (ISJ) | [6 empty] | Plant QA | Responsible person of Plant QA | To judge Products release to the market.
CRP | P6-80 | Mandatory |  |  | Commercialization Completion Judgment (CCJ) | 商品化完了判定 (CCJ) | [6 empty] | Product Design | Responsible person of Product Design | Review model design activities and feed back to next model activities /record design know how.
"○" for events to be implemented
For managing events by model,
put "○" ffor applicable model.
Note on C7: Optional for Derivative model or accessory
Note on C8: Basically Mandatory
Note on A86: Mass Production Preparation / 量産準備
Note on A93: Commercialization Review / 商品化レビュー

## Process Flow Chart
Process Flow Chart
Phase |  | Software |  | Panel | Product Design | Mech | Elec | Device
| Order SW from outsourcing |  | Sony design
Product Planning
商品企画
Design and Quality Concept
設計・品質構想
Design and Verification
設計・検証
Mass Production Preparation
量産準備
Initial Mass Production
初期量産
Commercialization Review
商品化レビュー
Software project
closure
Software mass production
release judgment
Software validation
release judgment
P2-6. Software Design
Concept Judgment
ODM-SW SW Implementation
Start Judgment meeting
P2-7. Software Quality
Concept Judgment
SW requirement (Feature Map)
confirmation meeting
P1-4. Software Project Kickoff
P1-4. Software Project
Kickoff
P2-6. Software Design
Concept Judgment
P2-7. Software Quality
Concept Judgment
P3-16. α release
P3-53. Software Release
Judgment Meeting
Software project closure
P2-81. Panel Design
& Quality Concept
Judgment
P3-14. Panel DVT DR
P3-54. Panel DFJ
P1-1. Fix Product Strategy
P1-6. Kick Off Meeting
P1-7. Basic Concept Meeting
P1-80. Product Planning Judgment /
Issue Series Concept Sheet
Products Plan Confirmation Meeting
P2-1. Event
Planning
P2-3. D4EX Kick Off
P2-4. SCT
P2-5. Patent
confirmation
Product planning MTG
/ PCS Issue
P2-79. Quality Concept
Judgment (QCJ)
P2-80. Design Concept
Judgment (DCJ)
Recommend holding
on the same day
P3-2. DCE compliance confirmation meeting
P3-3. Confirmation Meeting
before DVT
P3-4. DVT
P3-7. DVT DR
P3-13. Judgment of basic PS
P3-17. Confirmation Meeting
for Product Safety and Compliance
P3-21. Confirmation
Meeting before PVT
P3-22. Confirmation Meeting
before BOM Release
P3-23. BOM Release
P3-27. PVT
P3-24. Official Model Release
P3-25. Service classfication meeting
P3-28. Confirmation before
DCE application
P3-29. Confirmation meeting before
product safety application
P3-32. PVT DR
P3-35. Judgment of
design PS quality
P3-34. Judgment of
champion panel
performance
P3-40. MPQR check (2nd)
P3-41. EMC check
P3-42. RIPR check (2nd)
P3-43. DSS (Design Standard Safety) check
P3-47. Product standard for each model
P3-50. Compliance indication check (2nd)
P3-51. Product assessment (2nd)
P3-52. Product Safety check
P3-56. DFJ for
Power Supply unit
P3-80. Design Finalization
Judgment (DFJ)
P4-80. Mass Production
Judgment (MPJ) for PP
P5-50. Mass Production
Judgment (MPJ) for MP
P5-80. Initial Shipping
Judgment (ISJ)
P6-80. Commercialization
Completion Judgment (CCJ)
DRBFM Approval (Development)
Development Reporting meeting
Product Design transition
approval meeting
Cosmetic Design condition submission approval meeting
3D Study meeting ①
DRBFM Approval (Model)
3D Study meeting ②
Handmade review meeting
Mold order approval
Cosmetic Design fix
Mold parts review meeting
Mold parts review meeting
DRBFM Approval (Development)
Design transition
approval meeting
P1-3. New key device
Selection
DRBFM Approval (Model)
Power supply issue meeting (DVT)
B Board issue meeting
(DVT)
P3-12. Confirmation
for Key Device ES
P3-15. Judgment
for Key Device MP
Power supply issue meeting
(PVT)
B Board issue meeting
(PVT)
B Board issue meeting
(PP/MP)

## Application (hidden)
<Purpose> | This is to regulate important quality events and details how they should be controlled for new product introduction.
<Applied | All new products which TV group has business responsibility.
Products> |  | * This is basically applied for ODM/OEM products as well.
<Applied Region> | All over the world. (All design departments and all manufacturing plants)
<Sheet | Event Planning Table: | To show the next items for each control item.
Construction> |  | Mandatory or not, Event name, Control department, Practicing department, Outline
| Application: | To define how "NMIR" is applied. (This sheet)
| Wordings : | To define the meaning on this chart for difficult word, abbreviation, and possibly misleading word.
| Sample: | To explain "Detail" (the next item).
| Common Rule: | To show common rules which are not applied on a particular control item or are applied on a several control items in common.
| Detail: | To define details of each control item. Numbers of the sheets correspond to the ones on "Event Planning Table".
<Responsibility> | TV QA: | To control NMIR.
| Controlling dept: | To control responsible control item. (sheet on NMIR and other documents)
| Practicing dept: | To implement control items and keep the record if indicated.
<Open & View> | NMIR and other documents are open on QMS library.
Authority of its view is transferred from ISO Management Library at first, and maintained by TV QA later on.
<Records> | Records basically must be kept by any way of the follows.
1) Uploaded on e-21, 2) Directly linked from e-21, 3) Described exact location on e-21
<Modification>
Modification Flow
<Audit> | An internal audit is performed once a year. (Only the control item which GM of HQ-TVQA judged to be necessary.)
| Auditor: | TV QA
| Audittee: | Controlling departments (for maintenance of rules), Practicing departments (for its implementation and records)
Drafting
Revision of NMIR
by PIC of NMIR(TVQA)
Approval by GM of TVQA
Issue NMIR
Planning of revision
1st confirmation
by PIC of NMIR(TVQA)
Modify
OK
OK
Final confirmation
by TVQA
Adjustment with related department
Contact PIC of NMIR(TVQA)
When contents for change occurred, the control section plan a revision immediately
If necessary, TVQA held a meeting with the control section and discuss about modification.
Control Section
TVQA
Modify

## Wordings (hidden)
Pre-Confirmation of Export Regulation | When exporting product outside of Japan, justification based on Export Trade Control Order and Foreign Exchange Order is required. Consequently, for the pre-confirmation, “export regulation check sheet” shall be submitted to the Trade Information Control Department to confirm all clear
Safety Regulations | Mandatory and voluntary regulations established in each country and it is indispensable to follow them for sales activities.
Safety Regulatory Requirement | Engineering contents defined in Safety Regulations. Example of Engineering Standard: Electrical Appliance and Material Safety Law (Ministerial order section 1, section 2),UL (60065 Ver.7), FCC (Class-B), CE (EN55013, 55022).
SAPAPS | Usage status in market is assumed at designing stage. The possibility of occurrence of reliability incidents is anticipated. The discussions about the countermeasures for them are completed in advance.
DR | Evaluate completeness of design quality, grasp problems and clarify plan corrective/improvement plan.
Business Responsible Person | General Manager of Business Division or General Manager of Design Section to whom the authority is transferred from General Manager of Business Division
Design Manager | Manager of Design Section or General Manager of Design Section or MGL
Software Design Manager | General Manager of Software Design Section or Manager of Software Design or Software PM to whom the authority is transferred from the General Manager of Software Design Section
DR Manager | Manager of DR section or General Manager of DR section
Safety Manager | General Manager of TVQA (PLAR) or General Manager of each region QA to whom the authority is transferred from General Manager of TVQA) (PLAR: PL Authorized Reviewer)
SP Manager | Manager of SP Section (SP: Service Promotion)
Power supply system Design Manager | Manager of Power supply system Design Section or General Manager of Power supply system Design Section
Quality Manager | Superintendent of quality assurance in the manufacturing plant (e.g. General Manager of Quality Assurance and General Manager of Quality Control)
Production Manager | Superintendent of production in the manufacturing plant (e.g. Senior General Manager and General Manager of Production)

## JDM ODM OEM Definition (hidden)
Reference materials
Definition of JDM/ODM
Definition that is used in TV GP
JDM | Sony is in charge of the verification of the basic system.
(Joint Design Manufacturer) | EMS is in charge of the product design after system verification by Sony.
ODM | EMS is in charge of main development.
(Original Design Manufacturer) | But Sony performs a design requirement and part designation, and performs a quality requirement in considerable range.
OEM | Sony performs all development and designs, and EMS produces it.
(Original Equipment Manufacturer)

## Sample (hidden)
No | 58
Controlling Dept | Quality Assurance
Control Item | Design Validation
Event Requirement | Mandatory
Practicing Dept. | SET Design
Attendees | SET Design, DR, Production Eng
Approvalment | Business Responsible Person
Criteria, Rule, etc. | 1) Product is to be valid for sale (To satisfy requirement of input.) 2) Design validation is to have been solved=No pending design problems (including FT problem). 3 DR remaining problem report shall be approved.
Another Document | Non
Record Name | DV Meeting Minutes
Responsibility | SET Design
Where/How to keep | e-21Web
Keeping Period | 3 Years
Department to manage the rule of this Item
Same number on Event Planning Table
department to practice this item with initiative.
Back to Event Planning Table
If it is necessary to perform all models, "Mandatory"is shown. If it is determined by Event Planning, "○" is shown. If blank, this event is not done for that particular model.
It is also allowed to describe URL which explains detail of the event.
ＳＡＭＰＬＥ
- If all necessary explanation is written on this page, another document is no needed. (Recommendable)
- Otherwise, fill in only minimum necessary explanation on this page, and write a name of another document. In this case, the document should be controlled as well.
A department which is responsible to create/keep the record. In this case, SET design is responsible and keeps it in e 21 Web.
Event Plan. Table

## Design change operation rule (hidden)
This page shows common rules which are not applied on a particular control item or are applied on a several control items in common.
Design change operation rule
1. Purpose
Shall define procedure from planning design change to production introduction at plant in order to prevent quality problems due to the design change.
2. Definition of design change
Design change describes the change of output of design.
Input of design change describes problems countermeasure, performance improvement, cost down, market claim response and request examining issue from production plant, etc.
3. Procedure of design change
(1) Planning of design change
If necessities of design change have occurred, design person in charge will plan design change.
Plan item
1. Reason of change
2. Effect
3. Required evaluation item
Evaluation item will be decided upon confirmation to relative dept in advance.
For presumption of side effect, check with past design information notice, PCN, release notice, DR problem, quality problem, etc.
Gather knowledgeable persons and conduct FMEA if needed.
Especially completely examine the following 7 items.
1) Change of Safety Critical Components 2) Possibility of conflict to regulatory requirement
3) Change of performance 4) Influence on EMC level
5) Awareness of side effect 6) Influence on SAPAPS result
7) Influence towards other related models
If safety critical components change will be required and the contents described in evaluation report issued by approval authority have been changed, submit Design change safety modification form to Product safety assurance section.
(2) Approval of design change examination plan
At first, Block leader will confirm the contents of design change planned by design person in charge. Next, ASE or PIC of Safety will confirm the contents of design change planned by design person in charge. Finally, Design responsible person will confirm the contents of design change planned by design person in charge, modify, etc if needed and approve the start of examination. If implementations have been judged as problem, it will be suspended or reviewed.
(Block leader : Chassis / System / Power supply / Panel / Mecha / Instruction manual etc)
(3) Verification and trial evaluation
Verify according to the approved confirmation item, which have been planned at the previous item (1).Trial evaluation will be conducted as needed.
If there is cause which changes measurement result by design/production variation, inspection will be conducted considering variation. Especially, for the change related to safety critical components and safety critical operation, inspection must be conducted, considering variation.
If design will change after BOM Release or after the release of software mass production, provide notice of design change and/or PCN in order to notify to production plant after completion.
(4) Issue notice of design change
After completion of verification and trial evaluation, design person in charge will issue notice of design change. Each specified format will be used for Electronics Design, Mechanical Design, Software Design for notification format of design change.
Changed contents, verification result of decided item at previous item (1) and urgent of change will be described at the notice of design change.
If there is parts change describe handling of old parts, notice of change attention to Service Div.
Also if prior confirmation (test run) will be judged as required before introducing to production plant, PCN will be issued separately with specified indication to related dept.
(5) PCN
Design person in charge will issue PCN for the following.
1. Change of production condition
2. Prior confirmation (test run) is required
3. Indication notice item, which will not be described to notice of design change
(6) Implementation approval of change
ASE will confirm parts related to safety problem of notice of proposed design change and PCN.
But when a confirmation person and an approval person have a qualification of ASE, a confirmation person and an approval person can perform conformation by ASE. In addition an approval person can perform conformation by the confirmation person.
Design responsible person will confirm verification implemented by Design person in charge and approve notice of design change and/or PCN by confirming whether sufficient effects, preventive measures for side effects have been definitely implemented, necessity of prior confirmation (test run) has been judged.
(7) Notification of design change
Design person in charge will notify the notice of approved design change and/or PCN to all the production plant related to design change and all the related design section.
Also if design change of safety critical components, notify the notice of design change and/or PCN to Product safety assurance section and also to Parts Engineering section.
(8) Judgment of production introduction availability
Production engineering person in charge of production plant who is responsible for acceptance side of design change will confirm of no problem in the result of examination of design change based on notice of design change, PCN issued by Design person in charge.
Request additional information of technical report, design comments, etc to design person in charge as needed.
Also if Production Engineering Dept of production plant or QA Div has been judged as necessary of reevaluation of side effects, Design person in charge will conduct reevaluation of side effects.
Judgment of production introduction availability shall be conducted by person who has the authority of mass production start based on the confirmation result of Production Engineering Division.
4. Design change process flow
5. Design Information Bulletin (DIB) (Sample)
6. Design Change Safety Modification Form
FDPE-02 Form_Design Change Safety Modification (In QMS Library)
Event Plan. Table
Input of design change
Planning of design change
(ex. Design Information Bulletin (DIB))
Verification and trial evaluation
PCN
Notice description of design change
(ex. Release Notice)
Confirmation by production plant
Production introduction
Approval of design change examination plan
Approval of change
Judgment of production introduction availability
Production process
Judge : Person who has the authority of production start
OK
NG
OK
NG
NG
OK
Design person in charge
Judge : Design responsible person
Design person in charge
Process before BOM Release is ti here.
Judge : Design responsible person
Related to EMC/Safety
or Construction Change
Issue Safety Modification Form
Check or Test OK?
No
NG
OK
Yes
ASE
Review
Confirm DIB
Judge : Block leader
Review
Confirm DIB
Judge : ASE or PIC of Safety
NG
NG
OK
OK
Suspend
Review

## P1-1
No. | P1-1 | No. | P1-1
Control Item | Fix Product Strategy | Control Item | 商品戦略策定
Event Requirement | Mandatory/Optional | Event Requirement | Mandatory/Optional
Responsibility | Product Planning | Responsibility | 商品企画
Attendees | Business responsible person or a person in charge appointed by business responsible person, Product Planning., Product Design., Other Related Dept. | Attendees | ビジネス責任者またはビジネス責任者が指名した担当者、商品企画、商品設計、その他関連部門
Approval | Business responsible person | Approval | ビジネス責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | To establish product strategy (business plan, line-up strategy, feature strategy, design strategy and so on) studying with business responsible person, department in charge of design, and related departments in product strategy meeting. | Criteria, Rule, etc. | 商品戦略会議にて、商品戦略（ビジネスプラン、ラインアップ戦略、フィーチャー戦略、デザイン戦略等）をビジネス責任者、設計担当部署並びに関連部署と協議の上、策定する。
Another Document | Not specified | Another Document | Not specified
Record Name | Meeting Minutes and Materials, and Product Concept Sheet | Record Name | 会議議事録、商品コンセプト資料
Responsibility | Product Planning Dept. | Responsibility | 商品企画部署
Where/How to keep | Server of Product Planning Dept. | Where/How to keep | 商品企画部署サーバー
Keeping Period | Not specified | Keeping Period | Not specified
Event Plan. Table

## P1-2
メインイベント | P1-2. 商品化プロジェクトレビュー |  |  |  |  | Main Event | P1-2. Commercialization PJ Review
目的 | 次年度キックオフに向けたプロセス改善点の見直し |  |  |  |  | Purpose | Review process improvement points for kickoff next fiscal year
承認者 | ー |  |  |  |  | Approval | ー
開催部署 | PMO |  |  |  |  | Responsibility | PMO
参加者 | PMO/PM/PDL/商品企画/ABM/事業企画 |  |  |  |  | Atendees | PMO/PM/PDL/Product Planning/ABM/Business Planning
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・当年度PJの改善点が抽出できており、次年度PJへの対策内容が明確であること | 次年度PJキックオフ資料（一部） 会議議事録 | Project |  |  |  | Improvement points of the current year's PJ have been extracted and the content of countermeasures for PJ next year is clear | ・Next year PJ kickoff material (part) ・Conference proceedings
商品企画 | [5 empty] | Product Planning
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | PMO |  |  |  | Responsibility |  | PMO
保管場所・方法 |  | ー |  |  |  | Where/How to keep |  | Not specified
保管期限 |  | プロジェクト終了まで |  |  |  | Keeping Period |  | Project end
Event Plan. Table

## P1-3
No. | P1-3 | No. | P1-3
Control Item | New Key device Selection | Control Item | 新キーデバイス選定
Event Requirement |  | Event Requirement
Responsibility | Device Group | Responsibility | デバイス部署
Attendees | Device Responsible, Product Design, QA, Software Design | Attendees | デバイス責任、商品設計、QA、ソフトウェア設計
Approval | Responsible person of Device or/and Responsible person of Product Design | Approval | デバイスの責任者または商品設計の責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | At the beginning of model development stage, select new device. Confirmation of Device specification Make quality decision item clear | Criteria, Rule, etc. | 次期モデル導入にあたり、新規デバイスを選定する デバイス仕様の確認 品質決済案件の明確化
| Development schedule Development cost Device evaluation result (if possible) Make problem and countermeasure clear (if possible) |  | 開発スケジュール 開発費用 デバイス評価結果（可能なら） 問題点と対応策の明確化（可能なら）
| Basically, this event covers following activities 1) Development Concept 2) Planning Judgment 3) Vender Selection Refer below table about Sponsoring Post and Judge |  | 原則として、以下の内容が実施されていること ①開発構想 ②企画判定 ③ベンダー選定 主催部署と判定者は下記の表を参照のこと
Another Document | Not specified | Another Document | Not specified
Record Name | Presentation Material, meeting minutes | Record Name | 発表資料、議事録
Responsibility | Product Design Group / Device Development Group | Responsibility | デバイス責任部署
Where/How to keep | Server of responsible group and etc. | Where/How to keep | 責任部署サーバー
Keeping Period | 3 years | Keeping Period | 3 years
Event Plan. Table

## P1-4
メインイベント | P1-4. ソフトウェアプロジェクトキックオフ |  |  |  |  | Main Event | P1-4. Software Project Kick off
目的 | PLやSW設計者がプロジェクトのScopeや設計計画やPJ計画を検討できる。 < ソフトウェアをODM開発する場合は任意開催 > |  |  |  |  | Purpose | PL and sw designer start study for deciding requirements scope and make develop plan. < In case of outsourcing SW development : Optional (Not mandatory) >
承認者 | なし |  |  |  |  | Approval | none
開催部署 | ソニーソフトウェア設計 |  |  |  |  | Responsibility | Sony Software Design
参加者 | Sony(SW PM, SW PL, SW TL, SW PJ, SWV) |  |  |  |  | Atendees | Sony(SW PM, SW PL, SW TL, SW PJ, SWV)
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | SWプロジェクトの位置づけ、目的、目標、コンセプト、仮のSWPJ全体計画 | SWプロジェクトの位置づけ、目的、目標、コンセプト、仮のSWPJ全体計画が策定済み。 | SW PJキックオフ会議議事録&発表資料 | Project |  |  | Positioning of the SW PJ objective, goal, concept and temporary over all SW PJ plan. | Positioning of the SW PJ objective, goal, concept and temporary over all SW PJ plan are fixed. | SW PJ kick off meeting minutes and presentation materials
商品企画 | 要件管理プロセスに沿って、要件エントリー |  | プロジェクト計画を左右するような重要なSW要件 |  |  | Product Planning | Entry SW requirement as per requirement management process. |  | Major SW requirements, which affect to project plan.
開発設計 | [5 empty] | Development design
商品設計 | 要件管理プロセスに沿って、要件エントリー |  | 最新の年度モデル量産計画、モデルラインナップ プロジェクト計画を左右するような重要なSW要件 |  |  | Product Design | Entry SW requirement as per requirement management process. |  | muss product plan, model lineup for the model year. Major SW requirements, which affect to project plan.
SW | 要件管理プロセスに沿って、要件エントリー |  | プロジェクト計画を左右するような重要なSW要件 |  |  | SW | Entry SW requirement as per requirement management process. |  | Major SW requirements, which affect to project plan.
Panel | 要件管理プロセスに沿って、要件エントリー |  | プロジェクト計画を左右するような重要なSW要件 |  |  | Panel | Entry SW requirement as per requirement management process. |  | Major SW requirements, which affect to project plan.
品証 | 要件管理プロセスに沿って、要件エントリー |  | プロジェクト計画を左右するような重要なSW要件 |  |  | QA | Entry SW requirement as per requirement management process. |  | Major SW requirements, which affect to project plan.
別途文書 |  | TV SW Process Asset Library |  |  |  | Another Document |  | TV SW Process Asset Library
文書管理 | [5 empty] | Document
記録物 |  | ソフトウェアプロジェクトキックオフ会議議事録，会議発表資料 |  |  |  | Record Name |  | Software Project Kick off meeting minutes and introduced materials
管理部署 |  | ソニーソフトウェア設計 |  |  |  | Responsibility |  | Software Design
保管場所・方法 |  | PJ common portal |  |  |  | Where/How to keep |  | PJ common portal
保管期限 |  | 5年 |  |  |  | Keeping Period |  | 5 years
Event Plan. Table

## P1-5
メインイベント | P1-5. 人体影響 リスク判定 |  |  |  |  | Main Event | P1-5. Adverse Health Effects: Risk Classification Judgment
目的 | 適用対象製品の仕様の承認(設計構想会議、展示会への出展の承認)までに、 人体影響による健康被害のリスクを評価し、低減すべきかを判断、承認を取得している事 |  |  |  |  | Purpose | To assess the risks of health damage caused by adverse health effects and to determine whether or not the risks should be reduced and obtaining approval.
承認者 | 設計責任者/品質責任者 |  |  |  |  | Approval | Responsible person of Product Design and responsible person of QA
開催部署 | 商品設計部門 |  |  |  |  | Responsibility | Product Design
参加者 | 商品設計部門/開発設計部門/企画・MK部門/品証・CS部門 |  |  |  |  | Atendees | Product Design/Development Design/Product Planning/QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・人体影響の判定・記録シートを用いて、チェック項目の該非判定。該当する場合は、リスク分類を実施。 ・判定結果について品質責任者(品質オフィサー)、設計責任者の承認を取得 又は、品質責任者、設計責任者から権限移譲された者 ・承認後又は、QMS-348J-01"人体影響の評価・判断プロセスに関する標準 第1版"施行前のModelで人体影響に関わる変更が生じた場合は、リスク判定、承認を取得。 ・リスク低減策が必要と判断された場合、リスク分類1/2に応じて低減策を検討。 |  | Project |  |  |  | ・Judgment of Adverse Health Effects using a recording sheet. If applicable, carry out risk classification. ・Obtain approval from the quality manager (quality officer) and design manager for the judgment results. Or a person who has been delegated authority from the quality manager or the design manager. ・ After approval, or if there is a change in the model before QMS-348J-01 , the risk assessment and approval are necessity. ・ If it is determined that a risk reduction measure is necessary, consider a reduction measure according to risk category 1/2.
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | ・人体影響の判定・記録シートを用いたリスク判定 ・品質責任者(品質オフィサー)、設計責任者の承認を取得 |  | 人体影響の判定・記録シート |  |  | Product Design | ・Risk assessment using Adverse Health Effects Check and Recording Sheet ・Get the approval of responsible person of product design and responsible person of QA |  | Adverse Health Effects Check and Recording Sheet
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | 人体影響の判定・記録シート |  |  |  | Another Document |  | Adverse Health Effects Check and Recording Sheet
|  | 人体影響の判定の概要書 | [5 empty] | Summary of classification of adverse health effects
文書管理 | [5 empty] | Document
記録物 |  | 人体影響の判定・記録シート |  |  |  | Record Name |  | Adverse Health Effects Check and Recording Sheet
管理部署 |  | 商品設計 |  |  |  | Responsibility |  | Product design
保管場所・方法 |  | e-21 |  |  |  | Where/How to keep |  | e-21
保管期限 |  | 生産終了から10年 |  |  |  | Keeping Period |  | 10 years after on line
| 【目的】 |  |  |  |  | 【Purpose】
| 人体影響による健康被害のリスクを評価し、低減すべきかを判断する。 |  |  |  |  | To assess the risks of health damage caused by adverse health effects and to determine whether or not the risks should be reduced
| 対象：販売、頒布、貸与、展示、体験提供する製品。 ハードウェア、ソフトウェア、コンテンツを含む。 |  |  |  |  | This item applies to the products that companies in the Sony Group sale, distribute, rent, exhibit and provide experiences for.
In addition, the products include hardware, software and contents (regardless of whether they are prototypes or commercially manufactured products).
【適用対象記録方法】
| 各Model、展示会の年間スケジュールに対し実施 |  |  |  |  | 【Applicable recording method】
| e.g. FY21 model(Segment名) |  |  |  |  | Implemented for each model and exhibition annual schedule
E.g. FY21 model (Segment name)
【ルール】
| 1. 人体影響の判定・記録シートを用いて、チェック項目の該非判定。該当する場合は、リスク分類を実施。 |  |  |  |  | 【Rule】
| 2. 判定結果について品質責任者(品質オフィサー)、設計責任者の承認を取得 |  |  |  |  | 1. Judgment of Adverse Health Effects using a recording sheet. If applicable, carry out risk classification.
| 又は、品質責任者、設計責任者から権限移譲された者 |  |  |  |  | 2. Obtain approval from the quality manager (quality officer) and design manager for the judgment results.
| 3. 承認後又は、QMS-348J-01"人体影響の評価・判断プロセスに関する標準 第1版"施行前のModelで、人体影響に関わる変更が生じた場合は、リスク判定、承認を取得。 |  |  |  |  | Or a person who has been delegated authority from the quality manager or the design manager.
| 仕向けの追加での実施は不要。 |  |  |  |  | 3. After approval, or if there is a change in the model before QMS-348J-01 , the risk assessment and approval are necessity.
| 人体影響に関わる変更か否かに関しては、関係者で協議、判断。 |  |  |  |  | 4. If it is determined that a risk reduction measure is necessary, consider a reduction measure according to risk category 1/2.
4．リスク低減策が必要と判断された場合、リスク分類1/2に応じて低減策を検討。
| 下記に該当する製品は、品質オフィサーの承認を得たうえで、リスク判定、その結果に対する承認を省略できる。 |  |  |  |  | For products falling under the following, requirements specified may be omitted after obtaining the approval of the Quality Officer.
| なお省略した根拠は、記録に残す(記録の方法は各事業会社に準じる)。 |  |  |  |  | The rationale for the omission must be documented (the method of documentation of each Business Company must be followed).
| ・QMS-348J-01"人体影響の評価・判断プロセスに関する標準 第1版"の4.1から4.3に定める事項を遵守したプロセスを経て、過去に【対象外】と判定された製品と、仕様と使用方法が同様である製品 |  |  |  |  | ・Products that have same specifications and usage as a product that has been classified as [Exclusion] after going through the process that is in compliance with the requirements specified
| ・QMS-348J-01"人体影響の評価・判断プロセスに関する標準 第1版"の4.1から4.3に定める事項を遵守したプロセスを経て、過去に【リスク分類1】または【リスク分類2】と判定されリスク低減策を実施した製品と、 仕様と使用方法が同様であり、同等のリスク低減策を実施する製品 |  |  |  |  | ・Products that have same specifications and usage as a product that has been classified as [Exclusion] after going through the process that is in compliance with the requirements specifiedProducts that have same specifications and usage as a product that has been classified as [Risk class 1] or [Risk class 2] after going through the process that is in compliance with the requirements specified
過去の製品と仕様、使用方法が同様か否かは、関係者で協議、判断。
Event Plan. Table

## P1-6
＊実施有無の判断はEvent Plannning(P2-1)に基づく
メインイベント | P1-6. Kick off Meeting |  |  |  |  | Main Event | P1-6. Kick off Meeting
目的 | Confirm availability of all necessary information for project start up. プロジェクトを始めるためのキックオフ（体制・会議体・方針の周知） |  |  |  |  | Purpose | Confirm availability of all necessary information for project start up.
承認者 | ー（承認なし） |  |  |  |  | Approval | ー
開催部署 | 商品設計部門/開発設計部門/SHES-M |  |  |  |  | Responsibility | Product Design/Development Design/SHES-M
参加者 | 商品設計部門/開発設計部門/SHES-M/企画・MK部門/経営企画部門/SW設計部門/調達部/品証・CS部門 |  |  |  |  | Atendees | Product Design/Development Design/SHES-M/Product Planning/ Business Planning/ SW Design/Procurement/QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | キックオフ資料 | ・新規Platformの場合は、スケジュールおよび進捗管理計画がたっていること ・新規Platformの場合はBプランが立っていること ・PJの目的、体制、責任の確認を実施すること ・PJ完了までの各イベントのスケジュール確認を実施すること ・開催条件のクライテリアを満足していること ・会議体(エスカレーションルート含む)が決まっていること | 会議議事録 キックオフ資料 | Project |  |  | Kickoff materials | · In the case of the new Platform, the schedule and the progress management plan are maintained · In the case of the new Platform, it is necessary to have B Plan · Conduct confirmation of purpose, structure, responsibility of PJ · Schedule confirmation of each event until PJ completion · Be satisfied with the criteria of the holding conditions · Conference body (including escalation route) has been decided | ・Conference proceedings ・Kickoff materials
商品企画 | 1.商品戦略策定 |  |  |  |  | Product Planning | Product Strategy
開発設計 | ・新規Platformの場合は、デバイススケジュールおよび進捗管理計画 ・Plat Form 決定 P1-3. 新キーデバイス（メインチップ）選定済 |  |  |  |  | Development design | · For the new Platform, the device schedule and progress management plan · Plat Form determination P1-3. New Key Device(Main chip) Selection
商品設計 | 新規Platformの場合はBプランを計画 |  |  |  |  | Product Design | For the new Platform Plan B plan
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計/開発設計/SHES-M |  |  |  | Responsibility |  | Product Planning and Product Design
保管場所・方法 |  | プロジェクトサイト |  |  |  | Where/How to keep |  | Project Site
保管期限 |  | プロジェクト終了まで |  |  |  | Keeping Period |  | Project end
Event Plan. Table

## P1-7
メインイベント | P1-7. 基本構想会議 |  |  |  |  | Main Event | P1-7. Basic Concept Meeting
目的 | 商品企画判定に向けて、中期からの変化点、中期開発アイテムのFeasibility study結果踏まえた各シリーズの勝ち筋についての合意形成を行う |  |  |  |  | Purpose | Towards the Product Planning Judgment (PPJ), we will form consensus on the winning line of each series based on the change point from the middle term, the Feasibility study result of the mid-term development item
承認者 | 事業部長 |  |  |  |  | Approval | Business Manager
開催部署 | 商品企画/商品設計/開発設計 |  |  |  |  | Responsibility | Product Planning/Product Design/Development Design
参加者 | 商品設計/開発設計/企画・MK/経営企画/SW設計/調達 |  |  |  |  | Atendees | Product Design/Development Design/Product Planning/ Business Planning/ SW Design/Procurement
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | 基本構想会議資料 | ・新規要素技術に対してDRBFMを実施し、リスクに対する対策目処が立っていること（DRBFM実施モデルのみ） ・新規要素技術に対し、次年度モデル搭載へのコストが明確であること ・新規要素技術に対し、次年度モデル搭載への設備検討ができていること ・新規要素技術搭載時の制約が明確であること ・新規要素技術のリスクに対する対策スケジュールが明確であること | 会議議事録 基本構想会議資料 | Project |  |  | Basic concept conference material | · Implementing DRBFM against new element technologies and taking measures for risk（for DRBFM model only） · The cost to new model element technology installation is clear. · To be able to investigate the equipment for installing the next year model against the new element technology · Restrictions on incorporating new element technology are clear · The schedule of measures against the risk of the new element technology is clear | ・Conference proceedings ・Basic concept conference material
商品企画 | [5 empty] | Product Planning
開発設計 | 開発報告会 設計移行承認会 |  |  |  |  | Development design | · Development meeting meeting · Design transition approval meeting
商品設計 | P1-6. Kick Off Meeting ・モデルを構成する技術が明確になっていること ・L/Uのフィーチャーリストが明確になっていること（ターゲットの売価・数量 or バリエーションが推定できていること） ・リスク案件が明確であること |  |  |  |  | Product Design | P1-6. Kick Off Meeting · The technology that makes up the model is clarified · The feature list of L / U is clear (It is possible to estimate selling price / quantity or variation of target) · Risk projects must be clear
SW | P1-4. SW PJ Kick Off 会議 |  |  |  |  | SW | P1-4. SW PJ Kick Off Meeting
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品企画/商品設計/開発設計/SHES-M |  |  |  | Responsibility |  | Product Planning/Product Design/Development Design/SHES-M
保管場所・方法 |  | プロジェクトサイト |  |  |  | Where/How to keep |  | Project site
保管期限 |  | プロジェクト終了まで |  |  |  | Keeping Period |  | Project end
Event Plan. Table
Note on M7: e-21に格納

## P1-80
メインイベント | P1-80. 商品企画判定(PPJ) / シリーズコンセプトシート発行 |  |  |  |  | Main Event | P1-80. Product Planning Judgement (PPJ) / Issue Series Concept Sheet
目的 | To fix product line-up/features/specifications/design. 商品ラインアップ並びに、シリーズ/モデルごとのフィーチャー/仕様、商品デザインを策定する |  |  |  |  | Purpose | To fix product line-up/features/specifications/design.
承認者 | 事業部長 |  |  |  |  | Approval | Business Manager
開催部署 | 商品企画 |  |  |  |  | Responsibility | Product Planning
参加者 | 商品設計/開発設計/企画・MK/経営企画/SW設計/調達 |  |  |  |  | Atendees | Product Design/Development Design/Product Planning/ Business Planning/ SW Design/Procurement
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・ターゲット売価、利益目標、モデルコストが算出されていること ・各シリーズ/モデルによる機能/仕様/デザイン/Line-upの完成。SW、システム、アーキテクチャの開発/設計を開始するための情報ができていること ・競合想定ができていること | シリーズ構想書(ver0.9) 会議議事録 商品企画判定会議資料 | Project |  |  |  | · The target selling price, the profit target, and the model cost are calculated · Completion of function / specification / design / Line-up by each series / model. Information to start development / design of SW, system, architecture · Competitive assumption is made | · Series Concept (ver. 0.9) ·Conference proceedings · Product Plan Judgment meeting materials
商品企画 | P1-7. 基本構想会議 |  | 商品企画判定及びシリーズ構想会議資料 |  |  | Product Planning | P1-7. Basic Concept Meeting |  | Product Plan Judgment & Series concept material
開発設計 | [5 empty] | Development design
商品設計 | P2-5. Patent確認: 既存Patent/Software Licenseの使用有無確認 |  |  |  |  | Product Design | P2-5. Patent Confirmation: Confirmation of the existing Patent / Software License has been completed.
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品企画/商品設計/開発設計 |  |  |  | Responsibility |  | Product Planning/Product Design/Development Design
保管場所・方法 |  | ー |  |  |  | Where/How to keep |  | ー
保管期限 |  | ー |  |  |  | Keeping Period |  | ー
Event Plan. Table

## P2-1
No. | P2-1 | No. | P2-1
Control Item | Event planninga/e21 project model registration | Control Item | 実施イベント計画/e21登録
Event Requirement | Mandatory | Event Requirement | Mandatory
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Sony(Product Design, DR, Products Safety, P/S Quality Promotion, Product Planning, Procurement, Plant Production Eng, Product Environment Control, Software Design, Panel Design, Power Supply System Design) | Attendees | Sony(Product Design, DR, Products Safety, P/S Quality Promotion, Product Planning, Procurement, Plant Production Eng, Product Environment Control, Software Design, Panel Design, Power Supply System Design)
Approval | Responsible person PD and QA(DR) | Approval | 商品設計および品質DR責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | Details are specified in the following Appendix "Decision method of events to be implemented" | Criteria, Rule, etc. | 下記の付表「実施イベント決定方法」を参照
| [Registration of e21 Project] |  | [e21プロジェクト登録方法は以下参照]
| ・Open “e21-Web”[URL : http://gcp.sony.com/sites/e21/SitePages/Home.aspx |  | ・“e21-Web”[URL：http://gcp.sony.com/sites/e21/SitePages/Home.aspx]を開く
Another Document | DS005003E e21 Operations Management Standard | Another Document | DS005003E e21 Operations Management Standard
Record Name | Event Planning Table (The first excel sheet of NMIR), e21 PJ registration | Record Name | Event Planning Table (The first excel sheet of NMIR), e21 プロジェクト登録
Responsibility | Product Design | Responsibility | 商品設計
Where/How to keep | e 21 | Where/How to keep | e 21
Keeping Period | 5年 | Keeping Period | 5 years
| Decision method of events to be implemented 1. Purpose Decide Design of new model introduction and events to be implemented based on agreement of each PIC of related department at the stage of design planning by each model. 2. Method (1) Time for Implementation: At the Design Planning (2) Host: Product Design Responsible Department (3) Discussion Participating Department (must): DR, Products Safety, P/S Quality Promotion, Product Planning, Procurement, Plant Production, Product environment Control Discussion Participating Department (If necessary): Software Design, LCD Panel Design, Power Supply System Design |  | 付表 実施イベント決定方法 １．目的 新規導入モデルの設計、及び評価をより効率良く行なうために、各モデル毎に設計計画の段階で、 関係部署の各担当者の合意の基に実施イベントを決める。 ２．方法 (1) 実施時期：設計計画時 (2) 主催 ：商品設計担当部署 (3) 協議参加部署（必須）：品質評価担当部署（DR）、製品安全担当部署、画音質担当部署 協議参加部署（必要な場合）: ソフトウェア設計担当部署、パネル設計担当部署、電源設計担当部署
| 3. Procedure (1) Product Design Responsible Department shall clarify specification of new introduction model. Especially for derivative model, clarify the difference of specification with original model upon clarifying the relationship between original models. (2) Discuss necessary events to be implemented item with each PIC of related department based on specification of introduction model and decide upon agreement. (3) Refer to guide line when "Event Planning Table" is made. |  | ３．手順 (1) 商品設計担当者は、新規導入モデルの仕様を明確にする。特に、派生モデルに関しては、 親モデルとの関係を明確にした上で、親モデルとの仕様の差分を明確にする。 (2) 導入モデルの仕様を基に、必要な実施イベント項目を関係部署の各担当者と協議し、合意を 得た上で決定する。 (3) 実施イベント項目を決める際には、「実施イベントガイドライン」を参考にして協議する。
| (4) Prepare "Event Planning Table" (the first excel sheet of NMIR) based on agreement result. Precaution of when preparing Event planning list 1) If derivative model, attach material clarifying the difference of specification with original model. 2) Describe in the comment column the reason about unimplemented item. 3) Describe in the comment column if there is a special instruction about items to be implemented. 4) Describe in the comment column if design will do evaluation. However, DR shall confirm evaluation result. |  | (4) 合意結果を基に、「実施イベント表」（NMIRの最初のシート）を作成する。 「実施イベント表」作成時の注意事項 1) 派生モデルの場合は、親モデルとの仕様の差分を明記した資料を添付する。 2) 実施しない項目に関しては理由をコメント欄に記入すること。 3) 実施する項目に関して特記事項がある場合はコメント欄に記入のこと。 4) 設計が評価を行なう場合は、その旨をコメント欄に記入すること。ただし、評価結果は DRが確認すること。
| (5) If Event Planning Table will be completed, receive an approval of Design Manager and DR manager, deliver to the related department, and Plant production engineering upon receiving confirmation of design evaluation responsible department (6) Also delver planning sheet to e21. (7) When confirmation meeting before DVT and PVT have been conducted. If there is change point, discuss with related person whether change of Event planning sheet is necessary or not. |  | (5) 「実施イベント表」が完成したら、商品設計担当責任者の承認をもらい、品質評価担当部署（DR）の承認をを得た上で、関連部署と製造事業所製技に配布する。 (6) 「実施イベント表」をe21事務局にも配布する。 (7) DVT前確認会議とPVT前確認会議が行なわれた時は、その際に、設計仕様に変更点が発生していない かどうかを確認する。変更点がある場合は、「実施イベント表」の変更が必要ないかどうかを関係者で協議する。
| (8)After deciding on the implementation event, issue the "e21" project registration form. |  | (8)実施イベント確定後、“e21”プロジェクト登録書を発行する。
| Guide Line |  | ガイドライン
| Please confirm the " Event Guideline" sheet. |  | "Event Guideline"シート参照
| Note-1: In case a model was transferred between Production plants. (Including Knock Down production) |  | 注記）製造事業所間で機種移管する場合（Knock Down生産も含む）
| -New chassis for the plant of transfer destination: Follow new model introduction events as model classification “I” of Common Design PQMR |  | ・移管先の事業所として新シャーシの場合は共通設計PQMR規定のモデル区分Ⅰ相当の導入イベント管理を行う。
| -Derivative Model for the plant of transfer destination: Follow new model introduction events as model classification “II” of Common Design PQMR |  | ・移管先の事業所として派生モデルの場合は共通設計PQMR規定のモデル区分Ⅱ相当の導入イベント管理を行う。
Former
Former
Event Plan. Table

## P2-2
審査会 | P2-2. D4Qキックオフ |  |  |  |  | Control Item | P2-2. D4Q kick off
目的 | 品質目標を定め、設計活動の指標を明確にする |  |  |  |  | Purpose | Set quality targets and clarify indicators of design activities
承認者 | 設計部長/品証部長 |  |  |  |  | Approval | Responsible person of Product Design
開催部署 | 商品設計 |  |  |  |  | Responsibility | Product Design
参加者 | 商品設計・品証 |  |  |  |  | Atendees | Product Design・QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・品質目標値(設計VOC/品証VOC/DVT/PVT問題件数、MP Rework)が設定され、その設計計画ができていること ・前年度のプロセスレビュー（試作時問題） を実施し、改善方針が決まっていること ・前年度の導入時および市場問題の再発防止策が決まっていること | 会議議事録 発表資料 | Project |  |  |  | · The quality target value (VOC of Design and QA / number of DVT / PVT problems, MP Rework) and Design plan has been set · Conducted process review (at trial stage problem) of the previous fiscal year and decided improvement policy · The measures to prevent the recurrence of the previous year's problem have been decided | Conference proceedings Briefing paper
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | ・モデルリスクアセスメント(リスク洗い出しおよび担当部署決定） P1-80. 商品企画判定 ・DRBFMでのリスク抽出、ランク付け ・前年度のプロセスレビュー ・前年度の問題点レビュー ・設計VOC |  | D4Qキックオフ資料 |  |  | Product Design | ・Model risk accessment (Define risk and R&R) P1-80. Product Plan Judgment · Risk extraction and ranking at DRBFM · Process review of the previous year · Issues review of the previous year · Design VOC |  | D4Q kickoff material
SW | [5 empty] | SW
Panel | [5 empty] | Panel
デバイス | [5 empty] | Device
品証 | ・品証VOC |  |  |  |  | QA | ・QA VOC
文書管理 | [5 empty] | Document
記録物 |  | 発表資料・議事録 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 5年 |  |  |  | Keeping Period |  | 5years
Event Plan. Table

## P2-3
メインイベント | P2-3. D4EXキックオフ |  |  |  |  | Main Event | P2-3. D4EX Kick Off
目的 | 製造性のKPI承認 |  |  |  |  | Purpose | Approval of manufacturable KPI
承認者 | 設計責任者 |  |  |  |  | Approval | Responsible person of Product Design
開催部署 | 商品設計 |  |  |  |  | Responsibility | Product Design
参加者 | 商品設計・製造 |  |  |  |  | Atendees | Product Design/Manufacture
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  |  生産性活動内容がクリアであること（DCMに向けての活動内容がクリアであること）  スケジュールと活動計画が確立されていること  KPIが明確に定義されていること（承認取れなければDCMに持ち込み） | KPI（承認取れなければDCMに持ち込み） 議事録 ・発表資料 | Project |  |  |  |  The productivity activity content is clear (the activity content for DCM is clear)  The schedule and activity plan have been established  The KPI has been clearly defined (it is brought to DCM unless approved) |  KPI (bring it to DCM if you can not approve) Minutes minutes ·Briefing paper
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | P1-80. 商品企画判定 ※設計構想判定の前に実施する |  | D4EXキックオフ資料 |  |  | Product Design | P1-80. Product Planning Judgment (PPJ) ※Execute before design concept judgment |  | D4EX kickoff material
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 発表資料・議事録 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | プロジェクト終了まで |  |  |  | Keeping Period |  | Project end
Event Plan. Table

## P2-4
No. | P2-4 |  |  | No. | P2-4
Control Item | SCT（System Confirmation Test) |  |  | Control Item | SCT（System Confirmation Test)
Event Requirement |  |  |  | Event Requirement
Responsibility | Product Design |  |  | Responsibility | 商品設計
Attendees | not provided |  |  | Attendees | not provided
Approval | Not specified |  |  | Approval | Not specified
Acceptation for ODM | #REF! |  |  | Acceptation for ODM | #REF!
Criteria, Rule, etc. | see below |  |  | Criteria, Rule, etc. | see below
Another Document | non |  |  | Another Document | non
Record Name | not provided |  |  | Record Name | not provided
Responsibility | not provided |  |  | Responsibility | not provided
Where/How to keep | not provided |  |  | Where/How to keep | not provided
Keeping Period | not provided |  |  | Keeping Period | not provided
| Objective |  | *System confirmation |  | 目的 |  | ・システム検証
|  |  | *Chassis structure confirmation by using real set (small number of set existed) |  |  |  | ・少数実機によるシャーシ構造検討
|  |  | *investigation by using simulation tool |  |  |  | ・シミュレーションを用いた検討
| Criteria at start | HW | *new device evaluation finished and decided to go |  | SCT開始時のクライテリア | HW | ・新規デバイスの評価完了、導入判断済み
|  |  | *all signal pass can be confirmed |  |  |  | ・すべての基本信号パスが確認可能
|  |  | *build up the HW for SW development |  |  |  | ・SWの開発に使用できるHWの作成可能
|  | SW | *SW for new device is driver + PC control level |  |  | SW | ・新規デバイス用SWはドライバ＋PCコントロールレベル
|  |  | *another request is necessary for transients confirmation software |  |  |  | ・トランジェント確認に必要なコントロールは個別要求
|  |  | *function is limited but stability is enough (no hung up by general operation) |  |  |  | ・限定機能だが、安定度は高い（ハングアップしない）
|  | Panel | *operation check is available with WS or last year's sample |  |  | パネル | ・WSまたは去年のサンプルで動作確認可能
|  |  | *set style Panel evaluation with last year's chassis |  |  |  | ・去年のシャーシとの組み合わせでセット評価
|  | Mechanical | *Hand made parts for structure confirmation |  |  | メカ | ・構造確認用の手作り品
| Guideline of activities |  | *System verification for each model by changing combination of parts and SW |  | アクティビティのガイドライン |  | ・部品やSWの載せ替えにより各地域の各モデルについてシステム検証を行う
|  |  | *Model simulation by combination of board and software |  |  |  | ・ボードとソフトの組み合わせによりモデルシミュレーションを行う
|  |  | *make HW for SW development platform |  |  |  | ・SWの開発プラットフォーム用HWとして作成
|  |  | *operation check of new device on system |  |  |  | ・システム上で新規デバイスの動作確認
|  |  | *basic investigation for heat and EMI (chassis structure decision) |  |  |  | ・熱、輻射の基礎検討（シャーシ構造の決定）
|  |  | *Parts count, variety, PWB size and cost confirmation |  |  |  | ・部品点数、品種、基板面積、コストの確認
|  |  | *SPEC verification of SW/HW (SPEC confirmation by real set) |  |  |  | ・SW/HWの仕様検証（仕様の現物確認）
|  |  | *confirm SW performance |  |  |  | ・SWのパフォーマンス確認
| Required output |  | *newly introduced HW, for example PWB and device confirmed （Core, VSW, DDC, power supply, Audio, SubM, ETher, USB HUB） |  | 要求されるアウトプット |  | ・基板やデバイスなど新規HW確認済み（Core, VSW, DDC, 電源, Audio, SubM, ETher, USB HUB）
|  |  | *basic structure of chassis is fixed from heat and EMI point of view |  |  |  | ・熱、EMIの観点から、シャーシの基本構造決定済み
|  |  | *HW completion level is good enough to have Full DR at DVT (ex : all pass confirmation) |  |  |  | ・DVTでFull DRができるレベルにHWの完成度が上がっていること（全パス確認など）
|  |  | *SW specification is fixed for DVT |  |  |  | ・DVTに必要なSW仕様確定
|  |  | *plan of supply SW for DVT assy is clear also this SW have the function and stability to have Full DR |  |  |  | ・Full DR可能な機能と安定度を持ったSWがDVTのAssyに供給可能な見通しができている
Event Plan. Table

## P2-5
No. | P2-5 | No. | P2-5
Control Item | Patent confirmation | Control Item | 特許確認
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | Product Design
Attendees | Intellectual Property Promotion, Product Design | Attendees | 知財推進、商品設計
Approval | Business responsible person | Approval | ビジネス責任者 （PVT前確認会議にて承認）
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | [ Clearance ] Confirm all the patent search has been started at the design concept. Make sure that it is clear with patent(or direction desided, if not cleared) by B4PVT. [ Patent ] Confirm the usage of existing Patent/Software License at the series concept. Confirm any addition of new Patent/Software License each design milestone(B4DVT/B4PVT/DFJ) *The procedure is as follows | Criteria, Rule, etc. | クリアランス： 設計構想時に全案件他社特許調査に着手できている事 及び B4PVTまでに クリアランス確認/対応方法の確立 が出来ている事 Patent： シリーズ構想時に既存Patent/Software Licenseの使用有無の確認が終わっている事 及び 設計マイルストン毎に新規案件追加の有無が確認出来ている事 *手順は以下の通りです
Another Document | Compliance master list | Another Document | コンプライアンスマスターリスト
Record Name | The record of the patent confirmation and the opinion. (Not to open) | Record Name | 特許確認見解の記録 （非公開）:クリアランスチェックシート
Responsibility | Intellectual Property Promotion | Responsibility | 知財推進
Where/How to keep | - | Where/How to keep | -
Keeping Period | 3 years | Keeping Period | 3年
*Procedure |  | *手順
Event Plan. Table

## P2-6
メインイベント | P2-6. ソフトウェア設計構想判定 |  |  |  |  | Main Event | P2-6. Software Design Concept Judgment
目的 | プロジェクトの要件と日程のコミットメントを確立すること。 |  |  |  |  | Purpose | Establish commitment of requirement scope and its plan.
承認者 | ソニーソフトウェア設計統括部長，ソフトウェア品質推進者 |  |  |  |  | Approval | Sony Software General Manager and Software Quality Supporter
開催部署 | ソニーソフトウェア設計 |  |  |  |  | Responsibility | Sony Software Design
参加者 | SW PM, SW PL, SW TL, SWV, HW PM, HW PL, 商品企画, QA |  |  |  |  | Atendees | SW PM, SW PL, SW TL, SWV, HW PM, HW PL, Product Planning, QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ＊プロジェクトの計画と方針は明確に定義されていること。 *プロジェクトで対応する要件範囲(以下、要件範囲と称す)が明確であること。 *要件範囲におけるUX関連要件の顧客価値が明確であること。 ＊要件範囲を実現するために、設計/品質活動が適切に計画されていること。 ＊プロジェクト全体の要件、スケジュール、品質、およびコストに影響を与える可能性のある大きなリスクと問題に対しては、適切な措置が計画されていること。 | 議事録＆発表資料 | Project |  |  |  | - Project plan and policy must be defined clearly. - Scope of requirements(Requirement Scope) for the Project is clrarified. - Cutomer's value of UX releated requirements in Requirement Scope is clarified. - Design and quality activity are planned appropriately to realize Requirement Scope. - Proper actions for to great risks and issue that will impact requirement, schedule, quality and cost of the whole project, are already planned. | Minutes and presentation materials
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | ＜SW開発が外部委託の場合＞ 委託先と事前にSW設計構想の確認・合意を行う |  | FDP-STDE-01B Form_Accessibility Check Sheet ACS Regulation FDP-STDE-01C Form_Accessibility Check Sheet UI Regulation |  |  | SW | < In case of outsourcing SW development > It is necessary to have confirmation and agreement in advance with contractor(s) on SW Design Concept. |  | FDP-STDE-01B Form_Accessibility Check Sheet ACS Regulation FDP-STDE-01C Form_Accessibility Check Sheet UI Regulation
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | TV SW Process Asset Library |  |  |  | Another Document |  | TV SW Process Asset Library
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
管理部署 |  | ソニーソフトウェア設計 |  |  |  | Responsibility |  | Software Design.
保管場所・方法 |  | PJ common portal |  |  |  | Where/How to keep |  | PJ common portal
保管期限 |  | 5年 |  |  |  | Keeping Period |  | 5 years.
| クライテリアの詳細 | *プロジェクトの計画と方針は明確に定義されていること。 - プロジェクトの対象範囲，開発するソフトウェア/成果物の定義，機能概要，スケジュール，以降のイベントの日程（例：UXレビュー），開発体制，リソース計画，ソフトウェアサイズ/労力の見積もり，ハードウェア/ソフトウェアの配布計画 - パフォーマンス，サードパーティソフトウェア，製品セキュリティ，製品のプライバシー，アクセシビリティなどに対する要求 |  |  |  |  | Details of Criteria | * Project plan and policy must be defined clearly. - Project scope, definition of software/outputs to be developed, feature abstract, schedule, dates of following events (ex. UX Review), development organization, resource plan, estimation of SW size/efforts, delivery plan of HW/SW - Requests for performance, third party SW, Product security, Product privacy, accessibility, etc.
|  | *要求管理プロセスに基づいて定義された要求を実現するために、プロジェクトが適切に計画されていること。 - スケジュール調整，開発するソフトウェアのサイズ，およびリソースの見積もり | [5 empty] | * Project planning is completed appropriately to realize requests that are defined based on requirement management process. - Coordination of schedule, SW size to develop, and resource estimation.
|  | * プロジェクト全体の要件、スケジュール、およびコストに影響を与える可能性のある大きなリスクと問題に対して、適切な措置がすでに取られ効果が出ていること。 - 取り上げられたリスクは、常にリスクチェックリストを使用して完全にカバーされている - 優先度の高いリスクを軽減するための行動が定義されており、責任者が明確である | [5 empty] | * Proper actions are already taken and becoming effective to great risks and issues that will impact requirement, schedule, and cost of the whole project. - Risks picked up are always kept fully covered by using risk check list. - Actions to reduce high priority risks are defined and responsible persons are clear.
Event Plan. Table

## P2-7
メインイベント | P2-7. ソフトウェア品質構想判定 |  |  |  |  | Main Event | P2-7. Software Quality Concept Judgment
目的 | ソフトウェア品質目標を定義し、それを達成するのに必要な計画の妥当性を検証し、ソフトウェア品質活動が開始可能かを判断する。 |  |  |  |  | Purpose | Define the target of software quality, verify the validity of the plan necessary to achieve it, and judge whether software quality activities can be started or not.
承認者 | ソフトウェア品質推進者 |  |  |  |  | Approval | Software Quality Supporter
開催部署 | ソニーソフトウェア設計 |  |  |  |  | Responsibility | Sony Software Design
参加者 | SW PM, SW PL, SW TL, SWV, HW PM, HW PL, QA |  |  |  |  | Atendees | SW PM, SW PL, SW TL, SWV, HW PM, HW PL, QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | - 妥当なソフトウェア品質目標が定義されていること。 - ソフトウェア品質活動の計画と方針が明確であること。 - 品質目標を達成するために有効なソフトウェア品質活動計画が立てられていること。 - プロジェクト全体の品質に影響を与えるような大きなリスクや問題に対しては、適切な措置が計画されていること。 | 議事録＆発表資料 | Project |  |  |  | - Valid target of software quality is defined. - Plan and policy for software quality activity are clear. - Valid software quality activity plan is defined to achieve quality target. - Proper actions for to great risks and issue that will impact requirement, schedule, quality and cost of the whole project, are already planned. | Minutes and presentation materials
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | ＜SW開発が外部委託の場合＞ 委託先と事前にSW品質構想の確認・合意を行う |  |  |  |  | SW | < In case of outsourcing SW development > It is necessary to have confirmation and agreement in advance with contractor(s) on SW Quality Concept.
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | TV SW Process Asset Library |  |  |  | Another Document |  | TV SW Process Asset Library
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
管理部署 |  | ソニーソフトウェア設計 |  |  |  | Responsibility |  | Software Design.
保管場所・方法 |  | PJ common portal |  |  |  | Where/How to keep |  | PJ common portal
保管期限 |  | 5年 |  |  |  | Keeping Period |  | 5 years.
| クライテリアの詳細 | * 妥当なソフトウェア品質目標が定義されていること。 |  |  |  |  | Details of Criteria | * Valid target of software quality is defined.
|  | * ソフトウェア品質活動の計画と方針が明確であること。 - 設計/実装/テストスペックシート/テスト計画のレビュー，ガイドライン/チェックリストの作成計画，UX(ユーザビリティ)のテスト計画，静的分析の実行計画など | [5 empty] | * Plan and policy for software quality activity are clear. - Review plan for design/implementation/test spec sheet/test plan, Create plan for guideline/check list, Test plan for UX quality (Usability), Execution plan for static analysis , etc.
|  | * 品質目標を達成するために有効なソフトウェア品質活動計画が立てられていること。 - 開発規模，テストケース数，不具合予測，工数見積の一貫性 | [5 empty] | * Valid software quality activity plan is defined to achieve quality target. - Development size, number of test cases, defects, effort estimation consistency.
|  | * プロジェクト全体の品質に影響を与えるような大きなリスクや問題に対しては、適切な措置がすでに取られ効果が出ていること。 - 取り上げられたリスクは、常にリスクチェックリストを使用して完全にカバーされている - 優先度の高いリスクを軽減するための行動が定義されており、責任者が明確である | [5 empty] | * Proper actions are already taken and becoming effective to great risks and issues that will impact the quality of the whole project. - Risks picked up are always kept fully covered by using risk check list. - Actions to reduce high priority risks are defined and responsible persons are clear.
Event Plan. Table

## P2-8
メインイベント | P2-8. 輝度スペック確認 |  |  |  |  | Main Event | P2-8. Confirmation of Luminances specification
目的 | 輝度値が当年度のLUの上下間、また前継後継モデル間で整合が取れていること |  |  |  |  | Purpose | To consistent luminance value of model from high-end thru to low-end in Lineup and forward and backword between previous and current year
承認者 | PM |  |  |  |  | Approval | Project Manager
開催部署 | 商品設計 |  |  |  |  | Responsibility | Product Design
参加者 | PJメンバー |  |  |  |  | Atendees | PJ Members
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ◆実施事項 輝度仕様決定プロセスに則って、DCJまでにTGT輝度（＋視野角・色域）を一覧化する。 最終Typical輝度TGTにリバイスし、PVT前確にてPM承認を得る。 ※TGT改版が必要になった場合、Panel Spec Fixedのクライテリアに従い、PVTにて実機確認し、必要に応じて設計部長承認を得てリストを更新する。変更時の承認プロセスは、輝度決定プロセス資料に従う。 | 輝度スペック管理リスト | Project |  |  |  | ◆What PDL should do： List the TGT luminance (+ viewing angle and color gamut) up to DCM according to the luminance specification decision process. Revise to the final Typical Luminance TGT and get PM approval at PVT. ※According to the criteria of Panel Spec Fixed, it shall be approved by Design General Manager. Check the actual TV Set by PVT and update the list as needed. refer to decision process if luminance TGT is changed from original. | Luminance Specification management list
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 輝度スペック管理リスト |  |  |  | Record Name |  | Luminance Specification manangement list
管理部署 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | 年度別プロジェクトサイト |  |  |  | Where/How to keep |  | Project site in each year
保管期限 |  | - |  |  |  | Keeping Period |  | -
Event Plan. Table

## P2-79
| No. | P2-79 |  | No. | P2-79
Control Item |  | Quality Concept Judgment (QCJ) | Control Item |  | 品質構想判定 (QCJ)
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | 商品設計
| Attendees | Product Design, Quality Promotion, DR, Device |  | Attendees | Product Design, Quality Promotion, DR, Device
| Approval | Responsible person of Product Design and responsible person of QA |  | Approval | 商品設計責任者/品証責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | By D4Q/DRBFM management chart, make a concern matter in the design quality and the countermeasure clear. (Include Items of QB, TV SPEC etc.) The details of the countermeasure are made clear by the design plan. 1. The type of D4Q/DRBFM management chart 1) Prevention of recurrence 2) Prevention |  | Criteria, Rule, etc. | D4Q/DRBFM管理表により、設計品質上の懸念事項及びその対応策を明確にする。 対応策の詳細は、設計計画にて明確にする。 １、D4Q/DRBFMの種類 1) 再発防止 2) 未然防止
|  | 2. Risk sampling method FMEA, Market data analysis, DRBFM |  |  | ２、リスク抽出方法 FMEA、市場データ分析
|  | 3. Item of D4Q/DRBFM management chart Item which is mentioned in the following. |  |  | ３、D4Q/DRBFM管理表の記入項目 下記に記載されている項目
|  | 4. Progress confirmation method Confirm progress in Confirmation before PVT and Design Finalization. Measure be completed by DFJ |  |  | ４、進捗確認方法 PVT前確認、DFJにおいて進捗確認を行なう。 DFJまでに方策が完了すること。
| Another Document | Non |  | Another Document | Non
Record | Record Name | D4Q/DRBFM management chart | Record | Record Name | D4Q/DRBFM management chart
| Responsibility | Sony Product Design |  | Responsibility | Sony Product Design
| Where/How to keep | Server of Product Design Dept. |  | Where/How to keep | Server of Product Design Dept.
| Keeping Period | 5 years. |  | Keeping Period | 5 years.
(sample)
（サンプル）
1. Prevention of recurrence
1. 再発防止
| 2. Prevention |  |  | 2. Prevention
Event Plan. Table

## P2-80
メインイベント | P2-80. 設計構想判定 (DCJ) |  |  |  |  | Main Event | P2-80. Design Concept Judgent (DCJ)
目的 | 商品企画判定(PPJ)からのモデルの進捗状況・詳細を加味し、次年度ビジネスのターゲットと設計プランを設定・承認する |  |  |  |  | Purpose | Target and approve business targets and design plans for the next fiscal year, taking into account the progress and details of the model from Product Plan Judgment (PPJ).
承認者 | 設計責任者/品質責任者 |  |  |  |  | Approval | Responsible person of Product Design and responsible person of QA
開催部署 | 商品設計 |  |  |  |  | Responsibility | Product Design
参加者 | 商品設計/開発設計/企画・MK/経営企画/SW設計/調達/品証・CS/事業所 |  |  |  |  | Atendees | Product Design/Development Design/Product Planning/ Business Planning/ SW Design/Procurement/QA/Plant
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | 設計構想会議資料 | *品質構想がクリアなこと *コンプライアンス（安規 [セット認証/電源、パネル、他モジュール認証]/DCE/その他認証アイテム）についての計画、担当者がクリアなこと （コンプライアンスマスターリストの作成） *スケジュールと活動計画が確立されていること *KPIが明確に定義されていること *バイタルセンシング製品への該当判断 （該当製品の場合，QMS-345 Appendix-1 商品企画フェーズに記載の7項目の実施し、設計構想フェーズに記載の6項目についてDVT前確認会議までに完了する計画が立っていること。） *人体影響のリスク判定実施、承認されている事 (リスク低減策が必要と判断された場合、リスク分類1/2に応じて低減策を検討。) *品質ボトムチェックシートの設計構想時の判断項目へ合意されること。 *Key Device判定の対象(検定承認品以外)が選定されていること | 議事録＆発表資料 | Project |  |  | Design Concept Meeting Material | *Quality Concept is clear. *Plan of Compliance is clear.(Safety standard[Set,PSU,Panel,other module] / DCE / other certified items、the person in charge is clear (creation of Compliance master list)) *Clear schedule and active plan is established. *KPI is defined clearly. *Applicable judgement Vital-sensing Product or not.(If applicable, the 7 tasks described in the Product planning phase of QMS-345 Appendix-1 should be implemented, and the 6 tasks described in the Product design phase should be planned to be completed by the confirmation meeting before DVT.) *Implementation of risk assessment for Health effects and approval the result. (If it is determined that a risk reduction measure is necessary, consider a reduction measure according to risk category 1/2.) *To be agreed upon the judgment items at the design concept of MPQR Check Sheet *Select the target of Key Device judgment (except for Parts Approval products) | Minutes and presentation materials
商品企画 | P1-80. シリーズ構想書（ver.1.0)発行 |  |  |  |  | Product Planning | Series concept Sheet (ver.1.0) issued
開発設計 | [5 empty] | Development Design
商品設計 | P1-5.人体影響 リスク評価 P2-1. 実施イベント計画 P2-5. Patent確認: クリアランス他社特許調査着手 P2-79. 品質構想会議 P2-2. D4EXキックオフ P2-8. 輝度スペック確認: シリーズ間、年度間での整合を確認し、ターゲット値を設定する（B4PVT,DFJで進捗確認） ・FDR027-03 Form 品質ボトムチェックシート P3-8. OoBE対象モデルの有無確認 |  | P2-5. コンプライアンスマスターリスト / クリアランスチェックリスト 人体影響の判定・記録シート |  |  | Product Design | P1-5. Adverse Health Effects Confirmation & Risk judgment P2-1. Event Plan P2-5. Patent confirmation (Clearance:Initiate patent searches for competitors and third parties) P2-79. Quality Concept Meeting P2-2. D4EX kickoff -Confirm the consistency of luminance specifications inbetween series and previous models and set the target value. -FDR027E-03 Form Minimum Product Quality Rules & Requirements Check Sheet P3-8. Confirmation of OoBE target models |  | P2-5. Compliance master list / ClearanceCheckList Adverse Health Effects Check and Recording Sheet
SW | P2-6. SW 設計構想会議 P2-7. SW 品質構想会議 |  |  |  |  | SW | P2-6. Software Design Concept Meeting P2-7. Software Quality Concept Meeting
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
管理 | ビジネスシミュレーション実施 |  |  |  |  | Business Planning | Business simulation implementation
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 3年 |  |  |  | Keeping Period |  | 3 years after O/L
Confirmation items
| Objective |  | *Judgment for starting Products Design
| Definition of Design concept in the project | Scope | *Detail plan for Design & Verification Phase (until DFJ) *Confirmation of changing point from Kick Off Meeting
|  | Precondition | *Product Concept Meeting has been finished and the contents of Design Concept Sheet are to satisfy requirements of Product Concept Sheet. *Software Design Concept Meeting has been completed
*Feature is fixed *Panel/Mechanical design concept is fixed *Quality Concept is clarified. (Risk Management Chart) *FMEA completed or schedule is clear
*Safety Regulatory Requirement (ex. FCC(Class-B)) must be clear and listed up
*Judge a product with the possibility of the virus infection and report the result for Design concept. When it was judged as an object product, declare it and request a plant for measures. Follow Sony STM-155/STM-156.
On the basis of the content of the SW design concept, confirm that the choice of the cryptographic key length and the algorithm are performed adequately. (Follow Sony SS STM-160)
|  | Schedule | *Detail schedule until Mass Production
|  | Organization/System | *Organization/System of Products Design team
| Progress of the project that should be confirmed in Design concept | Electrical Design | *first draft schematic is completed *confirm the changing point from development phase *Event Planning List of NMIR is completed
|  | SW Design | *confirm SW design plan and SW release plan
|  | Panel Design | *Development/Evaluation/Design schedule check until MP
|  | Mechanical Design | *Detail schedule until Mass Production
|  | Power Supply and Inverter Design | *plan for SPEC fix, sample supply and introduction schedule until MP
|  | New Parts | *Progress of New Parts investigation and introduction schedule
|  | Key Device | *SPEC. and schedule fixed
|  | Tuner | *actual development and introduction schedule
|  | Picture Quality Sound Quality | *Picture/Sound Quality design schedule
|  | Compliance: - Safety standard - Broadcast - Features (eg: Dolby,etc) -Accessibility | * Confirmation on the outline/schedule/organization to get related Compliances/certification approval * Clarify Safety & Environment scheme with the persons concerned. （TV scheme or V&S scheme or other） * Correspondence of Accessibility is clear. * Clarify unification of CB safety report. (Confirm the unification on CB safety report in the management judgment point; New genaration technology model(8K etc.)/ Multi panel model/ New SET factory / Panel new size/ color variation model)
|  | Environment | The value of a product environmental target is fixed.
|  | Export Control | Confirm submission of “Export Control Questionnaire” (URL：https://jps00006408.jp.sony.com/SHES_Comp/html/export/index.html)
|  | PWB | *confirmation for schedule until MP
|  | EMI | *confirmation for schedule, target margin and the measured model
|  | LOGO MASTER | *Check if LOGO MASTER is updated and which LOGO is necessary to print
| Issue |  | *make clear recovery plan for the issue which could not confirm at Kick Off Meeting and check if new point is added or not
| Risk | Risk Management | *IP clearance, Customer viewpoint FMEA、FMEA *Risk Management Chart *Confirm an cryptographic key length and the algorithm
| Guideline of confirmation items | Line Up | *Variation of HW/SW (model matrix)
|  | Benchmark | *check and comparison with other company products
|  | Market situation | *confirmation of market information
|  | Quality Target | *Quality Concept meeting (Risk management chart : creation and control) *Clear FMEA *Review for problem in the past *share the design know how
|  | Parts count/variety | *confirm actual situation and target
|  | Cost/MP | *confirm actual situation and target
|  | SST | *confirm actual situation and target
|  | Number of production plan and allocation | *confirm production plan
|  | Parts order situation | *confirm new parts list
|  | factory | *confirm factory allocation
Appendix Items and contents in Design Concept Sheet
Event Plan. Table

## P2-81
No. | P2-81 | No. | P2-81
Control Item | Panel Design & Quality Concept Judgment | Control Item | パネル設計構想・品質構想
Event Requirement | Mandatory/Optional | Event Requirement | Mandatory/Optional
Responsibility | Panel Mech Design | Responsibility | パネル設計
Attendees | Panel Design, Panel QA, Product Design, Procurement, Planning & Control, Plant Panel Engineering, Parts Design Group, Power Supply System Design, System Technology, Mechanical Design, DR | Attendees | パネル設計、パネル品質担当、商品設計、調達、管理、部品技術、電源設計、メカ設計、DR
Judgment | Senior Manager or above of panel design responsible department | Judgment | パネル設計責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *FMEA completed *PIC is clear with Member List *Schedule is clear with Panel Master Schedule *Review Panel Introduction Plan which includes items below - development cost/schedule/allocation (Panel, Back Light, and Module)/ planned quantity of trial and production/cost target *Deliberation of DR check sheet *Quality Concept is clear *Judgment for Panel Tool order and ES panel order *Reliability evaluation plan should be approved by Reliability Committee *There is no open development item. If there are open item, there should be clear milestone/organization/Contingency, then it is possible to manage their risk *There is prospect to achieve quality TGT (SMLD) | Criteria, Rule, etc. | *FMEAが終了していること *メンバー表にて担当者が明確になっていること *パネルマスタースケジュールにて日程が明確になっていること *下記に基づいたパネル導入計画の見直し - 開発コスト/日程/生産アロケーション (パネル、O-Cell、バックライト、他 Key Parts)/ 試作、生産の数量計画/コストターゲット *DRチェックシートの審議 *Q品質構想が明確になっていること *パネル用金型手配とESパネルの発注を行うための判断を行う *信頼性評価計画が信頼性委員会によって承認されている *開発未完了案件が無い事。ある場合は、開発案件のマイルストーン、体制、Contingecyが明確で、リスク管理可能であること *品質TGT(SMLD)達成見込みがある事
Another Document | LCD Panel Event Management Standard | Another Document | LCD Panel Event Management Standard
Record Name | Panel Plan Concept / Quality Concept Meeting minutes | Record Name | パネル企画構想・品質構想
Responsibility | Panel Design | Responsibility | パネル設計
Where/How to keep | e21 | Where/How to keep | e21
Keeping Period | 3 years | Keeping Period | 3 years
Event Plan. Table

## P3-1
No | P3-1 | No | P3-1
Control Item | Pre-confirmation of export regulation | Control Item | 輸出規制事前確認
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | Product Design
Attendees | Product Design PL, Import/Export Control | Attendees | 商品設計PL, 輸出入管理部署
Approval | Import/Export Control | Approval | 輸出入管理担当部署
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. |  | Criteria, Rule, etc.
| Confirm the Export Control Conference held and Export control classification ("HANTEI") completed. After “HANTEI” is completed, "Export Approval Notice" is issued by HES Compliance Sec.. As for the products and/or its software which will be exported or re-exported from Japan, they need “Export Approval Notice” to be issued by HES Compliance Sec in this NMIR process. “The products and/or its software” include not only MP sets but also trial sets/ mounted boards and their parts. The responsible person in charge of export regulation confirmation is clear, and it is expected to be completed before export. |  | ・輸出管理会議開催および輸出管理判定が完了したことを確認 ・判定完了後, "Export Approval Notice" が輸出入管理部署より発行 ・日本から輸出または再輸出される製品および/またはそのソフトウェアについては、このNMIRプロセスで輸出入管理部署が発行する "Export Approval Notice"が必要 ・「本製品および/またはそのソフトウェア」には、MPセットだけでなく、トライアルセット/実装基板およびその部品も含まれる - 輸出規制確認の責任担当者が明確になっており、輸出までに上記が完了する目途が立っていること
Another Document | Non | Another Document | Non
Record Name | Export regulation investigation | Record Name | 輸出規制調査票
Responsibility | Import/Export Control | Responsibility | 輸出入管理
Where/How to keep | Server of Import/Export Control | Where/How to keep | 輸出入管理担当部署サーバー内
Keeping Period | 5 years. | Keeping Period | 5 years.
Event Plan. Table

## P3-2
| No. | P3-2 |  | No. | P3-2
Control Item |  | DCE Compliance confirmation meeting | Control Item |  | DCE認証確認会議
| Event Requirement | Mandatory/Optional |  | Event Requirement | Mandatory/Optional
| Responsibility | Digital Country Expansion |  | Responsibility | DCE担当部署
| Attendee | Product Planning, Product Design (Electric, Mech, IM), TVQA, Software |  | Attendee | 商品企画、商品設計（電気、メカ、IM）、QA、ソフトウェア
| Approval | Responsible person of Digital Country Expansion |  | Approval | DCE責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | *Confirm the specifications of the set influencing Broadcast compliance and define schedule. *The information of the document requirement for compliance application from design is confirm with a design section and a safety section, and being common recognition. *Confirm the items according to the format. Please attached the material. |  | Criteria, Rule, etc. | *放送認証に影響を与えるセット仕様の確認と、スケジュールを明確にする *設計からの認証申請のための文書要求の情報は、設計部署と製品安全部署で確認し、共通認識とする *フォーマットに従い確認し、資料添付する
| Another Document |  |  | Another Document
Record | Record Name | Approval work request sheet, "DCE Standard Request Form" | Record | Record Name | Approval work request sheet, "DCE Standard Request Form"
| Responsibility | Sony Product Design. |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 1 year |  | Keeping Period | 1年
|  | Confirmation item |  |  | 確認項目
|  |  Define Broadcast application type/countries and new requirement/specification |  |  |  ブロードキャストアプリケーションの種類/国および新しい要件/仕様を定義する
|  |  To confirm each related parties (PL/ML, IM, Mecha, Software, Tuner, Product Safety) required document and submittion schedule |  |  |  各関係者 (PL, IM, Mecha, Software, Tuner, Product Safety)に必要な書類と提出スケジュールを確認する
|  |  Schedule ・Broadcast Compliance application schedule |  |  |  スケジュール ・Broadcast Compliance application schedule
|  | ・Define Broadcast Compliance target date (can achieve PP or MP) |  |  | ・放送認証取得スケジュール (PP or MPまで)
|  | ・Cut-Off date for modification (Make Cut-Off date of the design change clear.) |  |  | ・変更に関する締め切り (設計変更の締め切りを明確にする)
|  |  Organization of Digital Country Expansion. |  |  |  DCEの体制
FOR EXAMPLE ONLY
FOR EXAMPLE ONLY
Event Plan. Table

## P3-3
メインイベント | P3-3. DVT前確認会議（DVT前クライテリア確認） |  |  |  |  | Main Event | P3-3. Confirmation Meeting before DVT (Design Verification Trial)
目的 | DVT実施の可否を判定する |  |  |  |  | Purpose | Judgment for Go To DVT
承認者 | Project Manager |  |  |  |  | Approval | Project Manager
開催部署 | 商品設計部/開発設計 |  |  |  |  | Responsibility | Product Design/Development Design
参加者 | 商品設計/開発設計/SW設計/品質・CS ※メール開催も可 |  |  |  |  | Atendees | Product Design/Development Design/SW Design/QA ※E-mail holding is OK
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | DVT前確認資料 | ・各設計の承認会が完了していること ・各設計のチェックリストに応じたクライテリアがクリアになっていること 例：起型承認済み、ハーネス検討会済み、版下検討会済みなど | DVT前確認会議資料 議事録 | Project |  |  | Confirmation materials before DVT | · The approval meeting of each design has been completed · The criteria according to the check list of each design is clear | Minutes before DVT Conference Minutes
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | P2-5. Patent確認：新規案件追加の有無確認 P2-80. 設計構想会議済 P3-1. 輸出規制事前確認 -エレキ：各種基板（G、B、H、LD、Wifiなど）出図前判定済 -メカ：手作り検討会済 -DRBFMシートチェック済（DRBFMの実施により、設計リスク・再発防止への対処方法/計画がたてられていること） -バイタルセンシング該当製品の場合，QMS-345 Appendix-1 設計構想フェーズに記載の6項目の完了 |  | P2-5. コンプライアンスマスターリスト P3-19. 再発防止チェックシート |  |  | Product Design | P2-5. Patent Confirmation: Confirm new item addition P2-80. Design Concept Meeting P3-1. Pre-confirmation of export regulation -Electrical: Board (G, B,H,Wifi etc.) drawing approval -Mecha: handmade review meeting -DRBFM Sheet Check（DRBFM has been implemented, and design risks and recurrence prevention measures and plans have been established.） -Recurrence prevention check (Check for recurrence prevention by check sheet in each design) -In case of Vital-sensing Product, the 6 tasks described in the Product design phase of QMS-345 Appendix-1 should be implemented. |  | P2-5. Conpliance master list P3-19. Recurrence prevention check sheet
SW | [5 empty] | SW
Panel | P2-81. パネル設計品質構想会議済 |  |  |  |  | Panel | P2-81. Panel design quality concept Meeting
品証 | [5 empty] | QA
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | - |  |  |  | Where/How to keep |  | -
保管期限 |  | - |  |  |  | Keeping Period |  | -
| 目的 |  | *DVTへ移行するための判断 |  |  |  | Objective |  | *Judgment for Go To DVT
| プロジェクトの中での「DVT前確認」の定義 | スコープ | *代表モデルによるシャーシ検討内容確認 |  |  |  | Definition of Confirmation before DVT in the project | Scope | *confirmation for Chassis Investigation Plan with representative models
|  | 前提条件 | *メカの金型品供給可能な見通し |  |  |  |  | Precondition | *Clear plan to supply tooled mechanical parts
|  |  | *Full DR、Full FT可能な見通し | [5 empty] | *Clear plan of Full DR and Full FT execution
|  |  | *パネル品質構想会議が完了していること *ESパネル供給され、詳細検討可能な見通し | [5 empty] | *Panel Design/Quality Concept Meeting finished *Clear plan to supply ES panel and detail investigation will be available
|  |  | *DVTにおいて実装され、通常使用では安定動作するSWの項目とレベルの合意および供給見通しがある | [5 empty] | *SW will be implemented and stable enough by general operation, this SW level and item are agreed and schedule is clear for DVT release
|  | スケジュール | *スケジュールアップデートと進捗確認 |  |  |  |  | Schedule | *Schedule update and progress check
|  | 組織・体制 | *商品設計チームの組織、体制 |  |  |  |  | Organization/System | *Organization/System of Products Design team
| 「DVT前確認」の段階で確認すべき プロジェクトの進捗状況 | 電気設計 | *代表モデルと評価計画 |  |  |  | Progress of the project that should be confirmed in Confirmation before DVT | Electrical Design | *pick up representative models and make clear evaluation plan
|  | SW設計 | *DVTアッシ-時のSWリリース計画 |  |  |  |  | SW Design | *SW release plan until DVT assy
|  | パネル設計 | *ESパネル評価とCSパネル仕様決定計画 |  |  |  |  | Panel Design | *confirm ES panel evaluation plan and SPEC fix for CS panel
|  |  | *旧モデルを使ったWSサンプルの評価結果 | [5 empty] | *WS panel evaluation result with using previous model
|  | メカ設計 | *DVTで金型品供給のためのスケジュール |  |  |  |  | Mechanical Design | *schedule to supply tooled parts at DVT
|  | 電源設計 | *DVTへのサンプル供給スケジュールと評価計画 |  |  |  |  | Power Supply Unit | *schedule of supply sample board to DVT and evaluation plan
|  | 新規部品 | *新規部品リストの提出確認 |  |  |  |  | New Parts | *Confirmation for new parts list issue
|  | キーデバイス | *サンプル評価計画 |  |  |  |  | Key Device | *Sample evaluation plan
|  | Tuner | *サンプル評価計画 |  |  |  |  | Tuner | *Sample evaluation plan
|  | 画音質 | *アルゴリズム、基本画音質設計スケジュール |  |  |  |  | Picture Quality Sound Quality | *Algorithm and basic Picture/Sound Quality design schedule
|  | コンプライアンス: -安全規格 -放送認証 -フェーチャー (eg: Dolby,etc) | *コンプライアンス/認証取得の計画進捗更新 |  |  |  |  | Compliance: - Safety standard - Broadcast - Features (eg: Dolby,etc) | *Update progress on the confirmation plan to get related Compliances/certification approval
|  | PWB | *DVTでの設計スケジュール |  |  |  |  | PWB | *Design schedule for DTV
|  | EMI | *代表モデルでの評価計画とターゲット |  |  |  |  | EMI | *confirm evaluation schedule and target with representative models
| 課題 |  | *DVTにおいて確認困難な項目の対策案を明確にする |  |  |  | Issue |  | *make clear recovery plan for the issue which can not confirm at DVT
| リスク | リスクマネージメント | *D4Q/DRBFM確認 |  |  |  | Risk | Risk Management | *check Risk Management Chart again
|  |  | *暗号鍵の進捗及び変化点の確認 | [5 empty] | *confirmation for progress and changing point of the cryptographic key length
| 確認項目のガイドライン | ラインアップ | ・変更点確認 |  |  |  | Guideline of confirmation items | Line Up | *check changing point
|  | 他社との比較 | [5 empty] | Benchmark
|  | マーケット状況 | [5 empty] | Market situation
|  | 品質ターゲット | [5 empty] | Quality Target
|  | 部品点数・品種 | ・部品点数、品種、ターゲット確認 |  |  |  |  | Parts count/variety | *confirm actual situation and target
|  | コスト・MP | ・現状とターゲット確認 |  |  |  |  | Cost/MP | *confirm actual situation and target
|  | SST | ・現状とターゲット確認 |  |  |  |  | SST | *confirm actual situation and target
|  | 生産計画台数・アロケーション | [5 empty] | Number of production plan and allocation
|  | 部品手配 | [5 empty] | Parts order situation
|  | 事業所 | [5 empty] | factory
Event Plan. Table

## P3-4
No. | P3-4 |  |  | No. | P3-4
Control Item | DVT(Design Verification Trial) |  |  | Control Item | DVT(Design Verification Trial)
Event Requirement |  |  |  | Event Requirement
Responsibility | Product Design |  |  | Responsibility | 商品設計
Attendees | not provided |  |  | Attendees | not provided
Approval | Not specified | #REF! | #REF! | Approval | Not specified | #REF! | #REF!
Acceptation for ODM | #REF! | #REF! | #REF! | Acceptation for ODM | #REF! | #REF! | #REF!
Criteria, Rule, etc. | see below |  |  | Criteria, Rule, etc. | 下記の内容
Another Document | non |  |  | Another Document | non
Record Name | not provided |  |  | Record Name | not provided
Responsibility | not provided |  |  | Responsibility | not provided
Where/How to keep | not provided |  |  | Where/How to keep | not provided
Keeping Period | not provided |  |  | Keeping Period | not provided
| Objective |  | *investigation, evaluation, countermeasure, confirmation will be done and complete model design by using representative model. |  | 目的 |  | ・代表モデルによるHW/SWの検討/評価/対策/確認を行い、設計を完了させる
| Criteria at start | HW | *new device evaluation completed, all parts mounted and operation confirmed |  | CVT開始時のクライテリア | HW | ・新規デバイス評価完了、すべての部品がマウントされ、動作確認済み
|  | SW | *no hung up during evaluation (at general operation and reliability test) |  |  | SW | ・評価中（通常操作時、信頼性試験時）ハングアップしないこと
|  |  | *SW is implemented |  |  |  | ・実装完了
|  | Panel | *ES panel is available (spec fixed) |  |  | パネル | ・ESパネル供給可能（仕様決定済み）
|  | Mechanical | *tooled mechanical parts is available |  |  | メカ | ・型物メカ部品供給可能
|  |  | *Full DR, Full FT are available |  |  |  | ・Full DR、Full FT可能
| Guideline of activities |  | *Confirmation for basic function |  | アクティビティのガイドライン |  | ・基本的な機能の確認
|  |  | *Power ON/OFF, sequence, transients |  |  |  | ・電源オン、オフ、シーケンス、トランジェント
|  |  | *all pass and every kind of signal |  |  |  | ・すべての信号とすべてのパス
|  |  | *tuning and input change |  |  |  | ・チューニング、入力切り替え
|  |  | *analog (sound) mode ex: NICAM |  |  |  | ・NICAMなどすべてのアナログ（サウンド）モード
|  |  | *EPG, data broadcasting, CC, TEXT, etc. |  |  |  | ・EPG,データ放送、CC、TEXTなど
|  |  | *blanking, mute, etc |  |  |  | ・ブランキング、ミュートなど
|  |  | *confirmation for new HW (Tuner, Demod, Panel, PEL2, etc.) |  |  |  | ・新規HWの確認（Tuner、Demod,Panel,PEL2など
|  |  | *confirm New Feature (mainly system) |  |  |  | ・New Feature 確認（システム周り）
|  |  | *finalize HW control SPEC |  |  |  | ・HW制御仕様のファイナライズ
|  |  | *confirm heat and EMI (including MAX power condition) |  |  |  | ・熱、EMI確認（最大負荷時を含む）
|  |  | *Picture/Sound Quality of representative mode |  |  |  | ・代表モードの画音質（アルゴリズムの決定）
|  |  | *fix panel SPEC |  |  |  | ・パネルの仕様決定
|  |  | *confirm tooled mechanical parts |  |  |  | ・型物メカ部品の確認
|  |  | *parts tolerance confirmation |  |  |  | ・部品バラツキ検討
|  |  | *local DR (local unique signal, etc.), FT |  |  |  | ・現地DR（現地特有信号など）、FT
| Required output |  | *General evaluation/examination finished |  | 要求されるアウトプット |  | ・一通りの評価/検討終了
|  |  | *Keep EMI target margin for representative model |  |  |  | ・EMI代表モデルでマージン確保
|  |  | *pick up all problem and countermeasure is clear or prospect of countermeasure is clear |  |  |  | ・すべての問題点抽出と対策完了、または、対策の見通しが明確
|  |  | *remaining HW problem A=0、B=5 |  |  |  | ・HW問題A=0、B=5
Event Plan. Table

## P3-5
No. | P3-5 | No. | P3-5
Control Item | SAPAPS at DVT stage | Control Item | SAPAPS at DVT stage
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Product Design, DR, Products Safety, Ordinary people | Attendees | 商品設計、品質評価（DR）、製品安全、一般人
Approval | Responsible person of Product Design | Approval | 商品設計責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | Countermeasures against problems occurred and Schedule for solution are to be clarified. (Comply with Common SAPAPS Standard (DS029001E) for details) - Self-control by Product Design | Criteria, Rule, etc. | 問題発生時の対策と解決策のスケジュールを明確にすること。 （詳細については、共通SAPAPS規格（DS029001E）に準拠する）- Self-control by Product Design
Another Document | DS029001E Common SAPAPS Standard | Another Document | DS029001共通危害想定標準
| FDS029001E-01 Form_SAPAPS Implementation Report |  | FDS029001-01 Form_危害想定結果報告書
Record Name | SAPAPS Implementation Report | Record Name | 危害想定結果報告書
Responsibility | Product Design. | Responsibility | 商品設計
Where/How to keep | Self-control by Product Design | Where/How to keep | 商品設計自主管理
Keeping Period | 15 years. | Keeping Period | 12年
Event Plan. Table

## P3-6
No. | P3-6 | No | P3-6
Control Item | CIT (Customer Installation Test) at DVT stage | Control Item | DVT CIT (Customer Installation Test)
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Product Design, DR, Products Safety, Ordinary People | Attendees | 商品設計，DR，製品安全，一般人
Approval | DR | Approval | DR
Criteria, Rule, etc. | * To implement CIT as the same time of SAPAPS. * Refer to the appendix CIT operation rule) | Criteria, Rule, etc. | ・CITをSAPAPSの実施と合わせて実施する。 ・「CIT運用ルール」参照。
Another Document | Non | Another Document | 無し
Record Name | Problem of CIT | Record Name | CIT問題点
Responsibility | DR | Responsibility | DR
Where/How to keep | JIRA | Where/How to keep | JIRA
Keeping Period | 12 years. | Keeping Period | 12年
| CIT (Customer Installation Test) operation rule |  | CIT(Customer Installation Test)運用ルール
| 1. Purpose |  | １．目的
| CIT is the test, assumed as unpacking, setting, operating, watching TV, etc which user will perform after purchasing. It shall be intended for detecting problems from the evaluation of user point of view and perform rapid measurement. |  | CITとは、ユーザーが購入後に行なう、開梱、セッティング、操作する、TVを見るなどの行為を想定した試験であり、最終形態において、ユーザー視点による評価から不具合を発見し、早期対処を行なうことを目的とする。
| 2. Implementation responsible |  | ２．実行責任
| Host will be Product Design. Product Design responsible person will select implementation model in consulting with DR. |  | 主催は商品設計部署。実施モデルは商品設計がDRと協議して選定する。
| 3. Implementation term |  | ３．実施時期
| CIT will be implemented at the same time of SAPAPS. |  | SAPAPSの実施と合わせてCITを実施する。
| Measurement will be implemented until PVT if problem have been detected by DVT CIT. |  | DVT CITで問題点が発見された場合は、PVTまでに対策を実施する。
| 4. Test method |  | ４．試験方法
| (1) Test overview |  | (1)試験概要
| -Tester should have close sense to users and able to recognize problems. |  | ・試験者は、一般の人に近い感覚でかつ問題点に気がつく感性のある人が試験する必要がある。DRから1名（主）、設計から1名（副）
| -Confirm every operation according to the instruction manual. |  | ・取扱い説明書に沿って全ての操作を確認する。
| -Problems detected by CIT will be specified in JIRA. |  | ・CITにより発見された問題点は、JIRAに記載する。
| (2) CIT test flow |  | (2)CIT試験フロー
開梱試験（外装・梱包確認）
付属品確認（取説・投げ込み類）
設置（スタンド/壁掛け）
Unpackaging test (exterior / packaging check)
Accessory confirmation (instruction manual / fly sheet)
Installation (stand / wall)
Event Plan. Table

## P3-7
メインイベント | 27. DVT DR会議 |  |  |  |  | Main Event | 27. DR Meeting for DVT Result
目的 | 問題点を把握し、是正/改善についての計画を明確にする |  |  |  |  | Purpose | To grasp problems and make clear their correction/improvement plan.
承認者 | 品質評価（DR）責任者 |  |  |  |  | Approval | Responsible person of QA(DR)
開催部署 | 品質評価（DR） |  |  |  |  | Responsibility | QA(DR)
参加者 | 商品設計/デバイス/SW設計/品質評価(DR) |  |  |  |  | Atendees | Product Design/Device/SW Design/QA(DR)
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 残問題点に対し、是正/改善計画が明確であること。 | DVT DR会議議事録 | Project |  |  |  | The Correction/Improvement plan for remaining problem to be cleared. | Meeting minutes of DVT DR
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | DVT DR時制約事項 DVT DR評価(商品設計担当分) |  |  |  |  | Product Design | Limitation Item for DR evaluation DVT DR evaluation (Product Design assigned)
SW | DVT DR時制約事項 |  |  |  |  | SW | Limitation Item for DR evaluation
Panel | DVT DR時制約事項 |  |  |  |  | Panel | Limitation Item for DR evaluation DVT DR evaluation (Panel assigned)
品証 | DVT DR IN前確認会議 DVT DR評価計画（評価分担を含む） DVT DR評価(QA担当分) |  |  |  |  | QA | Before DVT DR IN Meeting DVT DR (Including evaluation assignment) DVT DR evaluation (QA assigned)
文書管理 | [5 empty] | Document
記録物 |  | DVT DR会議議事録 |  |  |  | Record Name |  | Meeting minutes of DVT DR
管理部署 |  | 品質評価(DR) |  |  |  | Responsibility |  | QA(DR)
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 12年 |  |  |  | Keeping Period |  | 12 years after On Line
DR問題点重要度ランクの定義（注1） | [5 empty] | Problem Ranking Table (for AA, A, B, C Rank) (Note 1)
（注1）これらのA,B,Cランク区分は一般的なものでありカテゴリー、機種内容、評価条件で異なる場合がある。 | [5 empty] | (Note 1): A, B and C Ranking given here is general principle and may change depending upon nature of the product or evaluation condition.
（注2）現在現象は出ていないが、過去に発生した問題と類似設計のもの及び類似部品、材料を使用しているものを含む。 | [5 empty] | (Note 2): This classification is to be applied even when no symptom is found, if the material, components, or design are similar or the same as those which had problems in the past.
Event Plan. Table

## P3-8
| No. | P3-8 |  | No. | P3-8
Control Item | (Common Event) | OoBE(Out of Box Experience) | Control Item | (Common Event) | OoBE(Out of Box Experience)
Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | QA
| Attendees | Non-TV related members, Product Design, QA |  | Attendees | 一般人、商品設計、QA
| Approval | - |  | Approval | -
| Acceptation for ODM |  |  | Acceptation for ODM
| Criteria, Rule, etc. | * To implement OoBE as part of the evaluation item of Conf QA (refer to another document) |  | Criteria, Rule, etc. | * To implement OoBE as part of the evaluation item of Conf QA (refer to another document)
| Another Document | OoBE CS.xlsx OoBE Guideline |  | Another Document | OoBE CS.xlsx OoBE Guideline
Record | Record Name | Remaning issues list | Record | Record Name | Remaning issues list
| Responsibility | Sony QA |  | Responsibility | Sony QA
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 12 years. |  | Keeping Period | 12 years.
|  | 1. Purpose |  |  | 1. Purpose
|  | OoBE is the test, assumed as unpacking which user will perform after purchasing. It shall be intended for detecting problems from the evaluation of user point of view and perform rapid measurement. |  |  | OoBE is the test, assumed as unpacking, setting, operating, watching TV, etc which user will perform after purchasing. It shall be intended for detecting problems from the evaluation of user point of view and perform rapid measurement.
|  | 2. Implementation responsible |  |  | 2. Implementation responsible
|  | Host will be Produce Design section. Product Design responsible person will select implementation model. |  |  | Host will be QA section. QA responsible person will select implementation model.
|  | 3. Implementation term |  |  | 3. Implementation term
|  | Product Design responsible person will select model from OoBE model. OoBE will be implemented as a part of evaluation item of Confirmation QA after Confirmation trial. Problem will be improved until design validation if problem have been detected by OoBE. |  |  | QA responsible person will select model from OoBE model. OoBE will be implemented as a part of evaluation item of Confirmation QA after Confirmation trial. Problem will be improved until design validation if problem have been detected by OoBE.
To be updated (By Mr. Kato)
Event Plan. Table

## P3-9
| No. | P3-9 |  | No. | P3-9
Control Item |  | RIPR check (1st) | Control Item |  | RIPRチェック(1回目)
Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | 商品設計
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | 1) Design is to evaluate the confirmation items before BOM Release and approve & keep it internally in design. 2)No possibility of Reliability Incident. - Self-control by Product Design. |  | Criteria, Rule, etc. | 1) BOMリリース前に設計側が規定のチェックシートを使用して、BOMリリース前項目を評価し、設計内部で承認、保管。 2) 品質事故の可能性が無いこと。 （設計自主管理）
| Another Document |  |  | Another Document
|  | FTBR-RI-E-01 Form_RIPR Check Sheet |  |  | FTBR-RI-01Form RIPR チェックシート
Record | Record Name | RIPR Check sheet. | Record | Record Name | RIPRﾁｪｯｸｼｰﾄ
| Responsibility | Sony Product Design. |  | Responsibility | 商品設計
| Where/How to keep | Self-control by Product Design |  | Where/How to keep | 商品設計自主管理
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 生産終了後10年
Event Plan. Table

## P3-10
| No. | P3-10 |  | No. | P3-10
Control Item |  | Minimum Product Quality Rules and Requirements check (1st.) | Control Item |  | 品質ﾎﾞﾄﾑﾁｪｯｸ(1回目)
Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | 商品設計
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | Minimum Product Quality Rules and Requirements are to be satisfied. - Self-control by Product Design No need confirmation and approval of QA. |  | Criteria, Rule, etc. | 品質ボトム基準の要求を満たしている事。(設計自主管理) ・チェックシートに品質保証部の確認/承認は不必要。
| Another Document |  |  | Another Document
|  | FDR027E-03 Form Minimum Product Quality Rules & Requirements Check Sheet |  |  | FDR027-03 Form 品質ボトムチェックシート
Record | Record Name | Quality Bottom Check Sheet | Record | Record Name | Quality Bottom Check Sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | Self-control by Product Design |  | Where/How to keep | 商品設計自主管理
| Keeping Period | 10 years |  | Keeping Period | １０年間
Event Plan. Table

## P3-11
No. | P3-11 | No. | P3-11
Control Item | Product assessment check (1st.) | Control Item | 製品ｱｾｽﾒﾝﾄ(1回目)
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Product Design, Product Environmental Dept. | Attendees | 商品設計、製品環境
Approval | Responsible person of Product Design | Approval | 商品設計責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *Before BOM Release, using the product assessment sheet, it confirms the achievement of design conception in writing the environmental goal. Details of the assessment URL: https://sonyjpn.sharepoint.com/sites/S125-018/web/index.aspx A product assessment sheet, a regulation check sheet, too, are subscribed to this Web site. | Criteria, Rule, etc. | ･BOMリリース前に製品アセスメントシートを使用して、設計構想書中の環境目標の達成度を確認する。 アセスメント詳細はWebサイト https://sonyjpn.sharepoint.com/sites/S125-018/web/index.aspx に定められており、製品アセスメントシート、法規制チェックシートもこのWebページに登録されている。
| *Responsibility of Execution : Must be model leader *Keep the record of the implementation. *Submitting it to Product Environmental Dept. is optional. |  | ・製品アセスメントの実行責任は機種リ－ダ－とする。 ・実施の記録を残すこと。
| *It makes a derivation model unnecessary in the implementation. But it fixes the judgment on discussing at the product design taking charge section and in the Product Environmental Dept. in " the implementation event plan " creating. |  | ・製品環境担当部署への提出は任意とする。 ・派生モデルは実施不要とするが、その判定は、「実施イベント計画」作成時に、商品設計担当部署と製品環境担当部署で協議の上決定する。
| *Because it is the self-management of the design, also keeps record of assessment sheet. |  | ・設計の自主管理イベントであり、記録も設計が保管する。
Another Document | Non | Another Document | 無し
Record Name | Product Assessment check sheet | Record Name | Product Assessment check sheet
Responsibility | Product Design. | Responsibility | 商品設計
Where/How to keep | e 21 | Where/How to keep | e 21
Keeping Period | 13 years. | Keeping Period | 13年
Event Plan. Table

## P3-12
No. | P3-12 | No. | P3-12
Control Item | Confirmation for Key Device ES | Control Item | キーデバイス ES確認
Event Requirement |  | Event Requirement
Responsibility | Device Responsible | Responsibility | デバイス責任
Attendees | Product Design, Device, PS responsible people, Software Design, DR | Attendees | 商品設計、デバイス、PS責任担当者、ソフトウェア設計、DR
Approval | N/A | Approval | N/A
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *This event is carried out for the parts which doesn't have Parts Approval. *Hold after device evaluation finished and before the deadline of the correction demand *about newly introduced device, all necessary evaluation finished or not | Criteria, Rule, etc. | *検定承認イベントがない部品に対して実施 *開催時期：デバイス評価終了後、修正要求締め切り前 *新規導入デバイスに対して、評価必要な項目が終了しているかどうか
| *if problem happen, explain about detail and recovery plan for the problem (decision item correction at ES1.1 etc *Confirm if there is problem or not and introduction into products, as key device |  | *問題があった項目のみ問題の内容と対処方法（割り切り、ES1.1で修正など）を説明 *キーデバイスとして、セット導入に問題がないかどうかを確認
| Basically, this event covers following activities 1) Development Concept Meeting 2) Planning Judgment Meeting 3) Vender Selection Meeting Refer below table about Sponsoring Post and Judge |  | 原則として、以下の内容が実施されていること 1) Development Concept Meeting 2) Planning Judgment Meeting 3) Vender Selection Meeting 主催部署と判定者は下記の表を参照のこと
| 1. confirm device requirement specification and development schedule 2. confirm device evaluation result 3. confirm fundamental picture quality performance 4. confirm correction item and decision item |  | 1. デバイス要求仕様、開発日程の確認 2. デバイス評価結果の確認 3. 基本画質パフォーマンスの確認 4. 修正依頼項目、割り切り項目の確認
| *only explanation is required under following condition -all necessary evaluation finished and no NG item which required HW correction |  | *下記条件にて報告のみ実施 -必要な評価が全て完了していてチップのHW修正が必要なNG項目がない
| -all necessary evaluation finished and even if there are NG item which required HW correction, schedule and side effect has low risk |  | -HW修正 が必要なNG項目があっても日程、副作用に対して低リスクの場合
*if there are uncompleted evaluation item and there are NG item which required decision/NG item which required HW correction with high risk
| -decide direction with agreement among model design responsible person, chassis design responsible person and device design responsible person |  | 評価完了していない項目がある場合、割り切り判断が必要なNG項目がある場合、またはHW修正に日程・ 副作用リスクが伴うNG項目がある場合は、商品設計責任部署、シャーシ設計責任部署、及び デバイス責任部署の合意の上、方向性を決める。
Another Document | Non | Another Document | Non
Record Name | Presentation Material, meeting minutes | Record Name | 発表資料、議事録
Responsibility | Product Design / Device Development | Responsibility | 商品設計/開発設計
Where/How to keep | Server of responsible group and etc. | Where/How to keep | 責任部署サーバー
Keeping Period | 3 years | Keeping Period | 3 years
Event Plan. Table

## P3-13
No. |  | P3-13 | No. |  | P3-13
Control Item |  | Judgment of basic PS (Picture/Sound) | Control Item |  | 基本画音質判定
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Attendees | Sony(Product Design, PS com., Product Planning) |  | Attendees | Sony(商品設計, 画音質委員, 商品企画)
| Approval | PS Chairman or Vice chairman |  | Approval | PS Chairman or Vice chairman
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | To judge PS quality is to comply basic performance and design policy. Show the following the flow and the judgment method of the PS committee activity. |  | Criteria, Rule, etc. | 基本性能、設計方針に合致することを判定する 下記に画音質委員会活動の流れと判定方法を示す。
| Another Document | TV PS committee system |  | Another Document | TV PS committee system
| Record Name | PS Quality Judgment Meeting report |  | Record Name | PS Quality Judgment Meeting report
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 3 years |  | Keeping Period | 3年間
[Ｆlow and Judgment method of the PS committee activity] |  |  | [画音質委員会活動の流れと判定方法]
*Definition of the model |  |  | *モデルの定義
1) Leading model : New design model |  |  | 1)リーディングモデル ： 新規設計モデル
2) Derivative model : Destination difference of the leading model, a size difference, a design difference, a panel difference, etc. |  |  | 2) 派生モデル ： 主にリーディングモデルの仕向け違い、サイズ違い、デザイン違い、パネル違い等で
|  | Design and Committee decide it. |  | 対応したものであるが、その他、設計と委員会で決める
*Ｆlow and Judgment method of the activity |  |  | *活動の流れと判定方法
Judgment of basic PS
DVT
PVT
Judgment of panel performance
Design PS quality meeting
Shipping
Design stage
Production stage
[Leading model]
[Derivative model]
DVT
PVT
Judgment of panel performance
Design PS quality meeting
PP/MP PS quality meeting
Shipping
Judgment : PS Chairman
or Vice chairman
Judgment : (PP)Production GM
(MP)Plant QA GM
Judgment : PS Committee
Judgment : PS Committee
Judgment : (PP)Production GM
(MP)Plant QA GM
Judgment : PS Chairman
or Vice chairman
Judgment : PS Chairman
or Vice chairman
PP/MP PS quality meeting
基本画音質判定
DＶＴ
PVT
パネル性能判定
設計画音質会議
PP/MP画音質会議
出荷
設計段階
製造段階
○リーディングモデル
○派生モデル
DＶＴ
PVT
パネル性能判定
設計画音質会議
PP/MP画音質会議
出荷
判定者：委員長
もしくは副委員長
判定者：委員長
もしくは副委員長
判定者：委員長
もしくは副委員長
判定者：（PP)製造部長
(MP)品証部長
判定者：画音質委員
判定者：画音質委員
判定者：（PP)製造部長
(MP)品証部長
Event Plan. Table

## P3-14
No. | P3-14 | No. | P3-14
Control Item | DR Meeting for Panel DVT | Control Item | パネルDVT DR会議
Event Requirement | Mandatory/Optional | Event Requirement | Mandatory/Optional
Responsibility | Panel Mech Design | Responsibility | パネル設計
Attendees | Panel Design, Panel QA, Product Design, DR, Plant Panel Engineering, Panel Parts, Mechanical Design | Attendees | パネル設計、パネル品証、商品設計、品証評価（DR）、事業所パネル技術、パネル部品、機構設計
Approval | Senior Manager or above of panel design responsible department | Approval | パネル設計担当課長以上
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *CS panel specification confirmation *ES panel evaluation result (DR Check Sheet) *CS panel evaluation plan *Acquisition plan of Panel Safety Regulations | Criteria, Rule, etc. | ・CSパネル仕様確認 ・ESパネル評価結果（DRチェックシート） ・CSパネル評価計画 ・パネル安規取得予定 CSパネル発注の判断を行う
Another Document | Panel Event Management Standard | Another Document | パネルイベント管理標準
Record Name | meeting minutes | Record Name | 議事録
Responsibility | Panel Design | Responsibility | パネル設計
Where/How to keep | e21 | Where/How to keep | e21
Keeping Period | 3 years | Keeping Period | 3年
Event Plan. Table

## P3-15
No. | P3-15 | No. | P3-15
Control Item | Judgment for Key Device MP | Control Item | キーデバイス量産判定
Event Requirement |  | Event Requirement
Responsibility | Device Responsible | Responsibility | デバイス設計
Attendees | Develop Design, Product Design, Device, PS responsible people, Software Design, DR | Attendees | 開発設計、商品設計、デバイス責任、画音質委員、ソフトウェア設計、品質評価(DR)
Approval | Responsible person of Device or/and Responsible person of Product Design | Approval | 商品設計責任者/デバイス責任担当責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *This event is carried out for the parts which doesn't have Parts Approval. *Confirmation items *Report of evaluation result and remaining problem *Schedule | Criteria, Rule, etc. | ＊検定承認のイベントがない部品に関して実施 *確認事項 *これまでの評価結果と、残問題報告 *今後の日程確認
| *Make judgment for MP with considering above report and business situation. |  | 上記確認事項報告とビジネス状況を総合してMP投入判断を行う
| Refer below table about Sponsoring Post and Judge |  | 主催部署と判定者は下記の表を参照のこと
Another Document | Non | Another Document | 無し
Record Name | Presentation Material, meeting minutes | Record Name | 会議発表資料、議事録
Responsibility | Product Design / Device Development | Responsibility | 商品設計担当部署/デバイス責任担当部署
Where/How to keep | Server of responsible group and etc. | Where/How to keep | 商品設計担当部署内サーバ等/デバイス責任担当部署内サーバ等
Keeping Period | 3 years | Keeping Period | 3年
Event Plan. Table

## P3-16
メインイベント | P3-16. αリリース |  |  |  |  | Main Event | P3-16. α Release
目的 | 機能評価が開始できる準備が整っていることを確認する |  |  |  |  | Purpose | Confirm ready to release for start functional evaluation
承認者 | ソフトウェア品質推進者 |  |  |  |  | Approval | Software Quality Supporter
開催部署 | ソニーソフトウェア設計 |  |  |  |  | Responsibility | Sony Software Design
参加者 | SW PM, SW PL, SW TL, SWV, HW PM, HW PL, QA |  |  |  |  | Atendees | SW PM, SW PL, SW TL, SQA, HW PM, HW PL, QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 機能評価が開始できる準備が整っていること - 結合テストが完了し、安定動作していること 機能評価を始めるための制約事項(ブロッキング)がないこと *すべてのソフトウェア機能が実装され、検証が計画されていること。 *検証結果は十分に分析され、不具合を解決する計画が準備されていること。 *システムテスト計画に大きな影響を与える高リスクおよび問題に対する対策が計画されていること。 | 議事録＆発表資料 | Project |  |  |  | * All software functions are implemented and planned verification is also completed. * Verification results are well analyzed, plan to resolve defects is prepared. * Countermeasures are planned for high risks and issues that will have a huge impact to System Test plan. | Minutes and presentation materials
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | ＜SW開発が外部委託の場合＞ 委託先と事前にSW品質がリリースのクライテリアを満足していることの確認・合意を行う |  |  |  |  | SW | < In case of outsourcing SW development > It is necessary to have confirmation and agreement in advance with contractor(s) that SW quality meets the criteria of SW validation release.
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | TV SW Process Asset Library |  |  |  | Another Document |  | TV SW Process Asset Library
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
管理部署 |  | ソニーソフトウェア設計 |  |  |  | Responsibility |  | Software Design.
保管場所・方法 |  | PJ common portal |  |  |  | Where/How to keep |  | PJ common portal
保管期限 |  | 5年 |  |  |  | Keeping Period |  | 5 years.
Event Plan. Table

## P3-17
| No. | P3-17 |  | No. | P3-17
Control Item |  | Confirmation Meeting for Product Safety and Compliance | Control Item |  | 安規/コンプライアンス確認会議
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | Product Design
| Attendees | Product Design/Development Design/SW Design/QA |  | Attendees | 商品設計/開発設計/SW設計/QA
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | *Confirm the specifications of the set influencing product safety compliance and define Safety to take, a schedule. |  | Criteria, Rule, etc. | *製品安全コンプライアンスに影響するセットの仕様を確認し、取得安規、スケジュールを明確にする。
|  | *The information of the set influencing product safety compliance is shared with a design section and a safety section, and being common recognition. |  |  | *製品安全コンプライアンスに影響するセットの情報が設計と製品安全部署で共有され、共通認識であること
|  | *Confirm the items according to the format. Please attached the material. |  |  | *下記確認項目に準拠した項目を確認し、会議資料を添付すること。
| Another Document |  |  | Another Document
Record | Record Name | Meeting minutes | Record | Record Name | 議事録
| Responsibility | Sony Product Design. |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 10 years |  | Keeping Period | 10 years
| Confirmation item |  |  | 確認項目
| ① Model features including power supply unit, panel, enclosure materials etc |  |  | ① 電源ユニット、パネル、エンクロージャー材料を含んだモデル仕様の確認
| ② Define take safety application type/countries |  |  | ②安規取得する規格名、国の確認
| ③ Optional Accessories (Make accessories to sell optionally clear. These are tested at the same time and are listed in CB/EMC report.) |  |  | ③同梱及び別売りアクセサリーの確認 (対象アクセサリーを明確にする。モデルと同時に試験が実施され、CB/EMCレポートに記載されること）
| ④Schedule ・Safety schedule (CB In, CB Out, EMC, Country Application) |  |  | ④スケジュール確認 ・安規スケジュール (CB In, CB Out, EMC, Country Application)
| ・Define Safety application target date (can achieve PP or MP) |  |  | ・安規取得日の設定 (PP or MPに間に合うこと)
| ・Cut-Off date for modification (Make Cut-Off date of the design change clear.) |  |  | ・設計変更締め切り日
| ・Panel / Multi panel (Confirm having multi-panel or not, a schedule of the certification.) |  |  | ・パネル認証（認証スケジュール）
| ・Power Supply Unit (Confirm a schedule of the certification.) |  |  | ・電源認証（認証スケジュール）
| ⑤ Required application documents and samples. (Make submission date clear.) |  |  | ⑤ 申請に必要な、書類、サンプル等を確認（提出データを確認する）
| ⑥ Organization of Safety approval. |  |  | ⑥安規取得体制の確認
Event Plan. Table

## P3-18
| No. | P3-18 |  |  |  | No. | P3-18
Control Item |  | Compliance indication check (1st) (ICCS/S-PAS) (prior to "Confirmation Meeting before PVT") |  |  | Control Item |  | Compliance indication check (1st) (ICCS/S-PAS) (prior to "Confirmation Meeting before PVT")
| Event Requirement |  |  |  |  | Event Requirement
| Responsibility | Product Design |  |  |  | Responsibility | 商品設計
| Approval | Responsible person of Product Design |  |  |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! | #REF! | #REF! |  | Acceptation for ODM | #REF! | #REF!
| Criteria, Rule, etc. | Product design person in charge makes the compliance check sheet of the charge model before "Confirmation Meeting before PVT" by using ICCS/S-PAS and confirms a necessary indication requirement. |  |  |  | Criteria, Rule, etc. | 商品設計担当者は、PVT前確認会議前に、ICCS/S-PASを使用して、担当モデルのコンプライアンスチェックシートを作成し、必要な表示要求項目を確認する。 製品安全担当部署は、ICCS/S-PAS上で商品設計担当部署の確認結果を確認する。
|  | ICCS : Integrated Compliance Check System |  |  |  |  | ICCS : Integrated Compliance Check System
|  | https://www2.crossview.sony.biz/tv/compliance/index/ |  |  |  |  | https://www2.crossview.sony.biz/tv/compliance/index/
|  | S-PAS Top page |  |  |  |  | S-PAS Top page
|  | http://gcp.sony.com/sites/S-PAS/SitePages/S-PAS_Support_Site.aspx |  |  |  |  | http://gcp.sony.com/sites/S-PAS/SitePages/S-PAS_Support_Site.aspx
|  | (Important notice) If Safety and Compliance related changes are happened after 1st ICCS/S-PAS Check, you should confirm a necessary indication requirement by using ICCS/S-PAS every time. (Example. parts change, production place change) |  |  |  |  | （重要事項） 最初のICCS/S-PASチェックの後に安全性とコンプライアンスに関連する変更が発生した場合は、ICCS/S-PASを使用して毎回必要な適応要件を確認する必要があります。 （例：部品の変更、生産場所の変更）
| Another Document |  |  |  |  | Another Document
Record | Record Name | Compliance Check Sheet |  |  | Record | Record Name | Compliance Check Sheet
| Responsibility | Sony Product Design |  |  |  | Responsibility | Sony Product Design
| Where/How to keep | ICCS/S-PAS |  |  |  | Where/How to keep | ICCS/S-PAS
| Keeping Period | 1 years |  |  |  | Keeping Period | 1 years
Event Plan. Table

## P3-19
メインイベント | P3-19. 再発防止チェックシート |  |  |  |  | Main Event | P3-19. Recurrence prevention check sheet
目的 | 過去に起きたHW問題の再発を防止するためのチェックシート |  |  |  |  | Purpose | Check sheet for preventing past HW problem
承認者 | 商品設計PM |  |  |  |  | Approval | Project Manager of PD
開催部署 | 試作前確認会議 |  |  |  |  | Responsibility | Each meeting before starting trial
参加者 | - |  |  |  |  | Atendees | -
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 各試作イベントでチェックシートの進捗確認を行う。 DFJまでに収束させること |  | Project |  |  |  | Check progress in each trial event. Complete all check item by DFJ.
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | F-JIRA, M-JIRAで管理されている最新の不具合案件をチェックリストにUpdateする。 |  | 再発防止チェックシート |  |  | Product Design | It will be updated to latest isssues into Recurence prevention check sheet |  | Recurrence prevention check sheet
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
C
文書管理 | [5 empty] | Document
記録物 |  | 再発防止チェックシート |  |  |  | Record Name |  | Recurrence prevention check sheet
管理部署 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | TBD |  |  |  | Where/How to keep |  | TBD
保管期限 |  | ー |  |  |  | Keeping Period |  | -
Event Plan. Table

## P3-20
メインイベント | P3-20. 人体影響 リスク軽減策 |  |  |  |  | Main Event | P3-20. Adverse Health Effects: Developing risk reduction measures
目的 | 適用対象製品の提供(DFJ、展示会への来場者への体験提供)までに、 人体影響による健康被害のリスク低減策を策定、実施、承認を取得している事 |  |  |  |  | Purpose | Develop, implement, and obtain measures to reduce the risk of health damage due to human effects before offering the applicable products (providing experiences to DFJ and exhibition visitors)
承認者 | 設計責印者/品質責任者 ★QMS(QED発行)では、品質オフィサーのみ |  |  |  |  | Approval | Responsible person of Product Design and responsible person of QA
開催部署 | 商品設計部門 |  |  |  |  | Responsibility | Product Design
参加者 | 商品設計部門/開発設計部門/企画・MK部門/品証・CS部門 |  |  |  |  | Atendees | Product Design/Development Design/Product Planning/QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・リスク分類毎に下記対応が実施されていること リスク分類1：少なくともQMS-348J 4.3に記載 されている低減策を検討。 リスク分類2：リスク低減策の案を本社品質・CS部門へ 報告し、合意を得る 案が無い場合は、本社品質・CS部門へ 相談し、低減策を策定、合意を得る ・リスク低減策について品質責任者(品質オフィサー)、設計責任者の承認を取得 又は、品質責任者、設計責任者から権限移譲された者 ・承認後、DFJ又は展示会の来場者への体験提供の場でリスク低減策実施計画を説明。 ・製品、展示会などの体験提供の場で、リスク低減策が実施される事 |  | Project |  |  |  | · The following measures have been implemented for each risk classification. [Risk class 1] The risk reduction measures specified in QMS-328E 4.3 must be at least developed. [Risk class 2] Planned risk reduction measures must be reported to the HQ Quality & CS Office and obtain the approval. If there are no such measures, must consult with the HQ Quality & CS Office and such measures must be developed after obtaining the approval. · Obtained approval from the responsible person of QA (Quality Officer) and responsible person of product design or delegated authority. · Explaining the plan to implement risk reduction measures at a place where DFJ or exhibition visitors can provide experience. · Risk reduction measures will be implemented at places to provide experiences such as products and exhibitions.
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | ・リスク低減策の策定 必要に応じて、QEDに低減策に関して、相談 ・品質責任者(品質オフィサー)、設計責任者の承認を取得 |  | 人体影響の判定・記録シート |  |  | Product Design | · Developing risk reduction measures. Consult with QED as needed for risk reduction measures. · Obtain approval from the responsible person of QA (Quality Officer) and responsible person of product design. |  | Adverse Health Effects Check and Recording Sheet
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | 人体影響の判定・記録シート |  |  |  | Another Document |  | Adverse Health Effects Check and Recording Sheet
|  | 人体影響の判定の概要書 | [5 empty] | Summary of classification of adverse health effects
文書管理 | [5 empty] | Document
記録物 |  | 人体影響の判定・記録シート |  |  |  | Record Name |  | Adverse Health Effects Check and Recording Sheet
管理部署 |  | 商品設計 |  |  |  | Responsibility |  | Product design
保管場所・方法 |  | e-21 |  |  |  | Where/How to keep |  | e-21
保管期限 |  | 生産終了から10年 |  |  |  | Keeping Period |  | 10 years after on line
| 【目的】 |  |  |  |  | 【Purpose】
| 人体影響による健康被害のリスクを評価し、低減すべきかを判断する。 |  |  |  |  | To assess the risks of health damage caused by adverse health effects and to determine whether or not the risks should be reduced
| 対象：販売、頒布、貸与、展示、体験提供する製品。 ハードウェア、ソフトウェア、コンテンツを含む。 |  |  |  |  | This item applies to the products that companies in the Sony Group sale, distribute, rent, exhibit and provide experiences for.
In addition, the products include hardware, software and contents (regardless of whether they are prototypes or commercially manufactured products).
| 【適用対象記録方法】 |  |  |  |  | 【Applicable recording method】
| 各Model、展示会毎に実施 |  |  |  |  | Implemented for each model and exhibition annual schedule
| e.g. FY21 model(Segment名) |  |  |  |  | E.g. FY21 model (Segment name)
| 【ルール】 |  |  |  |  | 【Rule】
| 1. リスク分類毎に下記対応を実施。 |  |  |  |  | 1. The following measures have been implemented for each risk classification.
| リスク分類1：少なくともQMS-348J 4.3に記載されている低減策を検討。対応内容、実施方法を関連部署で協議。 |  |  |  |  | [Risk class 1] | The risk reduction measures specified in QMS-328E 4.3 must be at least developed. Discuss the details of reduction measures and implementation methods in related departments.
リスク分類2：リスク低減策の案を本社品質・CS部門へ報告し、合意を得る
| 案が無い場合は、本社品質・CS部門へ相談、低減策を策定、合意を得る |  |  |  |  | [Risk class 2] | Planned risk reduction measures must be reported to the HQ Quality & CS Office and obtain the approval. If there are no such measures, must consult with the HQ Quality & CS Office and such measures must be developed after obtaining the approval.
※リスク低減策の妥当性がわかる根拠を明確にする事
| 2. 本社品質・CS部門への報告結果、策定したリスク低減策を人体影響の判定・記録シートに記入し、品質責任者(品質オフィサー)、設計責任者の承認を取得 |  |  |  |  | * Clarify the basis for understanding the validity of risk reduction measures.
| 又は、品質責任者、設計責任者から権限移譲された者 |  |  |  |  | 2. Obtain approval from the quality manager (quality officer) and design manager for the Adverse Health Effects Check and Recording Sheet after input reported result to the HQ Quality & CS Office.
| 3. 承認後、DFJ又は、展示会への来場者への体験提供の場でリスク低減策を実施。 |  |  |  |  | Or a person who has been delegated authority from the quality manager or the design manager.
| ※展示会については、展示予定の計画を提示する。 |  |  |  |  | 3. After approval, do plan to implement risk reduction measures at a place where DFJ or exhibition visitors can provide experience.
| 5. 人体影響の判定・記録シートにリスク低減策実施を追記し、本社品質・CS部門へ提出。 |  |  |  |  | * For exhibitions, present the plans for the exhibition.
4. Added the implementation of risk reduction measures to the Adverse Health Effects Check and Recording Sheet and submit it to the HQ Quality & CS Office.
Event Plan. Table

## P3-21
メインイベント | P3-21. PVT前確認会議 |  |  |  |  | Main Event | P3-21. Confirmation Meeting before PVT (Production Verification Trial)
目的 | PVT実施の可否を判定する （BOMリリース前確認確認会議との統合も可） |  |  |  |  | Purpose | Judgment for go to PVT phase （Can be combined with before BOM release confirmation meeting）
承認者 | Project Manager |  |  |  |  | Approval | Project Manager
開催部署 | 商品設計/開発設計 |  |  |  |  | Responsibility | Product Design/Development Design
参加者 | 商品設計/開発設計/SW設計/品質・CS |  |  |  |  | Attendees | Product Design/Development Design/SW Design/QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | PVT前確認会議資料 BOMリリース前確認会議資料 | 1. 設計残問題 AA,A=0,B≦5 又はB≦10で改善計画が明確になっていること 2. ソフトウェアリリース *PVT開始時に使用するソフトウェアが準備されていること *PVT評価時に使用するソフトウェアのリリース計画が明確になっていること 3. データ設定またはソフトウェア仕様による問題 *残問題は、PVTおよび設計検討活動を進める上で大きな障害とならないこと（例：スケジュールの影響） 4. パネルDFJにおいて設計完了の見込み有り、また原則としてパネルDVT DRが実施されていること 5. 品質目標の重要課題(D4Q[Level1/2]、DRBFM)の進捗に問題がないこと 6. 設計仕様に変更点が発生していないかどうかを確認すること。変更点がある場合は、実施イベント計画表の変更が必要ないかどうかを関係者で協議すること 7. 製品アセスメント（1回目）の設計承認が完了すること 8. 製品、展示会などの体験提供の場で、リスク低減策が実施される事 All confirmation items are OK. | PVT前確認会議議事録 BOMリリース前確認会議議事録 発表資料 | Project |  |  | PVT preconfirmation meeting material Before BOM release confirmation meeting material | 1. Pure hardware problem Remaining Issues: within AA,A=0,B≦5 or B≦10 and have clear plan to solve them 2. Software Release *Software for PVT start is ready. *Plan for releasing software for PVT evaluation is clarified. 3. Problem caused by Data Setting or software specification Remaining issues should not be a big obstacle to proceed PVT Trial and Design Review activity (Ex. Schedule impact) 4. Clear plan to have Panel DFJ and finish Panel design. Basically Panel DVT DR being carried out. 5. There shall be no problem in progress of important subject(D4Q[Level1/2] and DRBFM) of Quality Target. 6. Confirm whether change point occurs or not at design specification. If there is change point, discuss with related people whether it is necessary to change Event planning list. 7. Design approval of the product assessment (1st) being completed. All confirmation items are OK. | PVT Confirmation Conference Minutes Confirmation meeting minutes before BOM release Briefing paper
商品企画 | [5 empty] | Product Planning
開発設計 | P3-12. Key Device ES確認 |  |  |  |  | Development design | P3-12. Confirmation for Key Device ES
商品設計 | P2-5. Patent確認:[特許確認] 新規案件追加の有無が確認できていること [クリアランス確認] クリアランス確認とその対応方法が確立されていること P3-2. DCE Compliance confirmation meeting P3-4. DVT P3-5. SAPAS(DVT)レポート/CIT(OoBE対象モデル以外)実施 P3-13. 基本画音質 P3-17. 安規/コンプライアンス会議 P2-8. 輝度スペックについて、シリーズ間/年度間での整合を確認し、必要に応じてリストをアップデートする P3-20. 人体影響リスク低減策策定 |  | P2-5. コンプライアンスマスターリスト P3-9. RIPR確認 1st (check sheet) P3-10. 品質ボトムCheck Sheet 1st P3-11. 製品アセスメント check sheet 1st P3-18. コンプライアンス表示チェック 1st P3-19. 再発防止チェックシート P3-20. 人体影響の判定・記録シート(低減策) |  |  | Product Design | P2-5. Patent Confirmation: Confirming the existence of new item addition Clearance confirmation and response method have been established P3-2. DCE Compliance confirmation meeting P3-4. DVT(Design Verification Trial) P3-5. SAPAPS at DVT stage/CIT(other than OoBE model) P3-13. Judgment of basic PS (Picture/Sound) P3-17. Confirmation Meeting for Product Safety and Compliance P2-8. Confirm the consistency of luminance specifications inbetween series and previous models and update the spec data on the list as needed. |  | P2-5. Compliance master list P3-9. RIPR check (1st) P3-10. Minimum Product Quality Rules and Requirements check (1st.) P3-11. Product assessment check (1st.) P3-18. Compliance indication check 1st P3-19. Recurrence prevention check (Check for recurrence prevention by check sheet in each design)
SW | P3-16. αリリース -PVT開始時に使用するソフトウェアのリリース，およびPVT評価用ソフトウェアのリリース計画 |  |  |  |  | SW | P3-16. α release -Software for PVT start is released and prepare plan for releasing software for PVT evaluation.
Panel | P3-14. パネルDVT DR会議済 |  |  |  |  | Panel | P3-14. DR Meeting for Panel DVT
品証 | P3-7. DR会議 for DVT P3-8. OoBE（OoBE対象モデル) |  |  |  |  | QA | P3-7. DR Meeting for DVT result P3-8. OoBE(Out of Box Experience) (OoBE target model)
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 3年 |  |  |  | Keeping Period |  | 3 years after On Line
| Objective |  | *Judgment for go to PVT phase
| Definition of Confirmation before PVT in the project | Scope | *Detail plan of final confirmation until Design Validation
*Confirmation of changing point from Design concept meeting
|  | Precondition | 1. Pure hardware problem Remaining Issues: within AA,A=0,B≦5 or B≦10 and have clear plan to solve them
2. Software problem *Final SPEC. SW (all function is implemented and stable enough by general operation) has clear plan to supply to PVT *Confirm SQA evaluation release meeting schedule and have expectation of GO
3. Problem caused by Data Setting or software specification Remaining issues should not be a big obstacle to proceed PVT Trial and Design Review activity (Ex. Schedule impact)
4. Clear plan to have Panel DFJ and finish Panel design. Basically Panel DVT DR being carried out.
5. There shall be no problem in progress of important subject of Quality Target. If unable to achieve, recovery plan shall be submitted.
6. Compliance indication check(1st) by ICCS is completed. (Before "Confirmation Meeting before PVT")
7. Confirm whether change point occurs or not at design specification. If there is change point, discuss with related people whether it is necessary to change Event planning list.
（can be combined with before BOM release confirmation meeting） 8. Design approval of the product assessment (1st) being completed.
|  | Schedule | *Schedule update and progress check
|  | Organization/System | *reconfirmation for organization/system
*confirmation for system of model introduction into factory
| Progress of the project that should be confirmed in Confirmation before PVT | Electrical Design | *Final schematic is completed
*confirmation of changing point
|  | SW Design | *SW release plan until PVT assy
|  | Panel Design | *Panel SPEC fixed
*Detail schedule between DFJ and MP
|  | Mechanical Design | *confirmation of completion level of die
|  | Power Supply and Inverter Design | *Power Supply/INV SPEC fix
*Power Supply/INV DFJ schedule
|  | New Parts | *Problem review and schedule confirmation
|  | Key Device | *Problem review and schedule confirmation
|  | Tuner | *Problem review and schedule confirmation
|  | Picture Quality Sound Quality | *Basic P/S Quality fixed
*Final P/S Quality investigation schedule
|  | Compliance: - Safety standard - Broadcast - Features (eg: Dolby,etc) | *Update progress on the confirmation plan to get related Compliances/certification approval
|  | PWB | *confirmation for changing point
|  | EMI | *confirmation for EMI data including Panel
*confirm final EMI evaluation plan by model
|  | IP confirmation result | *check IP clearance result
|  | Spec-chart | *status check of data transfer to Palette
| Issue |  | *make clear recovery plan for unconfirmed item
| Risk | Risk Management | *progress check for Risk Management Chart
*risk confirmation for changing point
*confirmation for progress and changing point of the cryptographic key length
| Guideline of confirmation items | Line Up | *confirmation of the latest information
|  | Benchmark | *reconfirmation of the latest information
|  | Market situation | *reconfirmation of the latest information
|  | Quality Target | *progress check for Quality Concept
|  | Parts count/variety | *confirm estimation at MP, target and action plan
|  | Cost/MP | *confirm estimation at MP, target and action plan
|  | SST | *confirm estimation at MP, target and action plan
|  | Number of production plan and allocation | *update of production plan
|  | Parts order situation | *before BOM release meeting is done or scheduled
|  | factory | *confirm introduction system
*involvement of production people
Event Plan. Table

## P3-22
No. | P3-22 |  |  | No. | P3-22
Control Item | Confirmation Meeting before BOM Release |  |  | Control Item | BOMリリース前確認会議
Event Requirement |  |  |  | Event Requirement
Responsibility | Product Design |  |  | Responsibility | 商品設計
Attendees | Product Design, DR, Planning & Control, Procurement, Software Design, Mechanical Design, Panel Design, Product Planning |  |  | Attendees | 商品設計、DR、管理、調達、SW設計、メカ設計、パネル設計、商品企画
Approval | Responsible person of Product Design | #REF! | #REF! | Approval | 商品設計責任者
Acceptation for ODM | #REF! | #REF! | #REF! | Acceptation for ODM | #REF! | #REF! | #REF!
Criteria, Rule, etc. | 1) Ratio of released design drawings ≥80% (Except for internal parts, micon, board, harness construction and printed matter-label-packing) |  |  | Criteria, Rule, etc. | 1）原則として出図率80％以上とする。但し、社内製部品、ﾏｲｺﾝ,基板、ﾊｰﾈｽ組み立て、印刷物、ﾗﾍﾞﾙ、梱包材は除く
| 2) The schedule to hold Service classification meeting is to be clarified. |  |  |  | 2) サービス区分会議の開催予定が明確である事
| 3) There shall be no problem in the result of the pre-confirmation of export regulation (the targeted model only.) |  |  |  | 3) 輸出規制事前確認の判定結果に問題が無いこと。（対象モデルのみ）
| 4) Verify environment data for all parts are registerd in S-PAS If there is any parts without environmental data, clarify PIC and expected schedule obtaining environmental data. |  |  |  | 4) 全部品の環境データがS-PASに登録されていることを確認 環境データがない部品がある場合は、PICと環境データ取得予定スケジュールを明確にすること
| (can be combined with Before PVT confirmation meeting ) |  |  |  | （時期が合えば、PVT前確認会議と同時開催）
Another Document | FDR023-04_E Form_Before PVT confirmation meeting_Before BOM Release Meeting Minutes |  |  | Another Document | FDR023-04_E Form_Before PVT confirmation meeting_Before BOM Release Meeting Minutes
Record Name | meeting minutes |  |  | Record Name | 会議議事録
Responsibility | Product Design |  |  | Responsibility | 商品設計
Where/How to keep | e21 |  |  | Where/How to keep | e21
Keeping Period | 3 years after on line |  |  | Keeping Period | 3 years after on line
| Objective |  | *judgment for parts release and official Model MP order to factory |  | 目的 |  | ・部品をリリースして、正式に事業所へ生産を依頼するための判断
| Definition of Before BOM Release confirmation meeting in the project | Scope | *confirmation of BOM completion level, registration situation of new parts, factory allocation production/sales plan |  | プロジェクトの中での 「BOMリリース前確認会議」の 定義 | スコープ | ・BOM完成度、新規部品登録、事業所アロケーション、製造/販売プランの確認
|  | Precondition | *Ratio of released design drawings should be better than 80% (Except for internal parts, micon, board, harness construction and printed matter-label-packing) |  |  | 前提条件 | ・原則として出図率80％以上とする。但し、社内製部品、ﾏｲｺﾝ、基板、ﾊｰﾈｽ組み立て、印刷物、ﾗﾍﾞﾙ、梱包材は除く
|  |  | *The schedule of Service classification meeting is to be clarified |  |  |  | ・ｻｰﾋﾞｽ区分会議の開催予定が明確である事
|  |  | *There shall be no problem in the result of the pre-confirmation of export regulation (the targeted model only.) |  |  |  | ・輸出規制事前確認の判定結果に問題が無いこと。（対象モデルのみ）
|  |  | (if possible, this meeting should hold at same time with Before PVT meeting) |  |  |  | （時期が合えば、PVT前確認会議と同時開催）
|  | Schedule | *confirm about parts order situation and model introduction schedule |  |  | スケジュール | ・部品手配と事業所導入スケジュール確認
|  | Organization/System |  |  |  | 組織・体制
| Progress of the project that should be confirmed in Before BOM Release confirmation meeting | Electrical Design | *BOM completion level |  | 「BOMリリース前確認会議」の 段階で確認すべき プロジェクトの進捗状況 | 電気設計 | ・BOMの完成度
|  | SW Design |  |  |  | SW設計
|  | Panel Design | *New Panel supply plan |  |  | パネル設計 | ・新規パネル供給計画の確認
|  | Mechanical Design | *Final tooled parts supply plan |  |  | メカ設計 | ・最終金型部品の供給計画確認
|  |  | *About the derivative model and the color variation model, PIC of Mech. Design make Mechanical differences list and explain it in Before BOM Release confirmation meeting. Mechanical differences list is attached in the meeting minutes. |  |  |  | ・デリバティブ・カラバリなどのモデルについては、設計にてメカ相違点リストを作成し、検印した資料をBOMリリース前確認会議にて説明し、議事録に添付する。
|  | Power Supply and Inverter Design | *Supply plan confirmation |  |  | 電源/インバーター設計 | ・供給計画の確認
|  | New Parts | *Registration situation of New parts |  |  | 新規部品 | ・新規部品登録状況
|  | Key Device | *Registration situation and supply plan |  |  | キーデバイス | ・登録状況と供給スケジュール
|  | Tuner | *Registration situation and supply plan |  |  | チューナー | ・登録状況と供給スケジュール
|  | Picture Quality Sound Quality |  |  |  | 画音質
|  | Safety Standard |  |  |  | 安全規格・コンプライアンス
|  | compliance (ex : environment, Digital broadcast, Dolby, etc.) |  |  |  | （環境、Digital放送、Dolby等）
|  | PWB | *confirmation for changing point |  |  | PWB | ・登録状況と供給スケジュール
|  | EMI |  |  |  | EMI
| Issue |  |  |  | 課題
| Risk | Risk Management | *progress check for Risk Management Chart *risk confirmation for changing point |  | リスク | リスクマネージメント | ・新規部品等でリスク有る場合は確認
| Guideline of confirmation items | Line Up |  |  | 確認項目のガイドライン | ラインアップ
|  | Benchmark |  |  |  | 他社との比較
|  | Market situation |  |  |  | マーケット状況
|  | Quality Target |  |  |  | 品質ターゲット
|  | Parts count/variety |  |  |  | 部品点数・品種
|  | Cost/MP |  |  |  | コスト・MP
|  | SST |  |  |  | SST
|  | Number of production plan and allocation | *update of production plan |  |  | 生産計画台数・アロケーション | ・生産計画のアップデート
|  | Parts order situation | *before BOM release meeting is done or scheduled |  |  | 部品手配 | ・BOMリリース前確認会議済み、または予定済み
|  | factory | *confirm introduction system |  |  | 事業所 | ・導入体制の確認
|  |  | *The PP Evaluation Plan (evaluation/test items, schedule and sample quantity) shall have been made clear. |  |  |  | ・PP評価計画（評価・試験項目、及び供試台数）が明確である事。
|  |  | *involvement of production people |  |  |  | ・導入前の事業所からの参加
Event Plan. Table

## P3-23
No. | P3-23 | No. | P3-23
Control Item | BOM Release | Control Item | BOM Release
Event Requirement | Mandatory | Event Requirement | Mandatory
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Product Design | Attendees | 商品設計
Approval | Responsible person of Product Design | Approval | 商品設計責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *Official BOM release *Start official operation of RN | Criteria, Rule, etc. | *OMを正式リリースする *RN（Release Notice）の正式運用開始
Another Document | Non | Another Document | Non
Record Name | S-PAS Model master | Record Name | S-PAS 機種マスター
Responsibility | SGS | Responsibility | SGS
Where/How to keep | in S-PAS server as BOM release record | Where/How to keep | in S-PAS server as BOM release record
Keeping Period | not provided | Keeping Period | not provided
Event Plan. Table

## P3-24
No. | P3-24 | No. | P3-24
Control Item | Official Model Release | Control Item | Official Model Release
Event Requirement | Mandatory | Event Requirement | Mandatory
Responsibility | Product Design | Responsibility | Product Design
Attendees | Product Design, Mechanical Design, Procurement, Planning & Control | Attendees | 商品設計、メカ設計、調達、商品企画
Approval | Responsible person of Product Design | Approval | Responsible person of Product Design
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *Official release of BOM released models | Criteria, Rule, etc. | *BOMリリースした機種を正式に公開する
Another Document | Non | Another Document | Non
Record Name | S-PAS Model master | Record Name | S-PAS 機種マスター
Responsibility | SGS | Responsibility | SGS
Where/How to keep | in S-PAS server as BOM release record | Where/How to keep | in S-PAS server as BOM release record
Keeping Period | 3 years | Keeping Period | 3 years
Event Plan. Table

## P3-25
メインイベント | P3-25. サービス区分会議 |  |  |  |  | Main Event | P3-25. Service classification meeting
目的 | 商品の仕様を確認し、サービス構想会議で決定した修理に関するポリシーより、使用部品をサービスパーツ登録するかどうかを検討する。 |  |  |  |  | Purpose | Check the product specifications and consider whether to register parts as service parts based on the repair policy determined in the service concept meeting.
承認者 | サービス推進担当部署責任者 |  |  |  |  | Approval | Responsible person of Service Promotion
開催部署 | サービス推進 |  |  |  |  | Responsibility | Service Promotion
参加者 | 商品設計、サービス推進 |  |  |  |  | Atendees | Product Design, Region CS, CS section
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ･次の 1) - 5) が明確に決定されている事 1) 該当モデルのサービス方法 2) サービス対象部品のRP区分 3) サービス Manualの準備担当者と日程 4) IRPの決定とその準備担当者と日程、および、 サービスA番が取得できている事を確認すること。 未取得の場合は、1週間以内に取得しSP責任者へ 報告すること。 5) サービス実行部門への新機種名登録実行者と日程 （日本向けモデルのみ） | サービス区分会議議事録 GRPMによる部品表更新 | Project |  |  |  | Followings are to have been clarified: 1) Way of after-sales service for applicable models. 2) Service parts RP-Coding 3) Person who creates Service Manual and its schedule. 4) IRP, person who creates IRP, and its schedule and confirm whether service A can be acquired. If unable to acquire, acquire within 1 week and report to SP Manager. 5) Person who register new model name to Service sect. and its schedule. (Japan model only) | Minutes of Service Classification Meeting Parts List update by GRPM
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | P3-23. BOM リリース ・新規部品の図面及び、納入仕様書発行 |  |  |  |  | Product Design | P3-23. BOM release ・ Issuing new parts drawings and delivery specifications
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品質・CS | リリースされたBOMで、サービス区分が未登録の部品に対してサービス区分を決める。 |  |  |  |  | QA・CS | In the released BOM, determine the service class for the parts for which the service class is not registered.
別途文書 | [5 empty] | Another Document
文書管理 | [5 empty] | Document
記録物 |  | サービス区分会議議事録 |  |  |  | Record Name |  | Minutes of Service Classification Meeting
管理部署 |  | サービス推進 |  |  |  | Responsibility |  | CS Section
保管場所・方法 |  | SOEMファイルサーバー：SPC_Cover_Summary（\\43.74.140.20\grp_SPC_Document\5) SPC_Cover_Summary） |  |  |  | Where/How to keep |  | SOEM file server：SPC_Cover_Summary（\\43.74.140.20\grp_SPC_Document\5) SPC_Cover_Summary）
保管期限 |  | 1年 |  |  |  | Keeping Period |  | 1 year
Event Plan. Table

## P3-26
| No. | P3-26 |  | No. | P3-26
Control Item |  | Field test | Control Item |  | Field test
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Not specified |  | Approval | Not specified
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | * Market test performed on the site where products are actually in use, mainly for models with new chassis and new devices, in the design stage. * Ranking will be performed comply with appendix “Problem Ranking Table” for problem occurrence upon consultation with DR after test.) (If problems of Key Devices occurred, actions are to be taken when fully prepared.) |  | Criteria, Rule, etc. | *主として新シャーシ、新デバイス採用のモデルで設計段階で行う市場テスト。 *テスト後、DRと協議の上、発生問題に対して、“Problem Ranking Table”に従いランク付けを行う。(キーデバイスで問題が発生した場合に対応が十分に可能な時点で行う。)
| Another Document |  |  | Another Document
|  | FDR023E-05 Form_Field Test Report |  |  | FDR023E-05 Form_Field Test Report
Record | Record Name | Field Test Report | Record | Record Name | Field Test Report
| Responsibility | Sony Product Design |  | Responsibility | Sony Product Design
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 5 years |  | Keeping Period | 5 years
| Problem Ranking Table (for AA, A, B, C Rank) (Note 1) |  |  | Problem Ranking Table (for AA, A, B, C Rank) (Note 1)
| (Note 1): A, B and C Ranking given here is general principle and may change depending upon nature of the product or evaluation condition. |  |  | （注1）：ここに記載されているA、B、Cのランキングは一般的な原則であり、製品の性質や評価条件によって変わる場合があります。
| (Note 2): This classification is to be applied even when no symptom is found, if the material, components, or design are similar or the same as those which had problems in the past. |  |  | （注2）：この分類は、症状が見つからない場合でも、材料、コンポーネント、またはデザインが過去に問題があったものと類似または同じである場合に適用されます。
Event Plan. Table

## P3-27
No. | P3-27 |  |  | No. | P3-27
Control Item | PVT (Production Verification Trial) |  |  | Control Item | PVT (Production Verification Trial)
Event Requirement | Mandatory/Optional |  |  | Event Requirement | Mandatory/Optional
Responsibility | Product Design |  |  | Responsibility | 商品設計
Attendees | not provided |  |  | Attendees | not provided
Approval | Not specified | #REF! | #REF! | Approval | Not specified | #REF! | #REF!
Acceptation for ODM | #REF! | #REF! | #REF! | Acceptation for ODM | #REF! | #REF! | #REF!
Criteria, Rule, etc. | see below |  |  | Criteria, Rule, etc. | see below
Another Document | Non |  |  | Another Document | Non
Record Name | not provided |  |  | Record Name | not provided
Responsibility | not provided |  |  | Responsibility | not provided
Where/How to keep | not provided |  |  | Where/How to keep | not provided
Keeping Period | not provided |  |  | Keeping Period | not provided
| Objective |  | *final products verification by model |  | 目的 |  | ・モデル別の最終商品確認
| Criteria at start | HW | *before PVT confirmation meeting finished and judgment was go |  | PVT開始時のクライテリア | HW | ・PVT前確認会議開催、判定済み
|  | SW | *confirm SQA evaluation release meeting schedule and have expectation of GO |  |  | SW | ・SQA評価リリース判定会議合格済み、または合格の見込み有り
（設計もクライテリア確認済み）
|  | Panel | *Final SPEC CS panel is available |  |  | パネル | ・最終仕様のCSパネル供給可能
|  |  | *evaluation schedule until panel DFJ is clear |  |  |  | ・パネルDFJまでの評価計画明確
|  | Mechanical | *Final parts is available |  |  | メカ | ・最終型物品供給可能
| Guideline of activities |  | *Final products confirmation |  | アクティビティのガイドライン |  | ・最終商品仕様確認
|  |  | *confirmation for all function (including production mode and service mode) |  |  |  | ・すべてのファンクション確認（工場モードとサービスモード含む）
|  |  | *DR problem closed completely |  |  |  | ・DR問題点の完全解決
|  |  | *final Panel SPEC confirmation |  |  |  | ・最終パネル仕様確定
|  |  | *confirm final mechanical parts SPEC |  |  |  | ・最終メカ仕様確定
|  |  | *final conclusion of Picture/Sound Quality |  |  |  | ・画音質最終確定
|  |  | *final confirmation of heat and EMI |  |  |  | ・熱、輻射対策の最終確定
|  |  | *tolerance investigation |  |  |  | ・バラツキ検討
|  |  | *approval for safety standard |  |  |  | ・安全規格申請
|  |  | *final Field Test |  |  |  | ・FT最終確認
|  |  | *complete each check sheets |  |  |  | ・各種チェックシート完成
| Required output |  | *panel DFJ finished |  | 要求されるアウトプット |  | ・パネルDFJ完了
|  |  | *Keep EMI target margin for 3 sets |  |  |  | ・EMI3台測定でマージン確保
|  |  | *Power Supply/INV. DFJ completed |  |  |  | ・電源DFJ完了
|  |  | *no remaining problem |  |  |  | ・残問題無し
|  |  | *SW release |  |  |  | ・SWリリース
|  |  | *prospect of necessary item for MP is clear |  |  |  | ・量産までに必要な項目の見通し明確
|  |  | (for example, parts supply, over all adjustment standard, safety standard approval, evaluation schedule) |  |  |  | （部品供給、作業指導書、案規取得見通し、評価計画など）
Event Plan. Tab le

## P3-28
| No. | P3-28 |  |  |  | No. | P3-28
Control Item |  | Confirmation before DCE Application |  |  | Control Item |  | DCE申請前確認
| Event Requirement | Mandatory/Optional |  |  |  | Event Requirement | Mandatory/Optional
| Responsibility | Digital Country Expansion |  |  |  | Responsibility | DCE責任部署
| Attendees | - |  |  |  | Attendees | -
| Approval | Responsible person of Digital Country Expansion | 0 | 0 |  | Approval | DCE責任部署
| Acceptation for ODM | #REF! | #REF! | #REF! |  | Acceptation for ODM | #REF! | #REF! | #REF!
| Criteria, Rule, etc. | 【Content Implementation】 Check the Digital Broadcast application sample and document with the experts to comply regulations and technical standards of the applicable destination before the sample application. |  |  |  | Criteria, Rule, etc. | 【コンテンツの実装】デジタル放送アプリケーションのサンプルを確認し、専門家とドキュメントを作成してから、サンプルアプリケーションの前に該当する宛先の規制と技術基準を遵守する
|  | 【Check Point】 |  |  |  |  | 【確認ポイント】
|  | · EMC: Confirmation is done without problem, or it is clearly expected to be confirmed. |  |  |  |  | · EMC: 問題がないこと、もしくは確認すべきことが明確でになっていること
|  | • Confirm Indication: Ready to submit the necessary Sample/Drawings etc. at application. |  |  |  |  | • 表示確認: 申請時に必要なサンプル/図面などを提出する準備ができていること
|  | Parts Materials: Necessary Parts information and sample are confirmed and ready. |  |  |  |  | 部品材料: 必要な部品情報とサンプルが確認され、準備ができていること
|  | • Structure: Check is completed without problem |  |  |  |  | • 構造: 問題がないことの確認が完了していること
|  | • Test: Confirmation is done without problem, or it is clearly expected to be confirmed. |  |  |  |  | • Test: 問題がないこと、もしくは確認すべきことが明確でになっていること
|  | 【Criteria】 |  |  |  |  | 【Criteria】
|  | When all follow-up items are made clear and To_Do_List is completed. |  |  |  |  | すべてのフォローアップ項目が明確になり、To_Do_Listが完了していること
|  | Due date and the person in charge must be made clear in To_Do_List. |  |  |  |  | To_Do_Listで期日と担当者を明確にする
|  | If a follow-up item has a risk, the risk must be specified in To_Do_List. |  |  |  |  | フォローアップ項目にリスクがある場合、To_Do_Listでリスクを特定する
|  | DCE approval schedule must be updated. |  |  |  |  | DCE承認スケジュールを更新する
|  | Confirm to complete each item in To Do List (sample) after this meeting within due date. |  |  |  |  | 期日内にTo Doリスト（Sample）の各項目を完了することを確認する
| Another Document | Non |  |  |  | Another Document | Non
Record | Record Name | DCE Request form , Shipment Confirmation List |  |  | Record | Record Name | DCE Request form , Shipment Confirmation List
| Responsibility | DCE |  |  |  | Responsibility | DCE
| Where/How to keep | e21 |  |  |  | Where/How to keep | e21
| Keeping Period | 3 years after On Line |  |  |  | Keeping Period | 3 years after On Line
| Checklist (Sample) |  |  |  |  | Checklist (Sample)
Event Plan. Table

## P3-29
| No. | P3-29 |  |  |  | No. | P3-29
Control Item |  | Confirmation Meeting before Product Safety Application |  |  | Control Item |  | 安全規格申請前確認会議
| Event Requirement |  |  |  |  | Event Requirement
| Responsibility | Product Design |  |  |  | Responsibility | 商品設計
| Attendees | Product Design, Safety, Digital Country Expansion |  |  |  | Attendees | 商品設計、製品安全、DCE
| Approval | Responsible person of Safety | #REF! | #REF! |  | Approval | 製品安全 | #REF! | #REF!
| Acceptation for ODM | #REF! | #REF! | #REF! |  | Acceptation for ODM | #REF! | #REF! | #REF!
| Criteria, Rule, etc. | 【Content Implementation】 Check the safety sample and document with the experts to comply regulations and technical standards of the applicable destination before the sample application. |  |  |  | Criteria, Rule, etc. | 【内容の実施】安規用サンプルと文書を専門家と確認し、サンプル申請前に適用先の規制と技術基準に遵守する。
|  | 【Check Point】 |  |  |  |  | 【確認ポイント】
|  | · EMC /Wireless: Confirmation is done without problem, or it is clearly expected to be confirmed. |  |  |  |  | · EMC /ワイヤレス： 問題がないこと、もしくは確認すべきことが明確でになっていること
|  | • Confirm Indication: Ready to submit the necessary Sample/Drawings etc. at application. |  |  |  |  | • 表示確認: 申請時に必要なサンプル/図面などを提出する準備ができていること
|  | Parts Materials: Necessary Parts information and sample are confirmed and ready. |  |  |  |  | 部品材料: 必要な部品情報とサンプルが確認され、準備ができていること
|  | • Structure: Check is completed without problem |  |  |  |  | • 構造: 問題がないことの確認が完了していること
|  | • Test: Confirmation is done without problem, or it is clearly expected to be confirmed. |  |  |  |  | • Test: 問題がないこと、もしくは確認すべきことが明確でになっていること
|  | 【Criteria】 |  |  |  |  | 【Criteria】
|  | When all follow-up items are made clear and To_Do_List is completed, this meeting is closed. |  |  |  |  | すべてのフォローアップ項目が明確になり、To_Do_Listが完了していること
|  | Due date and the person in charge must be made clear in To_Do_List. |  |  |  |  | To_Do_Listで期日と担当者を明確にする
|  | If a follow-up item has a risk, the risk must be specified in To_Do_List. |  |  |  |  | フォローアップ項目にリスクがある場合、To_Do_Listでリスクを特定する
|  | Safety approval schedule must be updated. |  |  |  |  | 安規承認スケジュールを更新する
期日内にTo Doリスト（Sample）の各項目を完了することを確認する
Confirm to complete each item in To Do List (sample) after this meeting within due date.
| Another Document |  |  |  |  | Another Document
Record | Record Name | meeting minutes |  |  | Record | Record Name | meeting minutes
| Responsibility | Sony Product Design |  |  |  | Responsibility | Sony Product Design
| Where/How to keep | e21 |  |  |  | Where/How to keep | e21
| Keeping Period | 3 years after On Line |  |  |  | Keeping Period | 3 years after On Line
| To Do List (Sample) |  |  |  |  | To Do List (Sample)
Event Plan. Table

## P3-30
No. | P3-30 | No. | P3-30
Control Item | SAPAPS at PVT stage | Control Item | SAPAPS at PVT stage
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Product Design, DR, Products Safety, Ordinary People | Attendees | 商品設計、DR、製品安全、一般人
Approval | Responsible person of QA(Safety) | Approval | QA責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | Countermeasures against problems occurred and Schedule for solution are to be clarified. (Comply with Common SAPAPS Standard (DS029001E) for details) | Criteria, Rule, etc. | 発生した問題に対する対策と解決のスケジュールを明確にすること （詳細については、共通SAPAPS標準（DS029001E）に準拠）
Another Document | DS029001E Common SAPAPS Standard | Another Document | DS029001E Common SAPAPS Standard
| FDS029001E-01 Form_SAPAPS Implementation Report |  | FDS029001E-01 Form_SAPAPS Implementation Report
Record Name | SAPAPS Implementation Report | Record Name | SAPAPS Implementation Report
Responsibility | Product Design | Responsibility | 商品設計
Where/How to keep | e 21 | Where/How to keep | e 21
Keeping Period | 15 years | Keeping Period | 15 years
Event Plan. Table

## P3-31
No. | P3-31 | No | P3-31
Control Item | CIT (Customer Installation Test)/OoBE at PVT stage | 管理項目 | CIT (Customer Installation Test)/OoBE at PVT stage
Event Requirement |  | 実施
Responsibility | Product Design | 主催部署 | 商品設計
Attendees | Product Design, DR, Products Safety, Ordinary People | 参加 | 商品設計，DR，製品安全，一般人
Approval | DR | 判定者・承認者 | DR
Criteria, Rule, etc. | * To implement CIT as the same time of SAPAPS. * Refer to the appendix CIT operation rule * Refer to the appendix OoBE Guideline | 判断基準・実施内容 | *CITをSAPAPSの実施と合わせて実施する。 *「CIT運用ルール」下記参照。 * OoBE Guideline参照
*問題点をクローズすること。
Another Document | OoBE CS.xlsx | 別途文書 | OoBE CS.xlsx
| OoBE Guideline |  | OoBE Guideline
Record Name | Problem of CIT | 記録文書 | CIT問題点
Responsibility | DR | 保管部署 | DR
Where/How to keep | JIRA | 保管方法 | JIRA
Keeping Period | 12 years. | 保管期限 | 12年
| CIT (Customer Installation Test) operation rule |  | CIT(Customer Installation Test)運用ルール
| 1. Purpose |  | １．目的
| CIT is the test, assumed as unpacking, setting, operating, watching TV, etc which user will perform after purchasing. It shall be intended for detecting problems from the evaluation of user point of view and perform rapid measurement. |  | CITとは、ユーザーが購入後に行なう、開梱、セッティング、操作する、TVを見るなどの行為を想定した試験であり、最終形態において、ユーザー視点による評価から不具合を発見し、早期対処を行なうことを目的とする。
| 2. Implementation responsible |  | ２．実行責任
| Host will be Product Design. Product Design responsible person will select implementation model in consulting with DR. |  | 主催は商品設計部署。実施モデルは商品設計がDRと協議して選定する。
| 3. Implementation term |  | ３．実施時期
| CIT will be implemented at the same time of SAPAPS. |  | SAPAPSの実施と合わせてCITを実施する。
| Measurement will be implemented until PVT if problem have been detected by DVT CIT. |  | DVT CITで問題点が発見された場合は、PVTまでに対策を実施する。
| 4. Test method |  | ４．試験方法
| (1) Test overview |  | (1)試験概要
| -Tester should have close sense to users and able to recognize problems. |  | ・試験者は、一般の人に近い感覚でかつ問題点に気がつく感性のある人が試験する必要がある。DRから1名（主）、設計から1名（副）
| -Confirm every operation according to the instruction manual. |  | ・取扱い説明書に沿って全ての操作を確認する。
| -Problems detected by CIT will be specified in JIRA. |  | ・CITにより発見された問題点は、JIRAに記載する。
| (2) CIT test flow |  | (2)CIT試験フロー
Unpackaging test (exterior / packaging check)
Accessory confirmation (instruction manual / fly sheet)
Installation (stand / wall)
開梱試験（外装・梱包確認）
付属品確認（取説・投げ込み類）
設置（スタンド/壁掛け）
Event Plan. Table

## P3-32
メインイベント | P3-32. PVT DR会議 |  |  |  |  | Main Event | P3-32. DR Meeting for PVT Result
目的 | 問題点を把握し、是正/改善についての計画を明確にする |  |  |  |  | Purpose | To grasp problems and make clear their correction/improvement plan.
承認者 | 品質評価（DR）責任者 |  |  |  |  | Approval | Responsible person of QA(DR)
開催部署 | 品質評価（DR） |  |  |  |  | Responsibility | QA(DR)
参加者 | 商品設計/デバイス/SW設計/品質評価(DR) |  |  |  |  | Atendees | Product Design/Device/SW Design/QA(DR)
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 残問題点に対し、是正/改善計画が明確であること。 | PVT DR会議議事録 | Project |  |  |  | The Correction/Improvement plan for remaining problem to be cleared. | Meeting minutes of PVT DR
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | PVT DR時制約事項 PVT DR評価(商品設計担当分) |  |  |  |  | Product Design | Limitation Item for DR evaluation PVT DR evaluation (Product Design assigned)
SW | PVT DR時制約事項 |  |  |  |  | SW | Limitation Item for DR evaluation
Panel | PVT DR時制約事項 |  |  |  |  | Panel | Limitation Item for DR evaluation PVT DR evaluation (Panel assigned)
品証 | PVT DR IN前確認会議 PVT DR評価計画（評価分担を含む） PVT DR評価(QA担当分) |  |  |  |  | QA | Before PVT DR IN Meeting PVT DR (Including evaluation assignment) PVT DR evaluation (QA assigned)
文書管理 | [5 empty] | Document
記録物 |  | PVT DR会議議事録 |  |  |  | Record Name |  | Meeting minutes of PVT DR
管理部署 |  | 品質評価(DR) |  |  |  | Responsibility |  | QA(DR)
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 12年 |  |  |  | Keeping Period |  | 12 years after On Line
DR問題点重要度ランクの定義（注1） | [5 empty] | Problem Ranking Table (for AA, A, B, C Rank) (Note 1)
（注1）これらのA,B,Cランク区分は一般的なものでありカテゴリー、機種内容、評価条件で異なる場合がある。 | [5 empty] | (Note 1): A, B and C Ranking given here is general principle and may change depending upon nature of the product or evaluation condition.
（注2）現在現象は出ていないが、過去に発生した問題と類似設計のもの及び類似部品、材料を使用しているものを含む。 | [5 empty] | (Note 2): This classification is to be applied even when no symptom is found, if the material, components, or design are similar or the same as those which had problems in the past.
Event Plan. Table

## P3-33
No. | P3-33 | No. | P3-33
Control Item | O-Cell DFJ | Control Item | O-Cell DFJ
Event Requirement | Mandatory/Optional | Event Requirement | Mandatory/Optional
Responsibility | Panel Design | Responsibility | パネル設計
Attendees | MUST : Panel Design, Mechanical Design, QA, Product Design, Procurement, DR | Attendees | 必須出席者：パネル設計、メカ設計、品質、商品設計、調達、DR
| WANT : Planning & Control, Panel Parts, Power Supply System Design(LD), Plant Panel Engineering |  | 任意出席者：企画、管理、部品技術、電源設計(LD), パネル技術(製造事業所)
Approval | Responsible person of Panel Design | Approval | パネル設計責任者
Criteria, Rule, etc. | 1. O-cell evaluation (FOS/OPT performance) is finished | Criteria, Rule, etc. | 1.O-cell評価 (FOS/光学)済み
| 2. Reliability test(THB/HC) is finished |  | 2.信頼性試験(高温高湿/ヒートサイクル)済み
| 3. T-con evaluation is finished |  | 3.T-con評価済み
| 4. Deliberation at O-cell WG/(COF WG)/(GOA PJ) |  | 4.O-cell WG (/COF WG/GOA PJ) 審議済み
| 5. T-con Hex confirmation MTG is finished |  | 5.Hex確認会済み
| 6. SET PVT DR (O-cell related) is finished |  | 6.SET PVT DR (O-cell関係) 済み
| [Review items below] |  | [Review items below]
| *O-cell vender's reliability test result |  | *O-cellメーカー信頼性試験
| *O-cell/T-con Product Specification |  | *O-cell/T-con納入仕様書
| *O-cell Cosmetic specification |  | *O-cell 検査規格
| *FMEA review |  | *FMEAレビュー
| *Schedule and number of the 1st MP lot |  | *MP 1st Lot日程と番号
Another Document | Panel Event Management Standard | Another Document | Panel Event Management Standard
Record Name | Meeting Minutes | Record Name | Meeting Minutes
Responsibility | Panel Design | Responsibility | パネル設計
Where/How to keep | e21 | Where/How to keep | e21
Keeping Period | 3 years | Keeping Period | 3 years
Event Plan. Table

## P3-34
| No. | P3-34 |  | No. | P3-34
Control Item |  | Judgment of champion panel performance | Control Item |  | チャンピオン用パネル性能判定
Event Requirement |  | Mandatory | Event Requirement |  | Mandatory
Responsibility | Case of JDM | Sony Product Design | Responsibility | Case of JDM | ソニー商品設計
| Case of ODM | Leading model : Sony Product Design Derivative model : Outsourcing Product Design |  | Case of ODM | リーデイングモデル：ソニー商品設計 派生モデル：委託先商品設計
Attendees | Case of JDM | Sony(Panel Design, Product Design, PS com. Member) | Attendees | Case of JDM | ソニー（パネル設計、商品設計、画音質委員）
| Case of ODM | Leading model : Sony(Panel Design, Product Design, PS com. Member) Derivative model : Outsourcing Product Design, Sony Product Design |  | Case of ODM | リーデイングモデル：画音質委員長もしくは副委員長 派生モデル：画音質委員
Final Approval | Case of all | PS Chairman or Vice chairman | Final Approval | Case of all | ソニー画音質委員長もしくは副委員長
Acceptation |  | #REF! | Acceptation |  | #REF!
| Criteria, Rule, etc. | To confirm the picture performance of the panel and carry out the final confirmation whether or not there is the performance that can give the saleability of the model enough. O-cell HEX data must be checked and confirmed during this meeting. |  | Criteria, Rule, etc. | パネルの画像性能を確認し、モデルの販売性を十分に満足できる性能があるかどうかの最終確認を実施する。 O-Cell HEXデータは、この会議中に必ずチェックし確認を実施
| Another Document |  |  | Another Document
Record | Record Name | Meeting Minute | Record | Record Name | Meeting Minute
| Responsibility | Sony Panel Design |  | Responsibility | パネル設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 3 years |  | Keeping Period | 3 years
[Ｆlow and Judgment method of the PS committee activity] |  |  | [PS委員会活動の流れと判断方法]
*Definition of the model |  |  | ・モデルの定義
1) Leading model : New design model |  |  | ①リーディングモデル ： 新規設計モデル
2) Derivative model : Destination difference of the leading model, a size difference, a design difference, a panel difference, etc. |  |  | ②派生モデル ： 主にリーディングモデルの仕向け違い、サイズ違い、デザイン違い、パネル違い等で
|  | Design and Committee decide it. | 対応したものであるが、その他、設計と委員会で決める。
*Ｆlow and Judgment method of the activity |  |  | ・活動の流れと判定方法
Judgment of basic PS
DVT
PVT
Judgment of panel performance
Design PS quality meeting
Shipping
Design stage
Production stage
[Leading model]
[Derivative model]
DVT
PVT
Judgment of panel performance
Design PS quality meeting
PP/MP PS quality meeting
Shipping
Judgment : PS Chairman
or Vice chairman
Judgment : (PP)Production GM
(MP)Plant QA GM
Judgment : PS Committee
Judgment : PS Committee
Judgment : (PP)Production GM
(MP)Plant QA GM
Judgment : PS Chairman
or Vice chairman
Judgment : PS Chairman
or Vice chairman
PP/MP PS quality meeting
基本画音質判定
DＶＴ
PVT
パネル性能判定
設計画音質会議
PP/MP画音質会議
出荷
設計段階
製造段階
○リーディングモデル
○派生モデル
DＶＴ
PVT
パネル性能判定
設計画音質会議
PP/MP画音質会議
出荷
判定者：委員長
もしくは副委員長
判定者：委員長
もしくは副委員長
判定者：委員長
もしくは副委員長
判定者：（PP)製造部長
(MP)品証部長
判定者：画音質委員
判定者：画音質委員
判定者：（PP)製造部長
(MP)品証部長
Event Plan. Table

## P3-35
| No. | P3-35 |  | No. | P3-35
Control Item |  | Judgment of design PS quality | Control Item |  | 基本画音質判定
Event Requirement |  |  | Event Requirement
Responsibility | Case of JDM | Sony Product Design | Responsibility | Case of JDM | ソニー商品設計
| Case of ODM | Leading model : Sony Product Design Derivative model : Outsourcing Product Design |  | Case of ODM | Leading model : Sony 商品設計 Derivative model : Outsourcing 商品設計
Attendees | Case of JDM | Sony(Device Responsible, Product Design, PS com. Member) | Attendees | Case of JDM | Sony(デバイス責任者, 商品設計, 画音質委員メンバー)
| Case of ODM | Leading model : Sony(Device Responsible, Product Design, PS com. Member) Derivative model : Outsourcing Product Design, Sony Product Design |  | Case of ODM | Leading model : Sony(デバイス責任者, 商品設計, 画音質委員メンバー) Derivative model : Outsourcing商品設計, Sony商品設計
Final Approval | Case of all | Leading model : PS(Picture/Sound) Chairman or Vice chairman Derivative model : PS committee. | Final Approval | Case of all | ソニー画音質委員長もしくは副委員長
Acceptation for ODM |  | #REF! | Acceptation for ODM |  | #REF!
| Criteria, Rule, etc. | To judge final PS quality at design stage |  | Criteria, Rule, etc. | 設計段階での最終画音質判定
| Another Document | FDR031E-04 Form_PS Quality Judgment Meeting report |  | Another Document | FDR031E-04 Form_PS Quality Judgment Meeting report
Record | Record Name | PS Quality Judgment Meeting report, Data for P/S Judgment Mtg. | Record | Record Name | PS Quality Judgment Meeting report, Data for P/S Judgment Mtg.
| Responsibility | Sony Product Design |  | Responsibility | Sony商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 3 years |  | Keeping Period | 3 years
[Ｆlow and Judgment method of the PS committee activity] |  |  | ●画音質委員会活動の流れと判定方法
*Definition of the model |  |  | ・モデルの定義
1) Leading model : New design model |  |  | ①リーディングモデル ： 新規設計モデル
2) Derivative model : Destination difference of the leading model, a size difference, a design difference, a panel difference, etc. |  |  | ②派生モデル ： 主にリーディングモデルの仕向け違い、サイズ違い、デザイン違い、パネル違い等で
|  | Design and Committee decide it. | 対応したものであるが、その他、設計と委員会で決める。
*Ｆlow and Judgment method of the activity |  |  | ・活動の流れと判定方法
Judgment of basic PS
DVT
PVT
Judgment of panel performance
Design PS quality meeting
Shipping
Design stage
Production stage
[Leading model]
[Derivative model]
DVT
PVT
Judgment of panel performance
Design PS quality meeting
PP/MP PS quality meeting
Shipping
Judgment : PS Chairman
or Vice chairman
Judgment : (PP)Production GM
(MP)Plant QA GM
Judgment : PS Committee
Judgment : PS Committee
Judgment : (PP)Production GM
(MP)Plant QA GM
Judgment : PS Chairman
or Vice chairman
Judgment : PS Chairman
or Vice chairman
PP/MP PS quality meeting
基本画音質判定
DＶＴ
PVT
パネル性能判定
設計画音質会議
PP/MP画音質会議
出荷
設計段階
製造段階
○リーディングモデル
○派生モデル
DＶＴ
PVT
パネル性能判定
設計画音質会議
PP/MP画音質会議
出荷
判定者：委員長
もしくは副委員長
判定者：委員長
もしくは副委員長
判定者：委員長
もしくは副委員長
判定者：（PP)製造部長
(MP)品証部長
判定者：画音質委員
判定者：画音質委員
判定者：（PP)製造部長
(MP)品証部長
Event Plan. Table

## P3-36
| No. | P3-36 |  | No. | P3-36
Control Item |  | Drop and vibration check | Control Item |  | 落下振動チェック
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design (Mechanical) |  | Responsibility | 商品設計（機構設計）
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | 1) No problems worse than B rank and no problems to be confirmed. 2) No need confirmation and approval of QA |  | Criteria, Rule, etc. | 1) Bランク以上及び確認の問題が無い事 2) チェックシートに品質保証部の確認/承認は不要
| Another Document |  |  | Another Document
|  | FTBR-RS-E-03 Form Drop and Vibration Standard Check Sheet |  |  | FTBR-RS-E-03 Form Drop and Vibration Standard Check Sheet
Record | Record Name | Drop & vibration standard check sheet | Record | Record Name | Drop & vibration standard check sheet
| Responsibility | Sony Mechanical Design |  | Responsibility | 機構設計担当部署
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 5 years |  | Keeping Period | 5 years
Event Plan. Table

## P3-37
| No. | P3-37 |  | No. | P3-37
Control Item |  | Remote commander check | Control Item |  | リモコンチェック
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of Product Design |  | Approval | 商品設計
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | 1) No problems worse than B rank and no problems to be confirmed. 2) No need confirmation and approval of QA. |  | Criteria, Rule, etc. | 1) Bランク以上及び確認の問題が無い事。 2) チェックシートに品質保証部の確認/承認は不要。
| Another Document |  |  | Another Document
|  | FTBR-RS-E-05 Form_Remote Commander Check sheet |  |  | FTBR-RS-E-05 Form_Remote Commander Check sheet
Record | Record Name | Remote Commander Check Sheet | Record | Record Name | Remote Commander Check Sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 5 years |  | Keeping Period | 5 years
Event Plan. Table

## P3-38
No. | P3-38 | No. | P3-38
Control Item | Serviceability check | Control Item | サービス性基準チェック
Event Requirement |  | Event Requirement
Responsibility | Product Design | Responsibility | Product Design
Approval | Responsible person of Service Promotion | Approval | サービス担当部署
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | To judge serviceability based on Serviceability check sheet | Criteria, Rule, etc. | ｻｰﾋﾞｽ性基準ﾁｪｯｸｼｰﾄに基づき、ｻｰﾋﾞｽ性の判定を行う
Another Document | FTBR-SS-E-02 Form_Serviceability Check Sheet | Another Document | FTBR-SS-E-02 Form_Serviceability Check Sheet
Record Name | Serviceability check sheet | Record Name | Serviceability check sheet
Responsibility | Service Promotion | Responsibility | サービス担当部署
Where/How to keep | e 21 | Where/How to keep | e 21
Keeping Period | 5 years | Keeping Period | 5 years
Event Plan. Table

## P3-39
| No. | P3-39 |  | No. | P3-39
Control Item |  | Parts application check | Control Item |  | 部品使用基準チェック
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | 1) No problems worse than B rank and no problems to be confirmed. 2) No need confirmation and approval of QA. |  | Criteria, Rule, etc. | 1) Bランク以上及び確認の問題が無い事。 2) チェックシートに品質保証部の確認/承認は不必要。
| Another Document |  |  | Another Document
|  | FTBR-RS-E-04 Form Parts Application Standard Check sheet |  |  | FTBR-RS-E-04 Form Parts Application Standard Check sheet
Record | Record Name | Parts application check sheet | Record | Record Name | Parts application check sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 10 years |  | Keeping Period | 10 years
Event Plan. Table

## P3-40
| No. | P3-40 |  | No. | P3-40
Control Item |  | Minimum Product Quality Rules and Requirements check (2nd) | Control Item |  | 品質ボトムチェック (2回目)
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of QA |  | Approval | 品証評価（DR ）責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | Minimum Product Quality Rules and Requirements are to be satisfied. |  | Criteria, Rule, etc. | 品質ボトム基準の要求を満たしている事。
| Another Document |  |  | Another Document
|  | FDR027E-03 Form Minimum Product Quality Rules & Requirements Check Sheet |  |  | FDR027E-03 Form Minimum Product Quality Rules & Requirements Check Sheet
Record | Record Name | Quality Bottom Check Sheet | Record | Record Name | Quality Bottom Check Sheet
| Responsibility | Sony Product design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 10 years |  | Keeping Period | 10 years
Event Plan. Table

## P3-41
| No. | P3-41 |  | No. | P3-41
Control Item |  | EMC check | Control Item |  | EMCチェック
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of QA(Safety) |  | Approval | ソニー品証責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | (EMC Measurements Conditions Confirmation) EMC fluctuation should not exist under Set Design Conditions. (EMC Measurement) Satisfy the EMC design margin standard. (Refer to TV EMC Control Rule) |  | Criteria, Rule, etc. | （EMC測定条件の確認） セットの設計条件でEMC（特にEMI）変動が無い事。 （EMC測定） EMC設計マージン規格を満たしていること。（EMCチェックシート参照）
| Another Document | FTBR-EMC-E-02 Form_EMC Special Exemption |  | Another Document | FTBR-EMC-E-02 Form_EMC Special Exemption
|  | FTBR-EMC-E-01 Form_EMC Check sheet |  |  | FTBR-EMC-E-01 Form_EMC Check sheet
|  | TBR-EMC-E_TV EMC Control Rule |  |  | TBR-EMC-E_TV EMC Control Rule
Record | Record Name | EMC Check Sheet | Record | Record Name | EMC Check Sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e21
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 生産終了後10年
Event Plan. Table

## P3-42
| No. | P3-42 |  | No. | P3-42
Control Item |  | RIPR check (2nd) | Control Item |  | RIPRチェック（２回目）
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of Product Design |  | Approval | 品証責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | *To comply RIPR 100%. *To get approval from Responsible person of Product Design before DFJ |  | Criteria, Rule, etc. | ･RIPRを100%満足すること。 ･設計検認の２週間前までにチェックシートを安心安全担当へ提出し、DFJまでに承認を得ること。
| Another Document |  |  | Another Document
|  | FTBR-RI-E-01 Form_RIPR Check Sheet |  |  | FTBR-RI-E-01 Form_RIPR Check Sheet
Record |  |  | Record
| Record Name | RIPR Check sheet. |  | Record Name | RIPR Check sheet.
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e21
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 生産終了後10年
Event Plan. Table

## P3-43
| No. | P3-43 |  | No. | P3-43
Control Item |  | DSS (Design Standard Safety) check | Control Item |  | DSS (Design Standard Safety)確認
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of Product Design |  | Approval | 商品設計
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | DSS : Design Standard (Safety Part) *To comply DSS. *No need confirmation and approval of QA. |  | Criteria, Rule, etc. | DSS : Design Standard (Safety Part) *DSSに準拠. *品質保証部の確認/承認は不要
| Another Document | 01_E_CoverSheet.doc |  | Another Document | 01_E_CoverSheet.doc
|  | 02_E_CS_Body Detail Check20110314.xls |  |  | 02_E_CS_Body Detail Check20110314.xls
|  | 03_E_DataSheet_1.2.1.xls |  |  | 03_E_DataSheet_1.2.1.xls
|  | 04_JE_DataSheet_3.15.4.xls |  |  | 04_JE_DataSheet_3.15.4.xls
|  | 05_E_Datasheet_4.3A.doc |  |  | 05_E_Datasheet_4.3A.doc
Record | Record Name | DSS Check sheet. | Record | Record Name | DSS Check sheet.
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e21 |  | Where/How to keep | e21
| Keeping Period | 5 years |  | Keeping Period | 5 years
Event Plan. Table

## P3-44
| No. | P3-44 |  | No. | P3-44
Control Item |  | TV spec. special exemption request | Control Item |  | TVスペック特別許可願い発行
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | GPS/RS: Responsible person of Product Design & Sony QA. DSP/DSR: Responsible person of Product Design. |  | Approval | GPS/RS: 商品設計 & 品証. DSP/DSR: 商品設計
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | 1)In case that GPS/ RS/ DSP/ DSR is not be satisfied, “Request for permission to deviate from Spec” is to be issued in order to produce products temporarily with the special standards. 2)No occurrence of market problems is to be judged. |  | Criteria, Rule, etc. | 1)GPS/ RS/ DSP/ DSRが基準を満足できない場合が発生した時, 暫定的に一定期間特別規格で生産するために、「Request for permission to deviate from Spec」を発行する 2)市場問題が発生しないと判断できる事
| Another Document |  |  | Another Document
|  | FDR023E-10 Form_TV Spec Special Exemption Request |  |  | FDR023E-10 Form_TV Spec Special Exemption Request
Record | Record Name | Request for Permission to Deviate from Spec. | Record | Record Name | Request for Permission to Deviate from Spec.
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 5 years |  | Keeping Period | 5 years
Event Plan. Table

## P3-45
| No. | P3-45 |  | No. | P3-45
Control Item |  | RIPR special exemption request | Control Item |  | RIPR特別許可願い発行
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of Product Design |  | Approval | 商品設計
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | 1)In case that RIPR is not be satisfied, “Request for permission to deviate from Spec” is to be issued in order to produce products temporarily with the special standards. 2)No occurrence of RI is guaranteed. |  | Criteria, Rule, etc. | 1)RIPR要求を満足できない場合が発生した時、暫定的に一定期間生産するために “Request for permission to deviate from Spec”を発行する 2)RIが発生しないと判断できること
| Another Document |  |  | Another Document
| Common Document |  |  | Common Document
| Document for Sony | FDR023E-10 Form_TV Spec Special Exemption Request |  | Document for Sony | FDR023E-10 Form_TV Spec Special Exemption Request
| Document for Outsourcing |  |  | Document for Outsourcing
| Record Name | RIPR Special Exemption |  | Record Name | RIPR Special Exemption
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 生産終了後10年
Event Plan. Table

## P3-46
メインイベント | P3-46. DR残問題報告 |  |  |  |  | Main Event | P3-46. Report of pending DR problems
目的 | DRがDFJ前に最終設計品質完成度状況を設計に報告するもの |  |  |  |  | Purpose | Before DFJ, DR is to issue final design quality report to the Design.
承認者 | 品質評価（DR）責任者 |  |  |  |  | Approval | Responsible person of QA(DR)
開催部署 | 品質評価（DR） |  |  |  |  | Responsibility | QA(DR)
参加者 | - |  |  |  |  | Atendees | -
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | DRがDFJ前に最終設計品質完成度状況を設計に報告する。 問題が残っている時点で報告する場合，残問題がなくなるまで報告を更新する。 PVT DR会議議事録においてDR残問題が残っていない場合は報告を省略できる。 | DR残問題報告書 FDR023-11 Form_DR残問題報告書 | Project |  |  |  | Before DFJ, DR is to issue final design quality report to the Design. If issue report when problems remain, update the reports until there are no problems remaining. If there are no remaining DR problems in the Meeting minutes of PVT DR, reporting can be omitted. | Remaining Problem Conf.After Final DR Meeting FDR023E-11 Form_Remaining Problem Conf.After Final DR Meeting
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | P3-32. PVT DR会議 |  |  |  |  | QA | P3-32. DR Meeting for PVT Result
文書管理 | [5 empty] | Document
記録物 |  | DR残問題報告書 |  |  |  | Record Name |  | Remaining Problem Conf.After Final DR Meeting
管理部署 |  | 品質評価(DR) |  |  |  | Responsibility |  | QA(DR)
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 12年 |  |  |  | Keeping Period |  | 12 years after On Line
Event Plan. Table

## P3-47
| No. | P3-47 |  | No. | P3-47
Control Item |  | Product standard for each model | Control Item |  | モデル別製品規格の発行
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of Product Design |  | Approval | 商品設計
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | To specify quality specifications that are unique to each model. To insert the Design appearance specifications figure. |  | Criteria, Rule, etc. | ･モデル毎の固有な品質ｽﾍﾟｯｸを規定するもの。 ・デザイン外観仕様図を載せること。
| Another Document |  |  | Another Document
|  | FDR023E-12 Form_Product Standard for Each Model |  |  | FDR023E-12 Form_Product Standard for Each Model
Record |  |  | Record
| Record Name | Product Standard for Each Model |  | Record Name | モデル別製品規格
| Responsibility | Sony Technical Information |  | Responsibility | 技術情報
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 1 year |  | Keeping Period | 1 year
Event Plan. Table

## P3-48
| No. | P3-48 |  | No. | P3-48
Control Item |  | Schedule Management of Applications for Energy Regulations | Control Item |  | Energy Regulations申請 日程管理
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of QA(Energy Saving) |  | Approval | QA責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | To check works and application schedule for each Energy saving regulation required for the model. 1) Input the expected date all necessary documents for the application to be submitted to QA. 2) Send this sheet to QA with the Energy consumption measurement data. |  | Criteria, Rule, etc. | モデルに必要な各省エネ規制の作業と適用スケジュールを確認する。 1）QAに提出する申請書に必要なすべての文書の予定日を入力 2）このシートをエネルギー消費測定データとともにQAに送信
| Another Document |  |  | Another Document
|  | FDR098E-01 Form_Schedule Management sheet of Applications for Energy Regulations |  |  | FDR098E-01 Form_Schedule Management sheet of Applications for Energy Regulations
|  | DR098E Rule of Schedule Management sheet of Applications for Energy Regulations |  |  | DR098E Rule of Schedule Management sheet of Applications for Energy Regulations
Record |  |  | Record
| Record Name | Each check sheet |  | Record Name | Each check sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 生産終了後10年
Event Plan. Table

## P3-49
| No. | P3-49 |  | No. | P3-49
Control Item |  | Product Compliance Assessment Sheet（UC） | Control Item |  | Product Compliance Assessment Sheet（UC）
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | Product Design
| Approval | Responsible person of QA(Safety) |  | Approval | 品証責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | For USA and Canada models only. Check by Product Compliance Assessment Sheet. |  | Criteria, Rule, etc. | 対象はUSA、カナダ向けモデル。 Product Compliance Assessment Sheetに従い、確認、記入する。
|  | 1. All requirements are to be OK and are to be approved by PP. 2. At the time of DFJ, make a progress report for Products Safety. 3. When the item which is not OK occur at the time of before PP, report a recovery plan to Safety. |  |  | 1.全ての要求項目がPP前までにOKになり承認されること。 2.設計検認前の時点で一度、製品安全担当に進捗報告を行なうこと。 3.PP前の時点で、OKに出来ない項目が発生した場合は、対応計画を製品安全担当に報告すること。
|  | After all items were finally OK, get final approval by Sony QA GM. Follow details on “Product Compliance Assessment Sheet” (FDR023E-21) * This is requirement from SEL Legal department. |  |  | 最終的に全ての項目がOKになった後、品証部長の最終承認を得ること。 詳細は「Product Compliance Assessment Sheet」(FDR023E-21)に従う。 *SEL Legal departmentからの要求
| Another Document |  |  | Another Document
|  | FDR023E-21 Product Compliance Assessment Sheet |  |  | FDR023E-21 Product Compliance Assessment Sheet
| Record |  |  | Record
| Record Name | Product Compliance Assessment Sheet |  | Record Name | Product Compliance Assessment Sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e21 |  | Where/How to keep | e21
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 生産終了後10年
|  | Confirmation flow |  |  | Confirmation flow
Product Compliance Assessment Sheet
Confirm/Fill in
Design
Progress report for Products Safety
(Confirmation status and Approval plan)
Conf. mtg before PP
Confirm Approval completion
Completion
OK
NG
Report Approval plan for
Products Safety
Complete confirmation of all items
Final approval by QA GM
Completion
Product Compliance Assessment Sheet
確認・記入
設計検認
製安へ進捗報告
（確認状況・承認計画）
PP前確認会議
承認完了を確認
終了
OK
NG
承認計画を
製安へ報告
全ての項目の確認が終了
品証部長最終承認
終了
Event Plan. Table

## P3-50
| No. | P3-50 |  | No. | P3-50
Control Item |  | Compliance indication check (2nd) (ICCS/S-PAS) (Before Design validation) | Control Item |  | コンプライアンス表示チェック(設計検認前）
| Event Requirement | Mandatory |  | Event Requirement | Mandatory
| Responsibility | Product Design |  | Responsibility | 商品設計
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | Product design person in charge makes the compliance check sheet of the charge model before Design validation by using ICCS/S-PAS and confirms that indication contents of PVT product are correct. |  | Criteria, Rule, etc. | 商品設計担当者は、設計検認前に、ICCS/S-PASで作成した担当モデルのコンプライアンスチェックシートを使用し、PVT品の表示内容が正しいことを確認する。 製品安全担当部署は、ICCS/S-PAS上で商品設計担当部署の確認結果を確認する。
|  | ICCS : Integrated Compliance Check System |  |  | ICCS : Integrated Compliance Check System
|  | https://www2.crossview.sony.biz/tv/compliance/index/ |  |  | https://www2.crossview.sony.biz/tv/compliance/index/
|  | S-PAS Top page |  |  | S-PAS Top page
|  | http://gcp.sony.com/sites/S-PAS/SitePages/S-PAS_Support_Site.aspx |  |  | http://gcp.sony.com/sites/S-PAS/SitePages/S-PAS_Support_Site.aspx
|  | (Important notice) If Safety and Compliance related changes are happened after 2nd ICCS/S-PAS Check, you should confirm a necessary indication requirement by using ICCS/S-PAS every time. (Example. parts change, production place change) |  |  | (Important notice) 2回目のICCS/S-PASチェック後に安規とコンプライアンスに関連する変更が発生した場合は、ICCS/S-PASを使用して毎回必要な適応要件を確認する必要があります。 （例：部品変更、生産場所変更）
| Another Document |  |  | Another Document
Record |  |  | Record
| Record Name | Compliance Check Sheet |  | Record Name | Compliance Check Sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | ICCS |  | Where/How to keep | ICCS/S-PAS
| Keeping Period | 1 years |  | Keeping Period | 1 years
Event Plan. Table

## P3-51
No. | P3-51 | No. | P3-51
Control Item | Product assessment (2nd) | Control Item | 製品ｱｾｽﾒﾝﾄ(2回目)
Event Requirement | Mandatory | Event Requirement | Mandatory
Responsibility | Product Design | Responsibility | Product Design
Attendees | Product Design, Product Environmental Dept. | Attendees | 商品設計、環境
Approval | Responsible person of Product Design | Approval | 商品設計
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | *Confirm the environmental target achieved. | Criteria, Rule, etc. | *環境目標の達成度を確認する
| If there is any unachieved item, clarify its cause and obtain approval of responsible person. Details of the assessment URL: https://sonyjpn.sharepoint.com/sites/S125-018/web/index.aspx |  | 未達成項目がある場合はその原因を明確にし、判定者の承認を得ること。 アセスメントの詳細は、環境推進部のWeb サイト https://sonyjpn.sharepoint.com/sites/S125-018/web/index.aspxを参照。
| *Responsibility of Execution : Must be model leader |  | *製品アセスメントの実行責任者は機種リーダーとする。
| *Confirmation of environmental laws and regulations conformity is mandatory. |  | *環境法規制の遵守の確認は必須
Another Document | Non. | Another Document | Non.
Record Name | Product Assessment sheet, Regulation check sheet | Record Name | Product Assessment sheet, Regulation check sheet
Responsibility | Product environmental Dept. Product Assessment sheet, Regulation check sheet | Responsibility | Product environmental Dept. Product Assessment sheet, Regulation check sheet
Where/How to keep | Assessment sheet safekeeping（Product environment control section）, Copy safekeeping（e21) | Where/How to keep | Assessment sheet safekeeping（Product environment control section）, Copy safekeeping（e21)
Keeping Period | Product Assessment sheet, Regulation check sheet : 13years | Keeping Period | Product Assessment sheet, Regulation check sheet : 13years
Event Plan. Table

## P3-52
| No. | P3-52 |  | No. | P3-52
Control Item |  | Product Safety check | Control Item |  | Product Safety check
| Event Requirement | Mandatory/Optional |  | Event Requirement | Mandatory/Optional
| Responsibility | Product Design |  | Responsibility | Product Design
| Attendees | Product Design, Safety, Mechanical Design, Panel Design, Power Supply System Design |  | Attendees | 商品設計、製品安全、メカ設計、パネル設計、電源設計
| Approval | Responsible person of Product Design |  | Approval | 商品設計
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | *Confirm that Products comply with requirement of the safety standard before DFJ by using Product Safety Inspection Check Sheet. |  | Criteria, Rule, etc. | *Product Safety Inspection Check Sheetを使用して、製品がDFJの前に安全基準の要件を満たしていることを確認する
|  | *Number of Samplings : 1 unit |  |  | *サンプル台数 : 1 unit
|  | *Check only the check items related to a design change carried out after Product safety application. |  |  | *安全規格申請後に実施した設計変更に関連する項目のみを確認 する
|  | *When a design change is carried out after Product safety application, check the check sheet by using the set including design change specifications. |  |  | *安全規格申請後に設計変更を行う場合は、設計変更仕様書を含むセットを使用してチェックシートを確認する
| Another Document | Product Safety Inspection Check Sheet (FDPE-03) |  | Another Document | Product Safety Inspection Check Sheet (FDPE-03)
| Record Name | Product Safety Inspection Check Sheet |  | Record Name | Product Safety Inspection Check Sheet
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e21 |  | Where/How to keep | e21
| Keeping Period | 5 years |  | Keeping Period | 5 years
| Product Safety Check Flow |  |  | Product Safety Check Flow
Does the design change affect Safety ?
Yes
Item which is affected
Confirm all DIB which was carried out
after Product Safety Application
Choose item which is affected by Design Change
in product safety inspection check sheet
Item which is not affected
Check with actual TV-set and
input the result in the check sheet
Input "N/A" in the check sheet
Does the design change affect Safety ?
Yes
Item which is affected
Confirm all DIB which was carried out
after Product Safety Application
Choose item which is affected by Design Change
in product safety inspection check sheet
Item which is not affected
Check with actual TV-set and
input the result in the check sheet
Input "N/A" in the check sheet
Event Plan. Table

## P3-53
メインイベント | P3-53. ソフトウェア量産リリース判定会議 |  |  |  |  | Main Event | P3-53. Software Release Judgment Meeting
目的 | ソフトウェア品質活動によって特定された品質リスクを確認し，ソフトウェアの完成度が市場問題を起こさないレベルに達しているか否かを判定する。 |  |  |  |  | Purpose | To confirm quality risks identified by software quality activities involving related stakeholders to judge whether software can be released or not.
承認者 | ソニーSW PM, ソニー HW PM，ソフトウェア品質推進者 |  |  |  |  | Approval | Sony SW PM, Sony HW PM and Software Quality Supporter
開催部署 | ソニーソフトウェア設計 |  |  |  |  | Responsibility | Sony Software Design
参加者 | SW PM, SW PL, SW TL, SWV, HW PM, HW PL, 商品企画, QA |  |  |  |  | Atendees | SW PM., SW PL, SW TL, SQA, HW PM, Product Planning, Software Quality Supporter, QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ※リリースに必要なすべての要求，品質基準を満足していること。 ・残問題がないこと（A, B=0またはVerify済み) ・すべての未解決問題が特別許可判断されていること ・すべての必須機能の実装が完了していること。 ・Static Analysisによる案件が残っていないこと ・以下の要求案件を満足していること Performance / 3rd Party Software / Software Security / Certification / Compliance (環境及びアクセシビリティ) ・市場の過去問題に対し，再発防止されていること ・Google承認が取れていること ※品質視点において十分に安定していること。 -すべての計画されたテストケースが実行された。 -すべての計画されたフィールドテストが完了した。 -パッケージ評価が完了している -SQA視点でソフトウェア全体の品質が安定している。 <SW開発が外部委託の場合> ソフトウェアの品質が量産リリースの基準を満たしていることを、委託先と事前に確認し、同意されていること。 | 議事録＆発表資料 | Project |  |  |  | * Software meets all the requirements and quality criteria for products to be released. - No remaining defects exist (A,B=0, Verified) - All the unresolved defects have been specially exempted - All the mandatory features have been implemented - No remaining issues of Static Analysis - All the requirements for the following items are satisfied Performance/3rd Party Software/ Software Security/Certification/ Compliance (Environment & Accessibility) - Prevention of the Previous Market Issues has been executed - Google has already approved * Software is sufficiently stable from the viewpoint of quality. - All the planned testcases have been executed - All the planned field tests have completed - Package Evaluation has already completed - Overall software quality is stable from SQA’s viewpoint < In case of outsourcing SW development > It is necessary to have confirmation and agreement in advance with contractor(s) that SW quality meets the criteria of SW mass-production release. | Minutes and presentation materials
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | TV SW Process Asset Library |  |  |  | Another Document |  | TV SW Process Asset Library
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
管理部署 |  | ソニーソフトウェア設計 |  |  |  | Responsibility |  | Software Design.
保管場所・方法 |  | PJ common portal |  |  |  | Where/How to keep |  | PJ common portal
保管期限 |  | 5年 |  |  |  | Keeping Period |  | 5 years.
Confimrmation items | [5 empty] | Confimrmation items
Check List | (Check Point) |  |  |  |  | Check List | (Check Point)
| Remaing Defects | [5 empty] | Remaing Defects
| New Features | [5 empty] | New Features
| Performance | [5 empty] | Performance
| Static Analysis | [5 empty] | Static Analysis
| 3rd Party Software | [5 empty] | 3rd Party Software
| Software Security | [5 empty] | Software Security
| Certification | [5 empty] | Certification
| Compliance(Environment & Accessibility) | [5 empty] | Compliance(Environment & Accessibility)
| Prevention of Sakura Market Issues | [5 empty] | Prevention of Sakura Market Issues
| Google Approval | [5 empty] | Google Approval
| Software Evaluation | [5 empty] | Software Evaluation
| Field Test | [5 empty] | Field Test
| Package Evaluation | [5 empty] | Package Evaluation
| Bug Curve | [5 empty] | Bug Curve
| Quality Analysis Results | [5 empty] | Quality Analysis Results
Event Plan. Table

## P3-54
No. | P3-54 |  | No. | P3-54
Control Item | Panel DFJ (Design Finalization Judgment) |  | Control Item | パネルDFJ (Design Finalization Judgment)
Event Requirement | Mandatory/Optional |  | Event Requirement | Mandatory/Optional
Responsibility | Panel Design |  | Responsibility | パネル設計
Attendees | Panel Design, Panel QA, Product Design, Procurement, Planning & Control, DR, Plant Panel Engineering |  | Attendees | パネル設計、パネル品質担当、商品設計、調達、商品企画、DR
| Panel Parts, Power Supply System Design, System Technology, Mechanical Design |  |  | Panel Parts, Power Supply System Design, System Technology, Mechanical Design
Approval | Senior Manager or above of panel design responsible department |  | Approval | パネル設計責任者
Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
Criteria, Rule, etc. | Item | Remark | Criteria, Rule, etc. | Item | Remark
| 1. panel mechanical confirmation meeting finished | It is OK to judge by Panel DFJ |  | 1.パネルメカ確認会議済み | Panel DFJ内での判断でOK
| 2. Optical specification fix meeting finished | It is OK to judge by Panel DFJ |  | 2.光学仕様確認会議済み | Panel DFJ内での判断でOK
| 3. O-cell / T-con confirmation are finished | It is OK to judge by Panel DFJ |  | 3.O-cell/T-con仕様確認会済み | Panel DFJ内での判断でOK
| 4. Panel DR check sheet is done |  |  | 4.パネルDRチェックシート確認済み
| 5. Specification of SET EMI is fixed |  |  | 5.SET EMI仕様確定済み
| 6. Deliberation of each quality WG are done | COF WG/GOA PJ/ prevent recurrence of previous Panel issues |  | 6.各品質WG審議済み | COF WG/GOA PJ/パネル問題再発防止list
| 7. D4Q LV1/LV2 or equivalent event is done |  |  | 7.D4Q LV1/LV2もしくはそれ同等のイベント審議済み
| 8. Champion panel judgment finished |  |  | 8.チャンピオンパネル性能判定済み
| 9. SET PVT DR (panel related) is finished |  |  | 9.セットPVT DR評価(パネル関連)済み
| 10. ES/CS Trial issue is closed | fixed with production |  | 10.ES/CS試作問題点close済み | 製造側と合意
| [Review items (DR heck sheet) below] |  |  | [Review items (DR heck sheet) below]
| *CS panel evaluation result |  |  | *CSパネル評価結果
| *Vender's reliability test result |  |  | *メーカ信頼性試験結果
| *Parts specification is fixed |  |  | *部品仕様書
| *Product specification(Draft) is fixed |  |  | *納入仕様書(ドラフト版)
| *Interchangeability confirmation |  |  | *互換性確認
| *Material about environmental |  |  | *環境関連資料
| *Panel Safety Regulations |  |  | *Panel 安全規格レポート
| *FMEA review |  |  | *FMEA review
| *Quality concept review |  |  | *品質コンセプトのレビュー
| *Schedule and number of PP and 1st MP lot |  |  | *MP 1st Lot日程と数量
Another Document | Panel Event Management Standard |  | Another Document | Panel Event Management Standard
Record Name | meeting minutes |  | Record Name | meeting minutes
Responsibility | Panel Design |  | Responsibility | パネル設計
Where/How to keep | e21 |  | Where/How to keep | e21
Keeping Period | 3 years |  | Keeping Period | 3 years
Event Plan. Table

## P3-55
| No. | P3-55 | No |  | P3-55
Control Item | (Common Event) | DFJ (Design Finalization Judgment) for Power Supply unit |  | (Common Event) | 電源DFJ (Design Finalization Judgment)
Event Requirement |  |  | 実施
Responsibility | Case that Sony designs power supply | Sony Power Supply System Design | 主催部署 | ソニーが電源設計の場合 | ソニー電源システム設計
| Case that Outsourcing of the Sony appointment designs power supply | Sony Power Supply System Design |  | ソニー指定の委託先が電源設計の場合 | ソニー電源システム設計
| Case that Outsourcing of the ODM appointment designs power supply (There is the case that Sony orders outsourcing for ODM) | Sony Product Design |  | ODM先指定の委託先が電源設計の場合 (ODM先に対してソニーが委託先を指示する場合もある） | ソニー商品設計
Attendees | Case that Sony designs power supply | Sony(Product Design, Power supply system Design, DR, Products Safety, Parts Development) | 参加 | ソニーが電源設計の場合 | ソニー（商品設計、電源システム設計、品質評価（DR）、製品安全、部品開発）
| Case that Outsourcing of the Sony appointment designs power supply | Sony(Product Design, Power supply system Design, DR, Products Safety, Parts Development) |  | ソニー指定の委託先が電源設計の場合 | ソニー（商品設計、電源システム設計、品質評価（DR）、製品安全、部品開発）
| Case that Outsourcing of the ODM appointment designs power supply (There is the case that Sony orders outsourcing for ODM) | Sony(Product Design, Power supply system Design, DR, Products Safety, Parts Development) |  | ODM先指定の委託先が電源設計の場合 (ODM先に対してソニーが委託先を指示する場合もある） | ソニー（商品設計、電源システム設計、品質評価（DR）、製品安全、部品開発）
Approval | Case that Sony designs power supply | Responsible person of Sony Power Supply System Design | 判定者 | ソニーが電源設計の場合 | ソニー電源システム設計責任者
| Case that Outsourcing of the Sony appointment designs power supply | Responsible person of Sony Power Supply System Design |  | ソニー指定の委託先が電源設計の場合 | ソニー電源システム設計責任者
| Case that Outsourcing of the ODM appointment designs power supply (There is the case that Sony orders outsourcing for ODM) | Responsible person of Sony Product Design |  | ODM先指定の委託先が電源設計の場合 (ODM先に対してソニーが委託先を指示する場合もある） | ソニー商品設計責任者
Final Approval | Case of all | Responsible person of Sony Product Design | 最終承認者 | 全ての場合 | ソニー商品設計責任者
| Criteria, Rule, etc. | 1. Evaluation check sheet is to have been submitted and approved. 2. No manufacturing problem 3. No DR problem 4. No RIPR problem 5. All the past problem has been taken action |  | 判断基準・実施内容 | １．評価チェックシートが提出され承認済みであること。２．製造問題点無し。３．DR問題点無し。４．RIPR問題点無し。５．過去問題の対応全て対応済み。
Another Document | Common Document | Non | 別途文書 | 共通文書 | 無し
| Document for Sony | Non |  | ソニー向け文書 | 無し
| Document for Outsourcing | Non |  | 委託先向け文書 | 無し
| Record Name | Minutes of Power supply Confirmation Meeting |  | 記録文書 | Minutes of Power supply Confirmation Meeting
| Responsibility | Sony Power Supply Group |  | 保管部署 | Sony Power Supply Group
| Where/How to keep | e 21 |  | 保管方法 | e21
| Keeping Period | 3 years after O/L |  | 保管期限 | O/L後 3年
Event Plan. Table

## P3-56
メインイベント | P3-56. ローカライゼーションプロセス |  |  |  |  | Main Event | P3-56. Localization Process
目的 | 販社や倉庫で実施するローカライゼーションによるコンプライアンス問題の発生を防止する |  |  |  |  | Purpose | Prevent any compliance issue caused by localization at Sales Co. or W/H
承認者 | 品質保証部長 ＆ 該当エリアのRQM |  |  |  |  | Approval | QA General manager & RQM in each area
開催部署 | 設計部署起票 |  |  |  |  | Responsibility | Design section
参加者 | - |  |  |  |  | Atendees | -
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | SHES TV製品コンプライアンスローカライゼーションルールに則り，"SHES TV Localization Instruction"が発行されていること | SHES TV Localization Instruction | Project |  |  |  | "SHES TV Localization Instruction" has been issued in accordance with SHES TV product compliance localization rules. | SHES TV Localization Instruction
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Panel | [5 empty] | Panel
品証 | [5 empty] | QA
別途文書 |  | 製品コンプライアンス ローカライゼーション ルール |  |  |  | Another Document |  | Product Compliance Localization Rule
文書管理 | [5 empty] | Document
記録物 |  | SHES TV Localization Instruction |  |  |  | Record Name |  | SHES TV Localization Instruction
管理部署 |  | 品質保証部 |  |  |  | Responsibility |  | QCS TVQA
保管場所・方法 |  | TV Quality & CSDiv. webpage |  |  |  | Where/How to keep |  | TV Quality & CSDiv. webpage
保管期限 |  | 10年 |  |  |  | Keeping Period |  | 10 years
Event Plan. Table

## P3-57
| No. | P3-57 |  | No. | P3-57
Control Item | (Common Event) | Chinese company standard application / registration | Control Item | (Common Event) | 中国企業標準申請/登録
| Event Requirement |  |  | Event Requirement
| Responsibility | Product Design |  | Responsibility | 商品設計
| Approval | Responsible person of Product Design |  | Approval | 商品設計責任者
| Acceptation for ODM | #REF! |  | Acceptation for ODM | #REF!
| Criteria, Rule, etc. | For model which have been produced and sold in China. Comply with the common Chinese company action standardDS023002. |  | Criteria, Rule, etc. | 中国で生産・販売されているモデルが対象 共通中国企業標準対応標準（DS023002）に従い中国企業標準申請、登録を行なう
| Another Document |  |  | Another Document
|  | DR094E Common / Standard to support China Company Rule |  |  | DR094E Common / Standard to support China Company Rule
| Record |  |  | Record
| Record Name | Original copy of registered Chinese company standard |  | Record Name | 中国企業標準登録済み原本コピー
| Responsibility | Sony Product Design |  | Responsibility | 商品設計
| Where/How to keep | e 21 |  | Where/How to keep | e 21
| Keeping Period | 10 years after production discontinuation. |  | Keeping Period | 10 years after production discontinuation.
Event Plan. Table

## P3-80
メインイベント | P3-80. 設計完了判定 (DFJ) |  |  |  |  | Main Event | P3-80. Design Finalization Judgment (DFJ)
目的 | セット設計が完了していることを判定する |  |  |  |  | Purpose | To validate set design.
承認者 | 設計責任者/品質責任者 |  |  |  |  | Approval | Responsible person of Product Design and responsible person of QA
開催部署 | 商品設計部門/開発設計部門 |  |  |  |  | Responsibility | Development Design/Product Design
参加者 | 商品設計部門/開発設計部門/企画・MK部門/SW設計部門/調達部/品証・CS部門/事業所 |  |  |  |  | Atendees | Product Design/Development Design/SVP-M/Product Planning/ Business Planning/ SW Design/Procurement/QA/Office
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | チェックリスト |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  | 設計検認会議資料 | 1. 全ての設計問題が解決済み。（A=0、B=0）（DR残問題報告書が承認済み。） 2. PVT以降、設計変更があった場合は、全ての設計変更項目に関して次の項目を確認し内容を審議する。 ただし、DRと共同評価し検証した項目は除くことも可能。 1) 副作用検証の要否が正しく判断されていること。 2) 副作用検証が必要な設計変更に関しては正しく副作用が検証されていること。 3) 最終的に設計変更導入可否が正しく判断されていること。 （PVT後設計変更項目と副作用検証結果が記入されたリストを資料として添付すること。） 3. BOMリリース以降、回路変更があった場合は、変更部品、及び影響を受ける部品に対する部品使用基準ﾁｪｯｸが行なわれ、ﾁｪｯｸｼｰﾄが承認済み。 4. 画音質判定が合格済み。 5. SW RJM 判定済み、もしくは計画が立っていること 6. パネルDFJが合格済み。 7. 電源／確認会議が合格済み。 8. 品質構想の進捗確認終了。 9. 接続構想に準じた評価が完了。また、ロゴ認証が承認済み。（ロゴ認証未承認の場合はPP前までに所得の計画有り。） 10. 安全規格、省エネ規格は、原則として、PP前までに取得の計画有り。 11. 製品アセスメントで遵法項目がOKである。それ以外の項目は出荷前までに確認できる計画有り。 12. 設計ｱｳﾄﾌﾟｯﾄ(出図等)の見通しあり、ﾓﾃﾞﾙ別製品規格が承認済み。 13. RIPR、DSS、製品安全性検査、落下振動、リモートコマンダー（All：新規/流用（最新のチェックシートを使用））、サービス性基準、部品使用基準、SAPAPS実施報告書、CIT JIRA、コンプライアンス問題チェックのチェックシートが承認済み。 14. 品質ボトムチェックシートと要件チェックシートが承認済み。 15. EMCチェックシートの内容を審議する。 16. TV SPEC、画音質及びRIPR特別許可は、e-21及びS-Cabinet（必要に応じて）を通じてFDR023-10 Form_TVスペック特別許可願いを使用して、関係部門と発行、承認及び共有済み。 17. 法規制消費電力チェックシートを提出すること。 （対象機種のみ） 18. 中国で生産され、且つ販売されるモデルは、中国企業標準が出荷判定までに承認の計画有り。 （ODM/OEMモデルは、原則として、PPの一か月前までに承認の計画有り。） 19. USA、カナダ向けモデルは"Product Compliance Assessment Sheet"がPP前までに承認される計画があること。 20. ICCS/S-PASによるコンプライアンス表示確認が完了完了済みか、期限前に完了する計画有り。 21. 暗号キー長の選択とアルゴリズムが確実に実行されることの最終確認。 （ソニーSS STM-160に従う） 22. 販売会社が管理する取扱説明書の準備が完了済み。 25. 未承認の新規導入部品（末尾変更含む）がないこと。 または量産開始までに承認される計画がたっていること 注）問題が発生して次のイベントに進む場合は、ビジネス責任者の特別承認を得て、議事録に内容を記載すること （例：B問題が残っていても、PPのチップマウント開始 ） （派生モデルについては、該当する項目のみ判定基準を適用） 26. コンプライアンスマスターリストのアイテムが完了していること、もしくは量産前までに完了の計画あり 27.ローカライゼーションリワーク対象案件について、内容と対象モデルの確認ができていること 28. 製品、展示会などの体験提供の場で、リスク低減策が実施されている事 | 設計検認会議議事録 発表資料（チェックシート含） | Project |  |  | DV material | 1. All design problems are resolved. (A = 0, B = 0) (DR remaining problem report has been approved.) 2. If there is a design change after PVT, check the following items regarding all design change items and deliberate the contents. However, items co-evaluated with DR and verified can also be excluded. 1) The necessity of side effect verification is correctly judged. 2) Side effects are correctly verified with respect to design changes requiring side effect verification. 3) Ultimately the propriety of design change introduction is correctly judged. (Attach the list in which the post-PVT design change items and side effect verification results are attached as materials.) 3. After the BOM release, if there is a circuit change, parts check criteria are checked for changed parts and affected parts and the check sheet has been approved. 4. Image quality judgment passed. 5. RJM judgment completed or SW release planned 6. Panel DFJ passed. 7. Power supply / confirmation meeting passed. 8. Confirm progress of quality plan. (Confirmation by Risk Management Chart) 9. Evaluation based on the connection concept completed. Also, logo certification has been approved. (In case of unauthorized logo authentication, there is a plan of income before PP.) 10. As a rule, safety standards and energy saving standards are planned to be acquired before PP. 11. Compliance items are OK in product assessment. Other items are planned to be confirmed before shipment. 12. There is a prospect of design output (drawing etc), product specification by model has been approved. 13. Check for RIPR, DSS, product safety inspection, fall vibration, remote commander (All: new / diversion (using latest check sheet)), service quality standard, parts usage standard, SAPAPS implementation report, compliance problem check Sheet approved. 14. Quality bottom check sheet and requirement check sheet approved. 15. Discuss the contents of the EMC check sheet. 16. TV SPEC, image quality and RIPR special permission issued, approved and shared with relevant departments using FDR 02 - 10 Form_TV spec special permission request through e - 21 and S - Cabinet (if necessary). 17. Submit legally regulated power consumption check sheet. (Applicable models only) 18. The model manufactured and sold in China is planned to approve by the Chinese enterprise standard by shipping decision. (In principle, the ODM / OEM model has approval plans one month before PP.) 19. The model for USA, Canada has a plan that "Product Compliance Assessment Sheet" will be approved before PP. 20. Compliance confirmation by ICCS/S-PAS There is a plan that completion of confirmation has been completed or planned to be completed before the deadline. 21. Final confirmation of selection of cryptographic key length and ensured execution of algorithm. (Follow Sony SS STM-160) 22. The preparation of the instruction manual managed by the distributor is completed. 25. There are no unapproved newly introduced parts (including end change). Or that plans are approved before the start of mass production Note) If a problem occurs and proceed to the next event, obtain the special approval from the business manager and describe the contents in the minutes (eg, even if the problem B remains, PP chip mount starts) (For derivative models, only the applicable items apply judgment criteria) 26. Compliance Master List items have been completed or planned to be completed by mass production 27.Confirmation of content and target model for localization rework target Items 28. Risk reduction measures are implemented at places where products, exhibitions, and other experiences are provided. | Minutes of design finalization judgment Presentation materials (including check sheet)
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development Desiｇｎ
商品設計 | P2-5. Patent確認：新規案件追加の有無確認 (コンプライアンスマスターリスト確認) P3-15. Key Device MP判定 P3-20. 人体影響リスク低減策実施 P3-22. BOM.R前確認会議 P3-23. BOM.R P3-24. Model R P3-25. サービス区分会議 P3-26. Field Test P3-27. PVT P3-28. DCE申請前確認 P3-29. 安規申請前確認会議 P3-30. SAPAPS（PVTステージ）レポート/CIT(OoBE対象モデル以外） P3-34. Champion Panel 判定 P3-35. 設計画音質判定 P3-44. TVスペック特別許可願い発行 P3-45. RIPR特別許可願い発行 P3-47. モデル別規格発行 P3-55. 電源DFJ（量産基板出図） P3-57. 中国企業標準承認の計画確認 -基板（量産基板出図） P2-8. 輝度スペック最終確認（シリーズ間、年度間整合） P3-56. ローカライゼーションリワークプロセス |  | P2-5. コンプライアンスマスターリスト P3-36. 落下振動チェック P3-37. リモコンチェック P3-38. サービス性基準チェック P3-39. 部品使用基準チェック P3-40. 品質ボトムチェック 2nd P3-41. EMCチェック P3-42. RIPRチェック 2nd P3-43. DSS (Design Standard Safety) チェック P3-48. 法規制消費電力チェック P3-49. Product Compliance Assessment Sheet（UC）済 P3-50. ICCS/S-PASチェック (2nd) (Before DFJ) P3-51. 製品ｱｾｽﾒﾝﾄチェック 2nd P3-52. 製品安全チェック P3-55. 電源チェック P3-19. 再発防止チェックシート P3-20. 人体影響の判定・記録シート |  |  | Product Design | P2-5. Patent confirmation:Confirming the existence of new project addition(Compliance master list confirmed) P3-15. Judgment for Key Device MP P3-20. Taking risk reduction measures P3-22. Confirmation Meeting before BOM Release P3-23. BOM Release P3-24. Official Model Release P3-25. Service classification meeting P3-26. Field test P3-27. PVT P3-28. Confirmation before DCE Application P3-29. Confirmation Meeting before Product Safety Application P3-30. SAPAPS at PVT stage P3-34. Judgment of champion panel performance P3-35. Judgment of design PS quality P3-44. TV spec. special exemption request P3-45. RIPR special exemption request P3-47. Product standard for each model P3-55. Power supply DFJ (PP/MP CAD OUT) P3-57. Confirming the Chinese enterprise standard approval plan - Board (PP/MP CAD OUT) P2-8. Finally Confirm the consistency of luminance specifications inbetween series and previous models on the list. P3-56. Localization rework porcess |  | P2-5. Compliance master list P3-36. Drop and vibration check P3-37. Remote commander check P3-38. Serviceability check P3-39. Parts application check P3-40. Minimum Product Quality Rules and Requirements check (2nd) P3-41. EMC check P3-42. RIPR check (2nd) P3-43. DSS (Design Standard Safety) check P3-48. Schedule Management of Applications for Energy Regulations P3-49. Product Compliance Assessment Sheet（UC） P3-50. Compliance indication check (2nd) (ICCS/S-PAS) (Before Design validation) P3-51. Product assessment (2nd) P3-52. Product Safety check P3-55. Confirmation for Power supply and Inverter P3-19. Recurrence prevention check sheet P3-20. Adverse Health Effects Check and Recording Sheet
SW | P3-53. ソフトウェア量産リリース判定 |  |  |  |  | SW | P3-53. Software Release Judgment
Panel | P3-54. Panel DFJ |  |  |  |  | Panel | P3-54. Panel DV(Design Validation) meeting
品証 | P3-33. DR会議 for PVT P3-46. DR残問題確認 |  |  |  |  | QA | P3-32. DR meeting for PVT result P3-46. Confirmation of pending DR problems
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
登録責任者 |  | 商品設計 |  |  |  | Responsibility |  | Product Design
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 3年 |  |  |  | Keeping Period |  | 3 years after On Line
Confirmation items
| Objective |  | *Judgment for closing design activities and go to mass production
| Definition of Design validation in the project | Scope | *Confirmation for end of products design without any problem
|  | Precondition | 1. Design validation is to have been solved=No pending design problems（A=0、B=0) (DR remaining problem report shall be approved.)
2. When there are some design changes after PVT, deliberate the following items about all design change items. But the items which were evaluated and verified with DR can be excepted.
1) Necessity or not of side effect verification shall be judged definitely. 2) About the design change that side effect verification needs, the side effect shall be verified definitely.
3) The introduction of design change shall be finally judged definitely. The list which design change items after PVT and side effect verification results shall be attached as a material.
3. If there was circuit change after BOM Release, Parts Application Standard Check has been conducted for parts which was affected and check sheet has been approved.
4. P/S Judgment meeting shall be passed and its report shall be approved.
5. Software mass production conf. meeting shall be passed.
6. Panel DV meeting shall be passed.
7. Power supply/inverter confirmation meeting is to be have passed.
8. Progress of Quality Concept is finished (Confirmation of Risk Management Chart)
9. Evaluation comply with Connectivity Conception is to have been completed.
Logo certification is to have been finished. In the case of non-certification, there is a plan becoming finished with the certification by PP.
10. Safety and Environmental approval shall be completed by Sony QA and/or product design until before PP confirmation MTG
11. The lawful items of Product assessment is to be OK. As for the items except the lawful items, there are some prospects that judgment will have been completed by shipment.
12. Design Drawings are to be released or ready to be released and Product Standard for each model is to have been issued.
13. Check sheet of RIPR, DSS, Product Safety Inspection Check Sheet, Drop-Vibration, Remote Commander (All: New/Diverted, (Use the latest check sheet)), Serviceability, Parts application, SAPAPS Implementation Report and Compliance Issues Prevention Check shall be approved.
14. Minimum Product Quality Rules and Requirements check sheet shall be approved.
15. Deliberately confirm the Result of the EMC Check Sheet.
16. TV SPEC Deviation Request, P/S and RIPR Special Exemption are to have been issued and approved. (If necessary).
17. Law Regulation power consumption sheet shall be submitted. (Only for applicable model.)
18. The model which have been produced and sold in China has a plan of the Chinese company standard approval by the product release meeting. (Basically ODM/OEM model has a plan of approval by one month before PP.)
19. “Product Compliance Assessment Sheet” approval schedule shall be a plan to be approved by PP. (For USA, and Canada models only)
20. Compliance indication check by ICCS/S-PAS was completed or is planned to complete before each due date.
21. Final confirmation of the choice of the cryptographic key length and the algorithm being performed definitely. (Follow Sony SS STM-160)
22. Preparations of Instruction Manual managed by Sales Company were completed. ( For Europe models only)
23. Blank
24. Complete the Accessibility for hardware part.
25. Is there any newly introducing parts (including suffix change) which has NOT been approved. (Yes or No)
Note) If you go to next event with problem, you must get Special Approval by Business Responsible Person and write the contents on Minutes. （For example : Chip mount for PP will be started, even if B problem is remaining. )
(For derivative model, judgment criteria will be applied to only for applicable item)
|  | Schedule | *Detail schedule until shipping
|  | Organization/System | *reconfirmation for organization/system of MP introduction
| Progress of the project that should be confirmed in Design validation | Electrical Design | *Design completed and no remaining problem
|  | SW Design | *confirmation for MP introduction plan
|  | Panel Design | *Confirmation of result of Panel DFJ
*MP panel supply schedule check
|  | Mechanical Design | *confirmation for design close and MP parts supply schedule
|  | Power Supply and Inverter Design | *Confirm PS DFJ result
*Confirm MP PS supply schedule
|  | New Parts | *confirmation for design completion and introduction Schedule
|  | Key Device | *confirmation for design completion and introduction Schedule
|  | Tuner | *confirmation for design completion and introduction Schedule
|  | Picture Quality Sound Quality | *Final P/S Quality confirmed
|  | Compliance: - Safety standard - Broadcast - Features (eg: Dolby,etc) | * Confirm application approval schedule before PP
|  | Export Control “Export Control Questionnaire”& ”Export Approval Notice” | Final confirmation of "Export Control Questionnaire" updated if the latest answers to the Questionnaire need to be modified due to any design changes, and "Export Approval Notice" issued by HES Compliance Sec.,
|  | PWB | *confirmation for design completed and introduction Schedule
|  | EMC | *confirmation for EMC data including dispersion
|  | Adjustment, JIG | *confirmation of the way handling with plant
|  | WWOPS | *confirmation of WWOPS preparation
|  | Spec-Chart | *confirmation that data was sent to Palette
| Issue |  | *no remaining design issue
*issue for production and countermeasure are clear
| Risk | Risk Management | *close Risk Management Chart
*Final confirmation of the cryptographic key length and the algorithm
| Guideline of confirmation items | Line Up | *confirmation for changing point
|  | Benchmark of Competitor's model | *reconfirmation of the latest information
|  | Market situation | *reconfirmation of the latest information
|  | Quality Target | *Closing of Quality Concept and confirm the result at DV timing
|  | Parts count/variety | *confirm completion level
|  | Cost/MP | *confirm completion level
|  | SST | *confirm completion level
|  | Number of production plan and allocation | *confirm final production plan
|  | Parts order situation | *confirm parts order situation
|  | factory | *confirmation of actual introduction plan
Sample - Format of "Preparations of Instruction Manual managed by Sales Company"
Event Plan. Table

## P4-80
メインイベント | P4-80. PP量産判定 (MPJ) |  |  |  |  | Main Event | P4-80. Mass Production Judgment (MPJ) for PP
目的 | 下記のPPオンライン判定確認シートにもとづき、PP実行可否を判断する会議 （確認項目は最低限必要な要求項目を記載している。） |  |  |  |  | Purpose | This meeting judge whether PP can be started based on the following PP On-line judgment check list in PQMR Appendix 2. (These confirmation items are minimum requirement items.)
承認者 | 製造担当責任者もしくは製造技術担当責任者 |  |  |  |  | Approval | Responsible person of Plant Production or Plant Production Eng.
開催部署 | 事業所製技 |  |  |  |  | Responsibility | Plant Production Eng.
参加者 | 商品設計、品質評価（DR）、事業所品証、事業所製技、事業所製造、事業所サービス推進 |  |  |  |  | Atendees | Product Design, DR, Plant QA, Plant Production Eng, Plant Production, Plant Service Promotion
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・PPオンライン判定確認シートで不合格項目無きこと。 ・部品の環境対応確認報告書が作成され，製品環境管理責任者の承認が得られていること。 ・PP評価計画（評価・試験項目、日程、台数）が確定していること。 ・設計構想でウイルス混入の可能性があると判断された機種の場合は、製造プロセスにおいてウイルス混入対策が完了していることを確認する。 ・判定者の判断により、不合格項目とオンライン前確認会議または出荷判定会議までに満たすべき条件を書面に残した上で、「条件付合格」を可とする。 ・承認前（未承認）の部品をやむを得ず使用する場合は、該当部品が承認されるまで出荷しないことを条件とする。 ・IRPの準備状況をサービス区分会議での決定事項を基にレビューし、未対応事項があれば出荷判定会議までに対応を完了すること。 | 議事録＆発表資料 | Project |  |  |  | * There should not be any fail item on PP On-line judgment check list. * Verification Report for Environmental Compliance of parts shall be prepared and approval of Product Environmental Quality Manager shall be obtained. * The Quality Evaluation Plan (evaluation/test items, schedule and sample quantity) shall have been fixed. * In the case of the model judged that have possibility to be infected by the virus, at the time of the design concept, confirm that virus infection measures are completed in the production process. * “Go with condition” is acceptable at the discretion of a judging person if there are clear written conditions and schedule to be implemented before confirmation meeting before on-line or product release meeting. * If unacceptable parts that are not approved are forced to use, products shall not be shipped until applicable parts are approved. * Review preparation of IRP based on decision items at Service Classification Meeting and if there are items which have not been completed, action shall be completed by Product Release Meeting. | Minutes and presentation materials
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | P3-80. 設計完了判定 |  |  |  |  | Product Design | P3-80. DFJ (Design Finalization Judgment)
SW | [5 empty] | SW
Plant |  |  | PPオンライン判定確認シート |  |  | Plant |  |  | PP On-line judgment check list
品証 | [5 empty] | Plant QA
別途文書 |  | Production Quality Management Rules (PQMR) |  |  |  | Another Document |  | Production Quality Management Rules (PQMR)
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
管理部署 |  | 事業所製技 |  |  |  | Responsibility |  | Plant Production Eng.
保管場所・方法 |  | 規定せず |  |  |  | Where/How to keep |  | Not specified.
保管期限 |  | 10年 |  |  |  | Keeping Period |  | 10 years.
| *確認項目 | [5 empty] | *Confirmation items
Event Plan. Table

## P5-1
メインイベント | P5-1. PP画音質判定会議 |  |  |  |  | Main Event | P5-1. Judgment meeting for Picture/Sound performance at PP stage
目的 | PP品が設計チャンピオンと同等であることを判定する |  |  |  |  | Purpose | PP product is judged an equal thing with a design champion
承認者 | 製造担当責任者もしくは製造技術担当責任者 |  |  |  |  | Approval | Responsible person of Plant Production or Plant Production Eng.
開催部署 | 事業所製技 |  |  |  |  | Responsibility | Plant Production Eng.
参加者 | 商品設計、品質評価（DR）、事業所品証、事業所製技、事業所製造、事業所サービス推進 |  |  |  |  | Atendees | Product Design, PS Com member, Plant Production Eng, Plant Production, Plant QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 以下の実施方法のどちらかでPP品が設計チャンピオンと同等と判定されること。 | 画音質判定会議報告書、 測定データ結果 | Project |  |  |  | By either following method, PP product is judged an equal thing with a design champion. | PS Quality Judgment Meeting report, Data for P/S Judgment Mtg.
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Plant |  |  | 画質測定データ 音質測定データ |  |  | Plant |  |  | Picture measurement data Sound measurement data
事業所品証 | [5 empty] | Plant QA
別途文書 |  | FDR031-04 Form_画音質判定会議報告書 |  |  |  | Another Document |  | FDR031E-04 Form_PS Quality Judgment Meeting report
文書管理 | [5 empty] | Document
記録物 |  | 画音質判定会議報告書、 測定データ結果 |  |  |  | Record Name |  | PS Quality Judgment Meeting report, Data for P/S Judgment Mtg.
管理部署 |  | 事業所製技 |  |  |  | Responsibility |  | Plant Production Eng
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 3年 |  |  |  | Keeping Period |  | 3 years.
| 以下の実施方法のどちらかでPP品が設計チャンピオンと同等であることを判定する | [5 empty] | By either following method, PP product is judged an equal thing with a design champion.
| ① 設計画音質チャンピオンセットがある場合 | [5 empty] | 1 - When there is a design PS quality champion set.
| N=2以上のPP品画音質を設計画音質チャンピオンセットと比較評価を実施し、 | [5 empty] | To evaluate PS quality of PP product more than N=2 in comparison with the design PS quality champion set.
| 設計画音質チャンピオンセットと同等と判断されること。 | [5 empty] | It being judged to be equal with a design PS quality champion set.
| ② 設計画音質チャンピオンセットが無い場合 | [5 empty] | 2 - When there is not a design PS quality champion set.
| 1) 画質判定 | [5 empty] | 1) Picture quality judgment
| N=2以上のPPサンプルで以下の項目に関して測定を実施し、設計部より提示されている | [5 empty] | To perform the measurement with PP samples more than N=2 about the following items and confirm a certain thing in specifications in comparison with the picture quality champion data shown from design department.
画質チャンピオンデータと比較して規格内である事を確認する。
| ・ マクベスカラー測定 | [5 empty] | * Macbeth color measurement
| ・ ガンマデータ測定 | [5 empty] | * Gamma data measurement
| ・ 色度リニアリティデータ測定 | [5 empty] | * Chromaticity Linearity data measurement
| また、実施時には測定したN=2以上のPPサンプルを並べて画質確認し差分がない事を確認する。 | [5 empty] | To display PP samples more than measured N=2 and confirm a picture quality and confirm that there is not for difference.
| （差分がある場合には、測定データが規格内である事でOK判断を実施する） | [5 empty] | (When there is a difference, to confirm that there are measurement data in specifications and judge OK.)
| 2) 音質判定 | [5 empty] | 2) Sound quality judgment
| N=2以上のPPサンプルで設計部より支給された代表モデル（リファレンスモデル）との比較を実施し、同等である事を確認する。 | [5 empty] | To compare a representative model (a reference model) provided from design department with PP samples more than N=2 and confirm that these are equal.
| また、同時に以下のデータを測定し、規格内である事を確認する。 | [5 empty] | To measure the following data at the same time and confirm a certain thing in specifications.
| ・ 電気的測定 | [5 empty] | * Electric measurement
Event Plan. Table

## P5-2
メインイベント | P5-2. コンプライアンス表示チェック (最終) (ICCS/S-PAS) |  |  |  |  | Main Event | P5-2. Compliance indication check (final) (ICCS/S-PAS)
目的 | PP量産品の表示内容が正しいことを確認する |  |  |  |  | Purpose | Confirm that indication contents of PP product are correct.
承認者 | 事業所品証責任者 |  |  |  |  | Approval | Responsible person of Plant QA
開催部署 | 事業所品証 |  |  |  |  | Responsibility | Plant QA
参加者 | - |  |  |  |  | Atendees | -
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 事業所製品安全担当者による、MP前確認会議前に、ICCSで作成した担当モデルのコンプライアンスチェックシートを使用した、PP量産品の表示内容が正しいことの確認が完了すること。 ICCS : Integrated Compliance Check System https://www2.crossview.sony.biz/tv/compliance/index/ （重要なお知らせ） ICCSの最終チェック後に安全とコンプライアンスに関連する変更が発生した場合は、ICCSを使用して毎回必要な適応要件を確認する必要があります。 （例：部品の変更、生産場所の変更） | コンプライアンスチェックシート | Project |  |  |  | Plant Products Safety person in charge uses the compliance check sheet of the charge model made in ICCS before "Confirmation Meeting before MP" and complete confirmation that indication contents of PP product are correct. ICCS : Integrated Compliance Check System https://www2.crossview.sony.biz/tv/compliance/index/ (Important notice) If Safety and Compliance related changes are happened after Final ICCS Check, you should confirm a necessary indication requirement by using ICCS every time. (Example. parts change, production place change) | Compliance Check Sheet
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Plant | [5 empty] | Plant
品証 | [5 empty] | Plant QA
別途文書 | [5 empty] | Another Document
文書管理 | [5 empty] | Document
記録物 |  | コンプライアンスチェックシート |  |  |  | Record Name |  | Compliance Check Sheet
管理部署 |  | 事業所品証 |  |  |  | Responsibility |  | Plant Product Safety
保管場所・方法 |  | ICCS |  |  |  | Where/How to keep |  | ICCS
保管期限 |  | 7年 |  |  |  | Keeping Period |  | 7 years
Event Plan. Table

## P5-3
メインイベント | P5-3. 量産先行(PP)評価 |  |  |  |  | Main Event | P5-3. PP Evaluation
目的 | 事業所品質保証担当部署は、新機種導入時に、共通_製造PQMR規定の5-6項（「ロット判定」）に定める抜き取り検査（一般検査）、及び内部点検に加え、表１に基づく評価・試験を行い、量産品の品質が高いレベルで均一に維持されている事を確認する。 |  |  |  |  | Purpose | Plant QA shall conduct PP evaluations and tests based on Table 1 at the timing of new model introduction, in addition to the Sampling Inspection (General Inspection) and Internal Inspection specified in Item 5-6 （Lot Judgment）of the Common Production PQMR, and confirm that quality of products is kept in high level uniformly.
承認者 | 事業所品証責任者 |  |  |  |  | Approval | Responsible person of Plant QA
開催部署 | 事業所品証 |  |  |  |  | Responsibility | Plant QA
参加者 | - |  |  |  |  | Atendees | -
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | IMET以外は原則MP前確認会議までに完了すること。 | 評価結果 | Project |  |  |  | All the Evaluations except for IMET shall be completed Confirmation Meeting Before On-Line in principle. | Evaluation Result
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Plant | [5 empty] | Plant
品証 | [5 empty] | Plant QA
別途文書 |  | TBR-GPS 一般製品規格 |  |  |  | Another Document |  | TBR-GPS-E General Product Standard
|  | TBR-RS 信頼性基準 | [5 empty] | TBR-RS-E Reliability Standard
|  | TBR-DSP 設計基準（製品規格編） | [5 empty] | TBR-DSP-E Design Standard (Product Standard Part)
|  | TBR-RI 品質事故防止基準（RIPR） | [5 empty] | TBR-RI-E RIPR (Reliability Incident Preventive Rule)
|  | DR096E Production Quality Management Rule | [5 empty] | DR096E Production Quality Management Rule
文書管理 | [5 empty] | Document
記録物 |  | 規定せず |  |  |  | Record Name |  | Not specified
管理部署 |  | 事業所品証 |  |  |  | Responsibility |  | Plant QA
保管場所・方法 |  | 規定せず（出荷判定会議議事録に準ずる） |  |  |  | Where/How to keep |  | Plant QA（Pursuant to Common Product Release Meeting Operation Standard）
保管期限 |  | 10年（但し出荷判定会議の資料として） |  |  |  | Keeping Period |  | 10 years （as a record of Product Release Meeting ）
Event Plan. Table

## P5-50
メインイベント | P5-50. MP量産開定 (MPJ) |  |  |  |  | Main Event | P5-50. Mass Production Judgment (MPJ) for MP
目的 | 下記のPPオンライン判定確認シートにもとづき、MP実行可否を判断する会議 （確認項目は最低限必要な要求項目を記載している。） |  |  |  |  | Purpose | This meeting judge whether MP can be started based on the following MP On-line judgment check list in PQMR Appendix 2. (These confirmation items are minimum requirement items.)
承認者 | 製造担当責任者もしくは製造技術担当責任者 |  |  |  |  | Approval | Responsible person of Plant Production or Plant Production Eng.
開催部署 | 事業所製技 |  |  |  |  | Responsibility | Plant Production Eng.
参加者 | 商品設計, 品質評価(DR), 事業所品証, 事業所製技, 事業所製造, 事業所管理, 事業所調達, DCE |  |  |  |  | Atendees | Product Design, DR, Plant QA, Plant Production Eng, Plant Production, Plant Production Control, Plant Procurement, DCE.
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | ・MPオンライン判定確認シートで不合格項目無きこと。 ・設計構想でウイルス混入の可能性があると判断された機種の場合は、製造プロセスにおいてウイルス混入対策が完了していることを確認する。 ・判定者の判断により、不合格項目と出荷判定会議までに満たすべき条件を書面に残した上で、「条件付合格」を可とする。 ・"Safety Approval Worksheet /Confirm that the check sheet (Recordkeeping) of Accessibility"の完了が確認・承認され，SELのUC-COM Serverにアップロードされていること。 | 議事録＆発表資料 | Project |  |  |  | * There should not be any fail item on MP On-line judgment check list. *In the case of the model judged that the virus infection was possible at the time of the design concept, confirm that virus infection measures are completed in the production process. * “Conditional acceptance” is accepted at the discretion of a judging person if failure items and written conditions which clarify the items to be implemented for failure items are provided before product release meeting. *"Safety Approval Worksheet /Confirm that the check sheet (Recordkeeping) of Accessibility has completed with approval and confirm that the check sheet has uploaded on the UC-COM Server in SEL. | Minutes and presentation materials
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Plant | P5-1. PP画音質判定会議 |  | MPオンライン判定確認シート |  |  | Plant | P5-1. Judgment meeting for Picture/Sound performance at PP stage |  | MP On-line judgment check list
品証 | P5-2. コンプライアンス表示チェック (最終) (S-PAS/ICCS) P5-3. 量産先行(PP)評価 |  |  |  |  | Plant QA | P5-2. Compliance indication check (final) (S-PAS/ICCS) P5-3. PP Evaluation
別途文書 |  | Production Quality Management Rules (PQMR) |  |  |  | Another Document |  | Production Quality Management Rules (PQMR)
文書管理 | [5 empty] | Document
記録物 |  | 議事録・発表資料 |  |  |  | Record Name |  | Meeting minutes, presentation material
管理部署 |  | 事業所製技 |  |  |  | Responsibility |  | Plant Production Eng.
保管場所・方法 |  | 規定せず |  |  |  | Where/How to keep |  | Not specified.
保管期限 |  | 10年 |  |  |  | Keeping Period |  | 10 years.
| *確認項目 | [5 empty] | *Confirmation items
Event Plan. Table

## P5-51
メインイベント | P5-51. MP画音質判定会議 |  |  |  |  | Main Event | P5-51. Judgment meeting for Picture/Sound performance at MP stage
目的 | MP品が設計チャンピオンと同等であることを判定する |  |  |  |  | Purpose | MP product is judged an equal thing with a design champion
承認者 | 事業所品証責任者 |  |  |  |  | Approval | Responsible person of Plant QA
開催部署 | 事業所品証 |  |  |  |  | Responsibility | Plant QA
参加者 | 商品設計, 画音質委員, 事業所製技, 事業所製造, 事業所品証 |  |  |  |  | Atendees | Product Design, PS Com member, Plant Production Eng, Plant Production, Plant QA
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 以下の実施方法のどちらかでMP品が設計チャンピオンと同等と判定されること。 | 画音質判定会議報告書、 測定データ結果 | Project |  |  |  | By either following method, MP product is judged an equal thing with a design champion. | PS Quality Judgment Meeting report, Data for P/S Judgment Mtg.
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Plant |  |  | 画質測定データ 音質測定データ |  |  | Plant |  |  | Picture measurement data Sound measurement data
事業所品証 | [5 empty] | Plant QA
別途文書 |  | FDR031-04 Form_画音質判定会議報告書 |  |  |  | Another Document |  | FDR031E-04 Form_PS Quality Judgment Meeting report
文書管理 | [5 empty] | Document
記録物 |  | 画音質判定会議報告書、 測定データ結果 |  |  |  | Record Name |  | PS Quality Judgment Meeting report, Data for P/S Judgment Mtg.
管理部署 |  | 事業所品証 |  |  |  | Responsibility |  | Plant QA
保管場所・方法 |  | e21 |  |  |  | Where/How to keep |  | e21
保管期限 |  | 3年 |  |  |  | Keeping Period |  | 3 years.
| 以下の実施方法のどちらかでMP品が設計チャンピオンと同等であることを判定する | [5 empty] | By either following method, MP product is judged an equal thing with a design champion.
| ① 設計画音質チャンピオンセットがある場合 | [5 empty] | 1 - When there is a design PS quality champion set.
| N=2以上のMP品画音質を設計画音質チャンピオンセットと比較評価を実施し、 | [5 empty] | To evaluate PS quality of MP product more than N=2 in comparison with the design PS quality champion set.
| 設計画音質チャンピオンセットと同等と判断されること。 | [5 empty] | It being judged to be equal with a design PS quality champion set.
| ② 設計画音質チャンピオンセットが無い場合 | [5 empty] | 2 - When there is not a design PS quality champion set.
| 1) 画質判定 | [5 empty] | 1) Picture quality judgment
| N=2以上のMPサンプルで以下の項目に関して測定を実施し、設計部より提示されている | [5 empty] | To perform the measurement with MP samples more than N=2 about the following items and confirm a certain thing in specifications in comparison with the picture quality champion data shown from design department.
画質チャンピオンデータと比較して規格内である事を確認する。
| ・ マクベスカラー測定 | [5 empty] | * Macbeth color measurement
| ・ ガンマデータ測定 | [5 empty] | * Gamma data measurement
| ・ 色度リニアリティデータ測定 | [5 empty] | * Chromaticity Linearity data measurement
| また、実施時には測定したN=2以上のMPサンプルを並べて画質確認し差分がない事を確認する。 | [5 empty] | To display MP samples more than measured N=2 and confirm a picture quality and confirm that there is not for difference.
| （差分がある場合には、測定データが規格内である事でOK判断を実施する） | [5 empty] | (When there is a difference, to confirm that there are measurement data in specifications and judge OK.)
| 2) 音質判定 | [5 empty] | 2) Sound quality judgment
| N=2以上のMPサンプルで設計部より支給された代表モデル（リファレンスモデル）との比較を実施し、同等である事を確認する。 | [5 empty] | To compare a representative model (a reference model) provided from design department with MP samples more than N=2 and confirm that these are equal.
| また、同時に以下のデータを測定し、規格内である事を確認する。 | [5 empty] | To measure the following data at the same time and confirm a certain thing in specifications.
| ・ 電気的測定 | [5 empty] | * Electric measurement
Event Plan. Table

## P5-80
メインイベント | P5-80. 初期出荷判定 (ISJ) |  |  |  |  | Main Event | P5-80. Initial Shipping Judgment (ISJ)
目的 | 商品への要求事項を満足しているか確認し出荷可否の判定を行う |  |  |  |  | Purpose | This meeting judge whether Products can be shipped out based on the ISJ confirmation items.
承認者 | 事業所品証責任者およびソニー品証部長 |  |  |  |  | Approval | Responsible person of Plant QA and Sony quality general manager
開催部署 | 事業所品証 |  |  |  |  | Responsibility | Plant QA
参加者 | 事業所品証，商品設計，品質評価（DR），事業所製技，事業所製造，事業所生産管理，事業所資材 |  |  |  |  | Atendees | Plant QA, Product Design, DCE, DR, Plant Production Eng, Plant Production, Plant Production Control, Plant Procurement
| Input |  |  | クライテリア | Output |  | Input |  |  | Criteria | Output
| 事前の実施事項 |  | 準備する書類 |  |  |  | Pre-implementation items |  | Documents to be prepared
Project |  |  |  | 下記要求事項に対し，不合格項目がないこと。 | 出荷判定会議の記録、及び、会議で使用した資料 | Project |  |  |  | There should not be any fail item on following PRM confirmation items. | Meeting minutes and shown material.
商品企画 | [5 empty] | Product Planning
開発設計 | [5 empty] | Development design
商品設計 | [5 empty] | Product Design
SW | [5 empty] | SW
Plant | [5 empty] | Plant
品証 | P5-51. MP画音質判定会議 |  |  |  |  | Plant QA | P5-51. Judgment meeting for Picture/Sound performance at MP stage
別途文書 |  | Production Quality Management Rules (PQMR) |  |  |  | Another Document |  | Production Quality Management Rules (PQMR)
文書管理 | [5 empty] | Document
記録物 |  | 出荷判定会議の記録、及び、会議で使用した資料 |  |  |  | Record Name |  | Meeting minutes and shown material.
管理部署 |  | 事業所品証 |  |  |  | Responsibility |  | Plant QA
保管場所・方法 |  | 規定せず |  |  |  | Where/How to keep |  | Not specified.
保管期限 |  | 10年 |  |  |  | Keeping Period |  | 10 years.
| *確認項目 | [5 empty] | *Confirmation items
Event Plan. Table

## P6-80
No. | P6-80 | No. | P6-80
Control Item | Commercialization Completion Judgment (CCJ) | Control Item | 商品化完了判定 (CCJ)
Event Requirement | Mandatory | Event Requirement | Mandatory
Responsibility | Product Design | Responsibility | 商品設計
Attendees | Product Design, QA, Device, plant, PIC of next model | Attendees | 商品設計、QA、デバイス設計、事業所、次年度モデル担当
Approval | Responsible person of Product Design | Approval | 商品設計責任者
Acceptation for ODM | #REF! | Acceptation for ODM | #REF!
Criteria, Rule, etc. | After complete model design, review about good point, bad point, goal attainment level etc. | Criteria, Rule, etc. | ・商品設計を終えて、良かった点、悪かった点、目標達成度などレビューを行う
| In addition, review the problems found before SSJ and to link to action of prevent recurrence |  | ・出荷開始判定までに発生した品質問題のレビューを行い、再発防止につなげる
| Feed back to next design team and it should be tied to improvement |  | ・次期商品設計チームに結果をフィードバックし、改善につなげる
Another Document | Non | Another Document | Non
Record Name | meeting minutes | Record Name | 議事録
Responsibility | Product Design | Responsibility | 商品設計
Where/How to keep | e21 | Where/How to keep | e21
Keeping Period | not provided | Keeping Period | not provided
Event Plan. Table
Event Plan. Table